## READ ME
NEW BALTIMORE — MATERIAL SURPLUS / SHORTAGE TRIAGE
Prepared by CVR Engineering · August 5, 2026 · Source-verified rebuild of the CWO reconciliation data
PURPOSE
One prioritized list of what appears over-ordered (return / restock candidates to free laydown space), what appears
under-ordered, and what has a CUE requirement but no captured order. Built from the project-wide rollup of the
15 CWO reconciliation workbooks (BOM vs CUE Material Summary vs PLS actual orders).
VALIDATION PERFORMED
CVR independently re-parsed the CUE Estimate PDF for CWO 73305080 (682 line items). Result: the reconciliation
workbook data matched the source exactly — 60/60 IM numbers, zero quantity mismatches, total cost identical
($36,177.10). Key finding: the "truncated" DTE IM numbers are only clipped visually in the PDF display; the full
18-digit values are intact in the PDF text layer and fully recoverable. No new DTE/CUE exports are required.
CAVEATS — READ BEFORE ACTING
1. CUE-side quantities are source-verified for one CWO (73305080); the other 14 CWOs used the same extraction
method but have not been line-checked. Spot-check before large-dollar decisions.
2. Actual Ordered quantities come from PLS Order Acknowledgment PDFs as captured in the reconciliation files.
Before physically returning anything, verify the line against the PLS PO record — request a line-item export
from PLS (IM, description, qty ordered, qty delivered, PO no., promise date). That export supersedes this file.
3. Unit costs are derived from CUE extended costs (cost ÷ qty) and are estimate-grade, for prioritization only.
4. "No captured order" can mean not ordered OR ordered outside the documents reviewed. Confirm with PLS.
5. 68 no-IM BOM rows across the project still need manual mapping (see the rollup workbook, No-IM tabs).
HOW TO USE (LEGEND)
Yellow cells are the only cells to edit: "Verified vs PLS?" (Y/N) and "Disposition / Action" (e.g., RETURN,
RESTOCK-YARD, KEEP-FUTURE-WO, ORDER, NO ACTION). Example: row 5 of Surplus tab might read Y ¦ RETURN — reel to PLS.
All other columns are data or formulas — do not overwrite. YARD flag = bulky item (poles, cable, crossarms, anchors).
IMMEDIATE YARD RELIEF (JOE): filter the Surplus tab on YARD = "YES" — cable reels and poles top the list.

## Inbound vs Triage (7-9-26)
OPEN ORDERS vs TRIAGE — ACTION LIST
Source: PLS Open Order Report NBALT as of 7/9/26 (197 open lines, line-item level with DTE IM). Open report shows undelivered lines only — delivered history not included.
A. STOP-SHIP REVIEW — already-surplus items with MORE inbound (cancel/reduce/divert BEFORE delivery; cheaper than returns, saves yard space)
DTE IM | Description | Surplus Today | Open Inbound Qty | Est. Unit Cost | Inbound Value at Risk | Expected Date(s) | Order / PO (lines) | Action (fill in)
300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | 2 | 48 | 3799.15 | 182359.2 | — | 12914382 L001
100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F | 169 | 260 | 138.81 | 36090.6 | 09/04/2026 | 12914023 L010
100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | 129 | 222 | 134.26 | 29805.72 | 09/04/2026 | 12914023 L012; 12914067 L014; 12914103 L008; 12914103 L009;
100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | 18 | 103 | 285.68 | 29425.04 | 07/29/2026 | 12914023 L025; 12914067 L037; 12914103 L022; 12914135 L028;
100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | 268 | 830 | 35.03 | 29074.9 | 08/11/2026 | 12914023 L051; 12914067 L065; 12914135 L058; 12914157 L057;
100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | 16 | 94 | 229.42 | 21565.48 | 07/23/2026 | 12914067 L070; 12914103 L051; 12914135 L061; 12914157 L059;
100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | 8 | 89 | 213.39 | 18991.71 | 07/29/2026 | 12914023 L054; 12914067 L073; 12914103 L052; 12914135 L063;
100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | 6 | 40 | 240.72 | 9628.8 | 07/29/2026 | 12914067 L074; 12914103 L053; 12914135 L064; 12914157 L062;
100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | 18 | 35 | 215.27 | 7534.45 | 09/04/2026 | 12914202 L015; 12914220 L013; 12914239 L015; 12914260 L009;
100336388 | CABLE_CNTRL,POWR AND CNTRL | 1 | 4 | 1332.49 | 5329.96 | — | 12914188 L070
100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | 6 | 132 | 35.09 | 4631.88 | — | 12914067 L064; 12914157 L056; 12914220 L043; 12914239 L053;
100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | 2 | 34 | 74.91 | 2546.94 | 09/04/2026 | 12914023 L014; 12914157 L014; 12914202 L014; 12914220 L012;
100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- | 17 | 65 | 38.46 | 2499.9 | 09/10/2026 | 12914202 L068; 12914260 L030; 12914361 L051
100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN | 74 | 200 | 10.23 | 2046 | 09/22/2026 | 12914023 L037
100052588 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,477K | 36 | 120 | 12.74 | 1528.8 | 10/30/2026 | 12914023 L017
100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 | 106 | 450 | 3.04 | 1368 | 11/11/2026 | 12914067 L021
100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 | 60 | 100 | 11.51 | 1151 | 09/22/2026 | 12914023 L036
100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT | 68 | 120 | 7.91 | 949.2 | 09/22/2026 | 12914067 L067
100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | 87 | 125 | 6.49 | 811.25 | 07/22/2026 | 12914067 L022; 12914188 L017; 12914202 L018; 12914239 L020;
100047695 | PIN_INSULATOR,HD,3/4 IN X 7 IN,GALV STL, | 19 | 60 | 12.76 | 765.6 | 08/19/2026 | 12914135 L051; 12914188 L053
100012488 | CUTOUT_FUSED,OPN,POLYMER,15KV MAX,110KV | 1 | 5 | 109.31 | 546.55 | 08/17/2026 | 12914135 L066; 12914188 L068; 12914333 L049; 12914340 L052
100106838 | PIN_INSULATOR,ANGLE XARM BRAKET,HOT DIPP | 12 | 23 | 13.27 | 305.21 | — | 12914023 L052; 12914135 L060
100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | 16 | 181 | 1.64 | 296.84 | 07/22/2026 | 12914067 L025; 12914103 L016; 12914135 L018; 12914157 L019;
100053167 | CLAMP_DEADEND,STRGHT LINE,MALLEABLE/DUCT | 14 | 5 | 15.01 | 75.05 | — | 12914239 L059a
100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | 46 | 8 | 0.75 | 6 | — | 12914359 L002
100015054 | Connector Wedge Al/Cu #6-#2 | 360 | 325 |  |  | 11/03/2026 | 12914023 L016; 12914103 L014; 12914157 L017; 12914202 L017;
100062712 | Connector Wedge Al/Cu #6-1/0 | 260 | 150 |  |  | 10/28/2026 | 12914135 L016; 12914188 L016; 12914340 L016
100035985 | 40kV Suspension Deadend Insulator | 3 | 3 |  |  | 08/25/2026 | 12914361 L048
| SUBTOTAL — inbound value at risk |  |  |  | 389334.08
B. SHORTAGES ALREADY COVERED BY OPEN ORDERS — do NOT re-buy these; inbound covers or exceeds the gap
DTE IM | Description | Shortfall (triage) | Open Inbound Qty | Covered? | Expected Date(s) | Note
100019342 | STRAP_GROUND,GALV STL | 264 | 500 | YES | 07/07/2026
100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | 16 | 391 | YES | TBD | Open qty far exceeds triage shortfall — order-ack capture was incomplete; open report is authoritative
100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC | 31 | 150 | YES | — | Open qty far exceeds triage shortfall — order-ack capture was incomplete; open report is authoritative
100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A | 140 | 50 | PARTIAL | 11/12/2026
100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | 1 | 50 | YES | 07/29/2026 | Open qty far exceeds triage shortfall — order-ack capture was incomplete; open report is authoritative
100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP | 56 | 44 | PARTIAL | —
300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | 2 | 35 | YES | — | Open qty far exceeds triage shortfall — order-ack capture was incomplete; open report is authoritative
100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | 6 | 30 | YES | 08/14/2026 | Open qty far exceeds triage shortfall — order-ack capture was incomplete; open report is authoritative
100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 | 27 | 25 | PARTIAL | 09/28/2026
100024531 | CONNECTOR_CABLE,PARRELL,ALUM,ACSR/ALUM,N | 3 | 25 | YES | — | Open qty far exceeds triage shortfall — order-ack capture was incomplete; open report is authoritative
100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN | 6 | 8 | YES | —
100302982 | BRACKET_MNTNG,POLETOP VRTCL,1-PHAS LP IN | 1 | 6 | YES | 08/11/2026 | Open qty far exceeds triage shortfall — order-ack capture was incomplete; open report is authoritative
C. KEY CHECKS
• ZERO items from the "Not Yet Ordered" tab appear in the open order report — that tab stands, pending closed-order history.
• NO WOOD POLES on PLS open order (only pole-mount transformers). The 81 cedar poles (~$187k est.) are NOT inbound from PLS —
confirm the pole supply chain (other supplier? closed order? unordered?) before assuming the delivery Joe expects.
• No past-due lines as of 7/9; statuses are Allocated / Not Past Due / On Hold. Several lines flagged "Req'd Expedite" with Sept-Nov expected dates.
• Open report covers open lines only. Delivered history still comes from the full line-item export (or the order acks already reviewed).

## Surplus – Return Candidates
SURPLUS – RETURN CANDIDATES
Actual ordered exceeds CUE requirement. Sorted by estimated value. Verify each line vs PLS before physical return. 91 items.
DTE IM | Description | UOM | # CWOs | Required (CUE) | Ordered (PLS) | Surplus Qty | Unit Cost (est) | Est. Value | YARD | Verified vs PLS? | Disposition / Action
100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 10 | 8206 | 37200.0001 | 28994.0001 | 1.28 | 37112.3201 | YES
100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 15 | 1078 | 1448 | 370 | 94.28 | 34883.6
100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 10 | 61866 | 86799.9999 | 24933.9999 | 1.09 | 27178.0599 | YES
100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F | EA | 9 | 91 | 260 | 169 | 138.81 | 23458.89
100079513 | NAIL_FASTENER,BARB,3/8 IN,2 IN LG,GALV S | EA | 2 | 32 | 3500 | 3468 | 6.2 | 21501.6
100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 13 | 93 | 222 | 129 | 134.26 | 17319.54
100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 13 | 562 | 830 | 268 | 35.03 | 9388.04
100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 11 | 68 | 83 | 15 | 544.84 | 8172.6 | YES
300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 11 | 49 | 51 | 2 | 3799.15 | 7598.3 | YES
100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 13 | 85 | 103 | 18 | 285.68 | 5142.24 | YES
100025788 | POLE_WOOD, PINE, 50FT, CL3 | EA | 5 | 35 | 43 | 8 | 604.66 | 4837.28 | YES
100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 15 | 227 | 305 | 78 | 55.54 | 4332.12
100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 8 | 17 | 35 | 18 | 215.27 | 3874.86
100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 10 | 78 | 94 | 16 | 229.42 | 3670.72
100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, | EA | 10 | 12 | 180 | 168 | 19.54 | 3282.72
100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 13 | 83 | 173 | 90 | 34.73 | 3125.7
100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 13 | 572 | 866 | 294 | 9.03 | 2654.82
100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 10 | 324 | 354 | 30 | 86.51 | 2595.3
100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 12 | 30 | 127 | 97 | 24.69 | 2394.93
100021353 | LINK_FUSE,UNV,30 AMP | EA | 12 | 22 | 290 | 268 | 7.17 | 1921.56
100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 12 | 38 | 84 | 46 | 39.73 | 1827.58 | YES
100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 15 | 1112 | 1729 | 617 | 2.93 | 1807.81
100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 11 | 81 | 89 | 8 | 213.39 | 1707.12 | YES
100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 8 | 126 | 220 | 94 | 16.56 | 1556.64
100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 11 | 34 | 40 | 6 | 240.72 | 1444.32 | YES
100336388 | CABLE_CNTRL,POWR AND CNTRL | EA | 1 | 3 | 4 | 1 | 1332.49 | 1332.49 | YES
100007836 | WIRE_TIE,NO. 8,CU,54 IN LG | FT | 4 | 11 | 500 | 489 | 2.55 | 1246.95
100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 14 | 756 | 1108 | 352 | 3.23 | 1136.96
100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 12 | 155 | 213 | 58 | 18.68 | 1083.44
100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 13 | 57894 | 60950 | 3056 | 0.33 | 1008.48 | YES
100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN | EA | 15 | 126 | 200 | 74 | 10.23 | 757.02
100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S | EA | 8 | 89 | 192 | 103 | 7.23 | 744.69
100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 15 | 342 | 560 | 218 | 3.24 | 706.32
100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 | EA | 9 | 40 | 100 | 60 | 11.51 | 690.6
100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- | EA | 6 | 48 | 65 | 17 | 38.46 | 653.82
100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | EA | 7 | 52 | 139 | 87 | 6.49 | 564.63
100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT | EA | 7 | 52 | 120 | 68 | 7.91 | 537.88
100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG | FT | 12 | 196 | 500 | 304 | 1.58 | 480.32
100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO | FT | 7 | 680 | 950 | 270 | 1.71 | 461.7 | YES
100052588 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,477K | EA | 5 | 84 | 120 | 36 | 12.74 | 458.64
100036858 | BRACKET_SUPPORT,TERMINATN/ARSTR | EA | 5 | 16 | 24 | 8 | 48.96 | 391.68
100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 10 | 74 | 111 | 37 | 9.11 | 337.07
100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 | EA | 12 | 344 | 450 | 106 | 3.04 | 322.24
100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 15 | 818 | 835 | 17 | 15.28 | 259.76
100047695 | PIN_INSULATOR,HD,3/4 IN X 7 IN,GALV STL, | EA | 3 | 41 | 60 | 19 | 12.76 | 242.44
100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 7 | 126 | 132 | 6 | 35.09 | 210.54
100053167 | CLAMP_DEADEND,STRGHT LINE,MALLEABLE/DUCT | EA | 3 | 16 | 30 | 14 | 15.01 | 210.14
100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 | EA | 7 | 107 | 150 | 43 | 4.33 | 186.19
100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 11 | 176 | 248 | 72 | 2.42 | 174.24
100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 11 | 22 | 94 | 72 | 2.32 | 167.04
100106838 | PIN_INSULATOR,ANGLE XARM BRAKET,HOT DIPP | EA | 5 | 11 | 23 | 12 | 13.27 | 159.24
100027126 | CLEVIS_STRN_INSUL,SECNDRY SRVC,PORCLN,1- | EA | 2 | 29 | 60 | 31 | 4.88 | 151.28
100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, | EA | 10 | 61 | 127 | 66 | 2.29 | 151.14
100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 8 | 32 | 34 | 2 | 74.91 | 149.82
100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 15 | 2280 | 3086 | 806 | 0.17 | 137.02
100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 15 | 2547 | 3776 | 1229 | 0.1 | 122.9
100012488 | CUTOUT_FUSED,OPN,POLYMER,15KV MAX,110KV | EA | 5 | 4 | 5 | 1 | 109.31 | 109.31
100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 10 | 130 | 161 | 31 | 2.88 | 89.28
100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T | EA | 8 | 14 | 20 | 6 | 14.61 | 87.66
100104417 | PIN_INSULATOR,XARM,5/8 IN X 6-1/2 IN,GAL | EA | 2 | 6 | 21 | 15 | 5.83 | 87.45
100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B | EA | 10 | 75 | 125 | 50 | 1.73 | 86.5
100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 | EA | 7 | 55 | 60 | 5 | 11.72 | 58.6
100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 15 | 327 | 339 | 12 | 3.79 | 45.48
100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 | EA | 8 | 43 | 62 | 19 | 2.31 | 43.89
100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC | EA | 10 | 188 | 195 | 7 | 5.16 | 36.12
100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 | EA | 8 | 70 | 246 | 176 | 0.2 | 35.2
100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 15 | 334 | 380 | 46 | 0.75 | 34.5
100007567 | CONNECTOR_OVERHEAD,FIRED ON,1/0 AWG,ALUM | EA | 2 | 10 | 20 | 10 | 3.03 | 30.3
100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 11 | 165 | 181 | 16 | 1.64 | 26.24
100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 14 | 869 | 993 | 124 | 0.17 | 21.08
100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 15 | 1205 | 1287 | 82 | 0.23 | 18.86
100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 14 | 249 | 251 | 2 | 8.13 | 16.26
100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 | EA | 10 | 86 | 100 | 14 | 0.92 | 12.88
100057790 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G | EA | 6 | 18 | 31 | 13 | 0.77 | 10.01
100030941 | LINK_FUSE,UNV,40 AMP | EA | 1 | 1 | 3 | 2 | 4.97 | 9.94
100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 10 | 101 | 118 | 17 | 0.38 | 6.46
100104745 | LINK_FUSE,UNV,25 AMP | EA | 2 | 3 | 4 | 1 | 3.53 | 3.53
100111213 | SCREW_LAG,1/4 IN DIA,2-1/2 IN LG,GALV ST | EA | 1 | 8 | 30 | 22 | 0.13 | 2.86
100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA | EA | 15 | 196 | 200 | 4 | 0.66 | 2.64
100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 15 | 516 | 517 | 1 | 1.48 | 1.48
100068975 | Fuse & Arrester Mounting Bracket | EA | 14 | 0 | 178 | 178
100015054 | Connector Wedge Al/Cu #6-#2 | EA | 9 | 0 | 360 | 360
100102696 | Guy Insulator Attachment | EA | 8 | 0 | 100 | 100
100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 7 | 0 | 139 | 139
100327860 | 3/4" x 7 3/4" Steel Pin with Lock Washer and Nut | EA | 6 | 0 | 80 | 80
100062712 | Connector Wedge Al/Cu #6-1/0 | EA | 4 | 0 | 260 | 260
100042507 | Bracket_mntng shield wire | EA | 2 | 0 | 11 | 11
100077194 | clamp susp 1/0 | EA | 2 | 0 | 10 | 10
100017083 | 5/8" ground rod connector | EA | 1 | 0 | 10 | 10
100024354 | 5/8" x 16 LG Machine Bolt | EA | 1 | 0 | 10 | 10
100035985 | 40kV Suspension Deadend Insulator | EA | 1 | 0 | 3 | 3
| TOTAL (est. value) | [6 empty] | 248901.88

## Shortage – Order Gaps
SHORTAGE – ORDER GAPS
CUE requirement exceeds captured orders. Confirm no order exists before buying. 53 items.
DTE IM | Description | UOM | # CWOs | Required (CUE) | Ordered (PLS) | Shortfall Qty | Unit Cost (est) | Est. Cost to Buy | YARD | Verified vs PLS? | Disposition / Action
100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP | EA | 10 | 100 | 44 | 56 | 229.42 | 12847.52
300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 9 | 28 | 26 | 2 | 5305.91 | 10611.82 | YES
100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L | FT | 15 | 12141 | 2307.1667 | 9833.8333 | 0.74 | 7277.0366 | YES
100042243 | POLE_WOOD, PINE, 60FT, CL 1 | EA | 5 | 11 | 7 | 4 | 1372.77 | 5491.08 | YES
100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 13 | 12328 | 7000 | 5328 | 0.84 | 4475.52 | YES
100069509 | POLE_WOOD, PINE, 50FT, CL 1 | EA | 5 | 15 | 11 | 4 | 860 | 3440 | YES
100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 13 | 747 | 514 | 233 | 10.5 | 2446.5
100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 14 | 505 | 402 | 103 | 21.7 | 2235.1
100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 | EA | 14 | 374 | 169 | 205 | 8.05 | 1650.25
100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A | EA | 11 | 190 | 50 | 140 | 9.71 | 1359.4
100042242 | POLE_WOOD, PINE, 55FT, CL 1 | EA | 7 | 27 | 26 | 1 | 1033.76 | 1033.76 | YES
100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | EA | 7 | 36 | 30 | 6 | 168.97 | 1013.82
100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 11 | 83 | 61 | 22 | 40.48 | 890.56
100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 11 | 83 | 69 | 14 | 60.69 | 849.66 | YES
100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL | LB | 15 | 247 | 51 | 196 | 3.98 | 780.08
100061029 | POLE_WOOD, PINE, 45FT, CL 1 | EA | 3 | 6 | 5 | 1 | 762.08 | 762.08 | YES
100065179 | MOUNT_TRNSCST,VEE,GALV STL,3 TRANSFRMRS, | EA | 4 | 6 | 3 | 3 | 237.97 | 713.91 | YES
100107159 | POLE_WOOD, PINE, 55FT, CL 3 | EA | 3 | 15 | 14 | 1 | 705.43 | 705.43 | YES
100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC | EA | 11 | 181 | 150 | 31 | 21.07 | 653.17
100019342 | STRAP_GROUND,GALV STL | EA | 15 | 764 | 500 | 264 | 1.9 | 501.6
100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 15 | 3696 | 3534 | 162 | 2.7 | 437.4
100018203 | POLE_WOOD, PINE, 40FT, CL 3 | EA | 3 | 5 | 4 | 1 | 436.45 | 436.45 | YES
100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 15 | 382 | 350 | 32 | 10.37 | 331.84
100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 13 | 51 | 50 | 1 | 297.3 | 297.3 | YES
100115241 | LINK_FUSE,UNV,15 AMP | EA | 13 | 160 | 98 | 62 | 4.35 | 269.7
100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 | EA | 11 | 167 | 160 | 7 | 35.88 | 251.16
100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S | EA | 7 | 160 | 102 | 58 | 3.54 | 205.32
100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 12 | 202 | 157 | 45 | 4.24 | 190.8
100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H | EA | 7 | 80 | 71 | 9 | 20.97 | 188.73
100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 11 | 99 | 74 | 25 | 7.47 | 186.75
100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS | EA | 7 | 29 | 22 | 7 | 22.41 | 156.87
100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 15 | 2391 | 2259 | 132 | 1.1 | 145.2
100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, | EA | 7 | 126 | 75 | 51 | 2.6 | 132.6
100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN | EA | 6 | 14 | 8 | 6 | 19.44 | 116.64 | YES
100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 | EA | 13 | 570 | 50 | 520 | 0.21 | 109.2
100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 | EA | 7 | 52 | 25 | 27 | 3.04 | 82.08
100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 14 | 412 | 411 | 1 | 72.97 | 72.97
100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL | EA | 13 | 124 | 26 | 98 | 0.7 | 68.6
100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM | EA | 7 | 43 | 32 | 11 | 6.17 | 67.87
100302982 | BRACKET_MNTNG,POLETOP VRTCL,1-PHAS LP IN | EA | 3 | 7 | 6 | 1 | 60.63 | 60.63
100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV | EA | 13 | 154 | 136 | 18 | 3.23 | 58.14
100317909 | CONNECTOR_TAP,SECNDRY H-TAP,ALUM | EA | 5 | 303 | 150 | 153 | 0.36 | 55.08
100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 12 | 152 | 127 | 25 | 1.93 | 48.25
100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 13 | 307 | 259 | 48 | 0.88 | 42.24
100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 15 | 543 | 527 | 16 | 2.27 | 36.32
100022671 | LINK_FUSE,UNV,20 AMP | EA | 2 | 33 | 28 | 5 | 4.33 | 21.65
100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR | EA | 8 | 70 | 57 | 13 | 1.44 | 18.72
100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, | EA | 11 | 94 | 85 | 9 | 1.49 | 13.41
100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 11 | 280 | 276 | 4 | 2.4 | 9.6
100024531 | CONNECTOR_CABLE,PARRELL,ALUM,ACSR/ALUM,N | EA | 2 | 28 | 25 | 3 | 2.57 | 7.71
100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 8 | 150 | 132 | 18 | 0.29 | 5.22
100019758 | NUT_SQUARE,5/8 IN,GALV STL,11 TPI | EA | 4 | 41 | 15 | 26 | 0.19 | 4.94
100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, | EA | 7 | 120 | 30 | 90 | 0.03 | 2.7
| TOTAL (est. value) | [6 empty] | 63870.3866

## Not Yet Ordered
NOT YET ORDERED
CUE requirement with NO captured order in reviewed documents — may be unordered OR ordered outside reviewed docs. 93 items.
DTE IM | Description | UOM | # CWOs | Required (CUE) | Unit Cost (est) | Est. Value | YARD | Verified vs PLS? | Disposition / Action
100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 7 | 81 | 2308.13 | 186958.53 | YES
300014341 | TRANSFORMER_DISTR,ISOLATION/OIL FILLED/P |  | 1 | 3 | 11127.15 | 33381.45 | YES
100332478 | SENSOR_CURRNT,LINE POST |  | 1 | 12 | 1349.39 | 16192.68
100289876 | POLE_WOOD,CEDAR,45 FT LG,CLASS 1 |  | 3 | 5 | 2949.44 | 14747.2 | YES
100341161 | POLE_WOOD,CEDAR,45 FT LG,CLASS 2 |  | 2 | 3 | 2603.39 | 7810.17 | YES
100313938 | POLE_WOOD,CEDAR,40 FT LG,CLASS 3 |  | 4 | 4 | 1891.65 | 7566.6 | YES
100302471 | CONTROL_CAPACITOR,OH CAPCTR CNTRL,13.8V, |  | 1 | 4 | 1796.82 | 7187.28
100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 14 | 5692 | 0.87 | 4952.04 | YES
100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 8 | 56 | 77.54 | 4342.24
100056487 | CABLE_BARE,1/0 AWG,CU,7 STRAND,ASTM B8/A |  | 1 | 2456 | 1.42 | 3487.52 | YES
100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 9 | 62 | 55.67 | 3451.54
100111680 | CABLE_INSUL,XLPE,3/0 AWG,ALUM,19 STRANDD |  | 1 | 896 | 3.64 | 3261.44 | YES
100289874 | POLE_WOOD,CEDAR,50 FT LG,CL 3,BUTT PRESE |  | 1 | 1 | 2677.57 | 2677.57 | YES
100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 8 | 3464 | 0.67 | 2320.88 | YES
100311653 | CONNECTOR_TAP,WDGE,ALUM ALLOY |  | 4 | 26 | 81.77 | 2126.02
100043112 | CABLE_INSUL,XLPE,1/0 AWG,CU,7 STRANDD,1 |  | 2 | 1118 | 1.85 | 2068.3 | YES
100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 10 | 147 | 13.26 | 1949.22
100027618 | CABLE_BARE,3/0 AWG,6 X 1 STRANDD,7670 FT |  | 3 | 5701 | 0.26 | 1482.26 | YES
100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 7 | 704 | 2.01 | 1415.04 | YES
100336386 | CABLE_CNTRL,POWR AND CNTRL |  | 1 | 1 | 1307.06 | 1307.06 | YES
100074003 | POLE_WOOD, PINE, 65FT, CL 2 |  | 1 | 1 | 1288.79 | 1288.79 | YES
100317530 | EXTENSION_POLE_TOP,60 IN LG,FBRGLAS |  | 1 | 2 | 613.75 | 1227.5 | YES
100031258 | PLATE_ADAPTER,MOUNTNG |  | 1 | 3 | 346.35 | 1039.05
100093755 | CABLE_INSUL,POWR,60 MIL XLPE,1/0 AWG,6 X |  | 3 | 1506 | 0.67 | 1009.02 | YES
100004957 | BASE_MNTNG,SIGN,10 IN WD,WOOD,8 IN LG |  | 1 | 4 | 202.18 | 808.72
100049677 | PADLOCK_ASSY,1-1/2 IN CASE |  | 1 | 6 | 112.96 | 677.76
100316436 | BRACKET_SUPPORT,CONDUIT STNDOFF,9 IN X 2 |  | 1 | 16 | 40.87 | 653.92 | YES
100342373 | POLE_WOOD,PINE,45 FT LG,CLASS 2 |  | 1 | 1 | 643.67 | 643.67 | YES
100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 8 | 28 | 20.59 | 576.52
100058551 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 2 | 31 | 16.56 | 513.36
100332479 | SENSOR_ACCESSORY,NEUTRAL |  | 1 | 1 | 498.52 | 498.52
100038906 | GUY_ASSY,5/16 IN DIA,165 FT LG,EHS STL S |  | 2 | 7 | 66.02 | 462.14
100065871 | CABLE_INSUL,60 MIL PE,1/0 AWG,HARD DRAWN |  | 2 | 307 | 1.16 | 356.12 | YES
100106252 | BRACE_SUPPORT,SIDWLK GUY,ZINC COATED STL |  | 2 | 3 | 104.74 | 314.22
100318537 | CONDUIT_RIGID,PVC,4 IN DIA,10 FT LG |  | 1 | 12 | 22.1 | 265.2 | YES
100064127 | LEAD_ELECT,SECNDRY,12 FT LG,ALUM, HARD D |  | 2 | 4 | 62.77 | 251.08
100078799 | BRACE_SUPPORT,SIDWLK GUY,ZINC COATED STL |  | 1 | 2 | 123.79 | 247.58
100303361 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 |  | 1 | 1 | 240.72 | 240.72 | YES
100110238 | PIN_INSULATOR,LAG SCRW,5/8 IN,GALV STL,8 |  | 6 | 22 | 7.83 | 172.26
100044155 | TUBE_ELECT,FUSE,4-1/2 IN OD,23 IN LG,PVC |  | 1 | 1 | 152.5 | 152.5
100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 7 | 160 | 0.95 | 152
100086522 | FITTING_SIDWLK,DUCTILE IRON |  | 3 | 5 | 26.72 | 133.6
100032501 | CABLE_INSUL,TRIPLEX,60 MIL HMPE,1/0 AWG, |  | 3 | 122 | 1.02 | 124.44 | YES
100056177 | CABLE_BARE,6 AWG,CU,SOLID,10000 FT LG,AS |  | 3 | 231 | 0.42 | 97.02 | YES
100024784 | MOUNT_TRNSCST,GALV STL,3 TRANSFRMRS,5/8 |  | 1 | 1 | 96.89 | 96.89 | YES
100035087 | LINK_CHAIN,1 IN X 3-1/4 IN,GALV STL,5/8 |  | 4 | 14 | 6.22 | 87.08
100017509 | LEAD_ELECT,SECNDRY,12 FT LG,CU,4/0 AWG |  | 2 | 2 | 43.18 | 86.36
100073793 | GUARD_PROTCT,U CABLE,2-1/4 IN WD,PLSTC,6 |  | 1 | 18 | 4.5 | 81
100335234 | STIRRUP_HYDRANT,DISC,4-5/8 X 4-5/8 X 2-5 |  | 1 | 3 | 26.13 | 78.39
100316438 | STRAP_CONDUIT,KIT,4 IN |  | 1 | 16 | 4.88 | 78.08 | YES
100013784 | INSULATOR_STRAIN,GUY,30 IN LG,FBRGLAS 24 |  | 2 | 5 | 15.46 | 77.3
100038866 | RACK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS |  | 2 | 2 | 36 | 72
100089247 | BOLT_MACHINE,5/8 IN DIA,11 TPI,34 IN LG, |  | 1 | 8 | 8.54 | 68.32
100005379 | SIGN_WARNING,PLSTC,BLK/WHITE,SCRWED |  | 1 | 4 | 16.47 | 65.88
100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 7 | 126 | 0.44 | 55.44
100069647 | WIRE_TIE,NO. 8,CU,45 IN LG |  | 6 | 36 | 1.39 | 50.04
100010817 | CONNECTOR_OVERHEAD,FIRED ON,NO. 2-556.5 |  | 1 | 3 | 16.62 | 49.86
100057912 | BOLT_MACHINE,3/4 IN DIA,10 TPI,14 IN LG, |  | 4 | 18 | 2.43 | 43.74
100055729 | CONNECTOR_CABLE,BARTAP,TINNED BRNZ,NO.6- |  | 2 | 5 | 8.25 | 41.25
100116153 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,NO.1 |  | 1 | 3 | 13.1 | 39.3
100046669 | BOLT_MACHINE,5/8 IN DIA,11 TPI,4 IN LG,G |  | 4 | 31 | 1.26 | 39.06
100098069 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,N |  | 1 | 3 | 12.74 | 38.22
100310066 | STRAP_GROUND,C-CLAMP,1.08 X 0.50 IN,STL, |  | 1 | 8 | 4.11 | 32.88
100001517 | LINK_FUSE,UNV,10 AMP |  | 2 | 10 | 2.93 | 29.3
100308950 | CONNECTOR_CABLE,GRND,NO. 6 SOLID TO 1/0 |  | 2 | 5 | 5.21 | 26.05
100352548 | CAP_END,BUMP,1.24 IN X 1.165 IN,PLSTC/RU |  | 1 | 8 | 3.25 | 26
100097571 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC. |  | 1 | 4 | 5.16 | 20.64
100076569 | BOLT_MACHINE,3/4 IN DIA,10 TPI,12 IN LG, |  | 3 | 10 | 1.98 | 19.8
100037863 | BOLT_MACHINE,5/8 IN DIA,11 TPI,30 IN LG, |  | 1 | 8 | 2.45 | 19.6
100072154 | SCREW_LAG, 1/4 IN DIA,2 IN LG,GALV STL,HE |  | 1 | 150 | 0.12 | 18
100039661 | BOLT_MACHINE,5/8 IN DIA,11 TPI,2 IN LG,G |  | 4 | 18 | 0.99 | 17.82
100040596 | CONNECTOR_CABLE,TAP,BRNZ,CU,4/0 AWG,2-HO |  | 1 | 2 | 7.85 | 15.7
100326132 | COVER_PROTCT,ANIMAL CONDUCTOR COVER,SILC |  | 1 | 1 | 14.99 | 14.99
100084565 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,1 |  | 2 | 4 | 3.04 | 12.16
100113829 | BOLT_EYE,5/8 IN DIA,11 TPI,10 IN LG,GALV |  | 2 | 4 | 2.75 | 11
100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 7 | 28 | 0.35 | 9.8
100042925 | FUSE_CURRNT_LIMIT,FAULT TAMER,15KV,10T A |  | 1 | 1 | 9.1 | 9.1
100071576 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,2 AC |  | 1 | 1 | 8.86 | 8.86
100088375 | RACK_INSULATOR,SUSPN,8 IN WIRE SPACING |  | 1 | 1 | 8.73 | 8.73
100039664 | WASHER_FLAT,3/4 IN ID,2 IN OD,WROUGHT ST |  | 4 | 22 | 0.33 | 7.26
100073619 | BOLT_EYE,5/8 IN DIA,11 TPI,14 INLG,GALV |  | 1 | 2 | 3.39 | 6.78
100108945 | INSULATOR_STRAIN,GUY,LARGE,PORCLN,SKY,5/ |  | 1 | 3 | 2.07 | 6.21
100301538 | CABLE_INSUL,TRIPLEX,XLPE,4/0 AWG,ALUM,19 |  | 1 | 4 | 1.49 | 5.96 | YES
100094846 | SCREW_LAG,3/8 IN DIA,4 IN LG,HOT DIP GAL |  | 4 | 12 | 0.46 | 5.52
100101973 | SIGN_WARNING,WHITE/YELW,480 VOLT,SCRWED |  | 1 | 1 | 5.49 | 5.49
100302469 | ENCLOSURE_ELECT,JUNCTION BOX,8 IN WD,8 I |  | 1 | 3 | 1 | 3
100095014 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 1 | 3 | 0.6 | 1.8
100058033 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 1 | 3 | 0.56 | 1.68
100050811 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 1 | 3 | 0.55 | 1.65
100084202 | BOLT_MACHINE,3/8 IN DIA,16 TPI,10 IN LG, |  | 1 | 1 | 1.5 | 1.5
100302470 | ENCLOSURE_ELECT,JUNCTION BOX,8 IN WD,8 I |  | 1 | 1 | 1 | 1
100057791 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G |  | 1 | 1 | 0.77 | 0.77
100030339 | CABLE_INSUL,XLPE,1/0 AWG,ALUM,7 STRANDD |  | 1 | 1 | 0.3 | 0.3 | YES
| TOTAL (est. value) |  |  |  |  | 322088.31

## PLS PO $ Summary (7-28-26)
PLS PURCHASE ORDER FINANCIAL SUMMARY — AS OF 7/28/2026
Source: PLS Purchase Order Report 7/28/2026 (PO-header level — dollars only, no line items/IMs). Blue = source data. CUE Est $ from CWO reconciliation workbooks.
CWO / Project | # POs | Original PO $ | PO Changes $ | Current PO $ | Invoiced $ | Outstanding $ | CUE Material Est $ | Current PO − CUE $ | Note
25000209 | 3 | 339027.28 | -72273.96 | 266753.32 | 48301.95 | 218451.08 |  |  | Project-level POs; incl. the -$72,274 reduction (verify vs the 8 planned UG PO cancellations)
73232522 | 2 | 89207.76 | 0 | 89207.76 | 77933.08 | 11274.68 | 143455.15 | -54247.39
73234686 | 1 | 51330.84 | 143.95 | 51474.79 | 51474.79 | 0 | 114600.29 | -63125.5
73239897 | 2 | 62027.79 | 0 | 62027.79 | 52653.07 | 9374.72 | 113119.61 | -51091.82
73239916 | 1 | 34392.61 | 0 | 34392.61 | 31846.92 | 2545.69 | 181388.96 | -146996.35
73239926 | 2 | 45389.08 | 0 | 45389.08 | 30739.26 | 14649.82 | 107363.49 | -61974.41
73240913 | 2 | 69409.08 | 0 | 69409.08 | 68901.64 | 507.44 | 193534.58 | -124125.5
73242557 | 1 | 33593.42 | 0 | 33593.42 | 33255.12 | 338.3 | 66525.33 | -32931.91
73242619 | 1 | 31417.99 | 0 | 31417.99 | 30572.25 | 845.74 | 65028.72 | -33610.73
73244139 | 1 | 39371.04 | 0 | 39371.04 | 39371.04 | 0 | 102398.73 | -63027.69
73279347 | 1 | 26954.81 | 0 | 26954.81 | 22142.85 | 4811.96 | 25975.2 | 979.61
73301547 | 1 | 41701.22 | 0 | 41701.22 | 40009.73 | 1691.49 | 93529.72 | -51828.5
73301585 | 1 | 75031.46 | 0 | 75031.46 | 74016.57 | 1014.89 | 84563.74 | -9532.28
73305080 | 1 | 13391.22 | 0 | 13391.22 | 12714.62 | 676.6 | 36177.1 | -22785.88
73346088 | 1 | 51878.42 | 0 | 51878.42 | 51757.02 | 121.4 |  |  | PO exists but CWO not in the 15 reconciliation workbooks — coverage gap
73358165 | 1 | 2754.76 | 0 | 2754.76 | 2754.76 | 0 | 7005.13 | -4250.37
73802595 | 1 | 18709.16 | 0 | 18709.16 | 18117.14 | 592.02 | 43971.25 | -25262.09
TOTAL | 23 | 1025587.94 | -72130.01 | 953457.93 | 686561.81 | 266895.83 | 1378637 | -425179.07
READ THIS BEFORE INTERPRETING THE GAP:
The "Current PO − CUE" gap does NOT automatically mean under-procurement. Likely explanations, in order:
1. DTE-supplied job stock — the CUE summaries are storeroom JSTK (job stock); a portion of material may be DTE-furnished, never a PLS PO.
2. Not-yet-ordered material (see Not Yet Ordered tab, ~$322k est.) — including the 81 cedar poles, which may also come from a non-PLS pole supplier.
3. Suppliers other than PLS for select items.
4. CUE estimate-grade pricing vs actual PO pricing.
WHAT THIS REPORT CLOSES: committed material dollars per CWO ($953k current, $687k invoiced, $267k outstanding) — the committed-cost input for the GP analysis.
WHAT IT DOES NOT CLOSE: per-IM quantity verification. This report is PO-header level. Still needed from PLS: LINE-ITEM detail (IM, qty ordered, qty delivered, PO no.).
CANCELLATION WATCH: only ONE reduction (-$72,274 on 25000209/M-00001) appears as of 7/28. If 8 underground POs are to be cancelled, the remaining reductions have not
hit this report yet — outstanding commitment is overstated until they do. Track future report versions against this baseline.
COVERAGE GAP: CWO 73346088 has a PLS PO ($51,878) but no reconciliation workbook — add it to the set.

## Open Order Detail (7-9-26)
Order | Line | PO | CWO | DTE IM (CPN) | Description | Qty Ordered | Qty Allocated | Qty Invoiced | Open Qty | Status | Expected Date | Notes
12914023 | 029 | 25000209/M-00002 | 73232522 | 100097490 | Anchor Helix 10in 6000lb 5/8in Rod | 8 | 8 | 0 | 8 | Allocated
12914023 | 051 | 25000209/M-00002 | 73232522 | 100301153 | Base Gain Galv With 9in Offset | 40 | 40 | 0 | 40 | Allocated
12914023 | 052 | 25000209/M-00002 | 73232522 | 100106838 | Bracket Angle Pin 1in Nylon Thread Pin | 3 | 3 | 0 | 3 | Allocated
12914023 | 010 | 25000209/M-00002 | 73232522 | 100328220 | Bracket Standoff 15 Deg 1ph 24in | 260 | 0 | 0 | 260 | Not Past Due | 09/04/2026 | Req'd Expedite
12914023 | 014 | 25000209/M-00002 | 73232522 | 100310427 | Bracket Standoff FG 1.5inX48in w/HD | 6 | 0 | 0 | 6 | Not Past Due | 09/04/2026 | Req'd Expedite
12914023 | 012 | 25000209/M-00002 | 73232522 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 17 | 14 | 0 | 17 | Not Past Due | 09/04/2026 | Req'd Expedite
12914023 | 017 | 25000209/M-00002 | 73232522 | 100052588 | Connector Wedge Al 477-636kcmil | 120 | 0 | 0 | 120 | Not Past Due | 10/30/2026 | Req'd Expedite
12914023 | 016 | 25000209/M-00002 | 73232522 | 100015054 | Connector Wedge Al/Cu #6-#2 | 60 | 0 | 0 | 60 | Not Past Due | 11/03/2026 | Req'd Expedite
12914023 | 054 | 25000209/M-00002 | 73232522 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 4 | 0 | 0 | 4 | Not Past Due | 07/29/2026
12914023 | 025 | 25000209/M-00002 | 73232522 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 4 | 0 | 0 | 4 | Not Past Due | 07/29/2026
12914023 | 036 | 25000209/M-00002 | 73232522 | 100008748 | Insulator Guy Strain 16k 18in Clev/Clev | 100 | 0 | 0 | 100 | Not Past Due | 09/22/2026 | Req'd Expedite
12914023 | 037 | 25000209/M-00002 | 73232522 | 100051352 | Insulator Guy Strain 16k 18in Clev/Eye | 200 | 0 | 0 | 200 | Not Past Due | 09/22/2026 | Req'd Expedite
12914067 | 050 | 25000209/M-00002 | 73234686 | 100321662 | Attachment Guy Pole eye plate | 150 | 150 | 0 | 150 | Allocated
12914067 | 065 | 25000209/M-00002 | 73234686 | 100301153 | Base Gain Galv With 9in Offset | 55 | 55 | 0 | 55 | Allocated
12914067 | 067 | 25000209/M-00002 | 73234686 | 100088112 | Bracket Neutral Wire Malleable Iron Galv | 120 | 0 | 0 | 120 | Not Past Due | 09/22/2026 | Req'd Expedite
12914067 | 014 | 25000209/M-00002 | 73234686 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 7 | 7 | 0 | 7 | Allocated
12914067 | 021 | 25000209/M-00002 | 73234686 | 100043150 | Connector Wedge Al/Cu #2-4/0 | 450 | 0 | 0 | 450 | Not Past Due | 11/11/2026 | Req'd Expedite
12914067 | 073 | 25000209/M-00002 | 73234686 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 4 | 0 | 0 | 4 | Not Past Due | 07/29/2026
12914067 | 036 | 25000209/M-00002 | 73234686 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 4 | 0 | 0 | 4 | Not Past Due | 07/29/2026
12914067 | 037 | 25000209/M-00002 | 73234686 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 12 | 0 | 0 | 12 | Not Past Due | 07/29/2026
12914067 | 074 | 25000209/M-00002 | 73234686 | 100303366 | Crossarm FG 3-5/8inX4-5/8inX120in Tangnt | 5 | 0 | 0 | 5 | Not Past Due | 07/29/2026
12914067 | 069 | 25000209/M-00002 | 73234686 | 100339982 | Cutout Polymer L Open 15.5kV 110kV BIL | 5 | 5 | 0 | 5 | Allocated
12914067 | 070 | 25000209/M-00002 | 73234686 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 15 | 0 | 0 | 15 | Not Past Due | 07/23/2026
12914067 | 025 | 25000209/M-00002 | 73234686 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 4 | 0 | 0 | 4 | Not Past Due | 07/22/2026
12914067 | 064 | 25000209/M-00002 | 73234686 | 100322238 | Insulator Riser Support 28kV sil rubber | 6 | 6 | 0 | 6 | Allocated
12914067 | 034a | 25000209/M-00002 | 73234686 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 10 | 9 | 0 | 10 | Not Past Due | 08/24/2026
12914067 | 022 | 25000209/M-00002 | 73234686 | 100074602 | Rod Armor Al .491-.521 Sgl 56in 11/set | 5 | 0 | 0 | 5 | Not Past Due | 07/22/2026
12914067 | 016 | 25000209/M-00002 | 73234686 | 100019342 | Strap Grnd Steel Galv DE Spec 121 Rev | 500 | 0 | 0 | 500 | Not Past Due | 07/07/2026
12914067 | 035 | 25000209/M-00002 | 73234686 | 100054802 | Switch disc 13.2kV 600a hookstick poly | 3 | 0 | 0 | 3 | Not Past Due | 08/14/2026
12914103 | 008 | 25000209/M-00002 | 73239897 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 30 | 30 | 0 | 30 | Allocated
12914103 | 009 | 25000209/M-00002 | 73239897 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 24 | 24 | 0 | 24 | Allocated
12914103 | 014 | 25000209/M-00002 | 73239897 | 100015054 | Connector Wedge Al/Cu #6-#2 | 44 | 0 | 0 | 44 | Not Past Due | 11/03/2026 | Req'd Expedite
12914103 | 052 | 25000209/M-00002 | 73239897 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 7 | 0 | 0 | 7 | Not Past Due | 07/29/2026
12914103 | 021 | 25000209/M-00002 | 73239897 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 2 | 0 | 0 | 2 | Not Past Due | 07/29/2026
12914103 | 022 | 25000209/M-00002 | 73239897 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 3 | 0 | 0 | 3 | Not Past Due | 07/29/2026
12914103 | 053 | 25000209/M-00002 | 73239897 | 100303366 | Crossarm FG 3-5/8inX4-5/8inX120in Tangnt | 1 | 0 | 0 | 1 | Not Past Due | 07/29/2026
12914103 | 050 | 25000209/M-00002 | 73239897 | 100339982 | Cutout Polymer L Open 15.5kV 110kV BIL | 27 | 27 | 0 | 27 | Allocated
12914103 | 051 | 25000209/M-00002 | 73239897 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 1 | 0 | 0 | 1 | Not Past Due | 07/23/2026
12914103 | 016 | 25000209/M-00002 | 73239897 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 3 | 0 | 0 | 3 | Not Past Due | 07/22/2026
12914103 | 011 | 25000209/M-00002 | 73239897 | 100110298 | Indicator Fault Navigator 24Hr Reset | 1 | 1 | 0 | 1 | Allocated
12914135 | 058 | 25000209/M-00002 | 73239916 | 100301153 | Base Gain Galv With 9in Offset | 13 | 13 | 0 | 13 | Allocated
12914135 | 060 | 25000209/M-00002 | 73239916 | 100106838 | Bracket Angle Pin 1in Nylon Thread Pin | 20 | 20 | 0 | 20 | Allocated
12914135 | 010 | 25000209/M-00002 | 73239916 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 14 | 14 | 0 | 14 | Allocated
12914135 | 015 | 25000209/M-00002 | 73239916 | 100043158 | Connector Wedge Al 1/0 to 3/0 | 50 | 0 | 0 | 50 | Not Past Due | 11/12/2026 | Req'd Expedite
12914135 | 016 | 25000209/M-00002 | 73239916 | 100062712 | Connector Wedge Al/Cu #6-1/0 | 70 | 0 | 0 | 70 | Not Past Due | 10/28/2026 | Req'd Expedite
12914135 | 063 | 25000209/M-00002 | 73239916 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 5 | 0 | 0 | 5 | Not Past Due | 07/29/2026
12914135 | 027 | 25000209/M-00002 | 73239916 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 1 | 0 | 0 | 1 | Not Past Due | 07/29/2026
12914135 | 028 | 25000209/M-00002 | 73239916 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 31 | 0 | 0 | 31 | Not Past Due | 07/29/2026
12914135 | 064 | 25000209/M-00002 | 73239916 | 100303366 | Crossarm FG 3-5/8inX4-5/8inX120in Tangnt | 5 | 0 | 0 | 5 | Not Past Due | 07/29/2026
12914135 | 061 | 25000209/M-00002 | 73239916 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 25 | 0 | 0 | 25 | Not Past Due | 07/23/2026
12914135 | 066 | 25000209/M-00002 | 73239916 | 100012488 | Cutout SPL 15kV 200a VAR 084 | 1 | 0 | 0 | 1 | Not Past Due | 08/17/2026
12914135 | 018 | 25000209/M-00002 | 73239916 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 25 | 0 | 0 | 25 | Not Past Due | 07/22/2026
12914135 | 051 | 25000209/M-00002 | 73239916 | 100047695 | Insulator Pin Crossarm HV 1in x 7in | 20 | 0 | 0 | 20 | Not Past Due | 08/19/2026
12914135 | 067 | 25000209/M-00002 | 73239916 | YCA282N | Lug 4/0 Cu 2-Hole Nema | 71 | 0 | 0 | 71 | Not Past Due | 08/17/2026
12914135 | 019 | 25000209/M-00002 | 73239916 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 72 | 0 | 34 | 38 | Not Past Due | TBD
12914135 | 025a | 25000209/M-00002 | 73239916 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 6 | 6 | 0 | 6 | Allocated
12914135 | 026 | 25000209/M-00002 | 73239916 | 100054802 | Switch disc 13.2kV 600a hookstick poly | 3 | 0 | 0 | 3 | Not Past Due | 08/14/2026
12914144 | 001 | 25000209/M-00002 |  | ORCHID | Wire Orchid 636-37 AAC OH | 86800 | 0 | 0 | 86800 | Not Past Due | 10/13/2026
12914157 | 057 | 25000209/M-00002 | 73239926 | 100301153 | Base Gain Galv With 9in Offset | 25 | 25 | 0 | 25 | Allocated
12914157 | 014 | 25000209/M-00002 | 73239926 | 100310427 | Bracket Standoff FG 1.5inX48in w/HD | 13 | 0 | 0 | 13 | Not Past Due | 09/04/2026 | Req'd Expedite
12914157 | 012 | 25000209/M-00002 | 73239926 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 1 | 1 | 0 | 1 | Allocated
12914157 | 017 | 25000209/M-00002 | 73239926 | 100015054 | Connector Wedge Al/Cu #6-#2 | 50 | 0 | 0 | 50 | Not Past Due | 11/03/2026 | Req'd Expedite
12914157 | 027 | 25000209/M-00002 | 73239926 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 4 | 0 | 0 | 4 | Not Past Due | 07/29/2026
12914157 | 028 | 25000209/M-00002 | 73239926 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 2 | 0 | 0 | 2 | Not Past Due | 07/29/2026
12914157 | 062 | 25000209/M-00002 | 73239926 | 100303366 | Crossarm FG 3-5/8inX4-5/8inX120in Tangnt | 7 | 0 | 0 | 7 | Not Past Due | 07/29/2026
12914157 | 061 | 25000209/M-00002 | 73239926 | 100089217 | Crossarm FG 3-5/8inX4-5/8inX48in Tangent | 2 | 0 | 0 | 2 | Not Past Due | 07/29/2026
12914157 | 059 | 25000209/M-00002 | 73239926 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 10 | 0 | 0 | 10 | Not Past Due | 07/23/2026
12914157 | 019 | 25000209/M-00002 | 73239926 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 30 | 0 | 0 | 30 | Not Past Due | 07/22/2026
12914157 | 056 | 25000209/M-00002 | 73239926 | 100322238 | Insulator Riser Support 28kV sil rubber | 3 | 3 | 0 | 3 | Allocated
12914157 | 020 | 25000209/M-00002 | 73239926 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 25 | 0 | 0 | 25 | Not Past Due | TBD
12914157 | 025a | 25000209/M-00002 | 73239926 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 20 | 20 | 0 | 20 | Allocated
12914157 | 026 | 25000209/M-00002 | 73239926 | 100054802 | Switch disc 13.2kV 600a hookstick poly | 3 | 0 | 0 | 3 | Not Past Due | 08/14/2026
12914188 | 058 | 25000209/M-00002 | 73240913 | 100301153 | Base Gain Galv With 9in Offset | 35 | 35 | 0 | 35 | Allocated
12914188 | 011 | 25000209/M-00002 | 73240913 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 11 | 11 | 0 | 11 | Allocated
12914188 | 070 | 25000209/M-00002 | 73240913 | 100336388 | Cable Connector 50ft GEN2 3 to 1 8 PIN | 4 | 4 | 0 | 4 | Allocated
12914188 | 060 | 25000209/M-00002 | 73240913 | 100024531 | Connector PG Al #8-2/0ACSR 3/8in | 25 | 25 | 0 | 25 | Allocated
12914188 | 016 | 25000209/M-00002 | 73240913 | 100062712 | Connector Wedge Al/Cu #6-1/0 | 60 | 0 | 0 | 60 | Not Past Due | 10/28/2026 | Req'd Expedite
12914188 | 015 | 25000209/M-00002 | 73240913 | 100108386 | Connector Wedge Al/Cu #6-3/0 | 25 | 0 | 0 | 25 | Not Past Due | 09/28/2026 | Req'd Expedite
12914188 | 065 | 25000209/M-00002 | 73240913 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 40 | 0 | 0 | 40 | Not Past Due | 07/29/2026
12914188 | 028 | 25000209/M-00002 | 73240913 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 10 | 0 | 0 | 10 | Not Past Due | 07/29/2026
12914188 | 029 | 25000209/M-00002 | 73240913 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 18 | 0 | 0 | 18 | Not Past Due | 07/29/2026
12914188 | 066 | 25000209/M-00002 | 73240913 | 100303366 | Crossarm FG 3-5/8inX4-5/8inX120in Tangnt | 15 | 0 | 0 | 15 | Not Past Due | 07/29/2026
12914188 | 062 | 25000209/M-00002 | 73240913 | 100339982 | Cutout Polymer L Open 15.5kV 110kV BIL | 7 | 7 | 0 | 7 | Allocated
12914188 | 063 | 25000209/M-00002 | 73240913 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 6 | 0 | 0 | 6 | Not Past Due | 07/23/2026
12914188 | 068 | 25000209/M-00002 | 73240913 | 100012488 | Cutout SPL 15kV 200a VAR 084 | 1 | 0 | 0 | 1 | Not Past Due | 08/17/2026
12914188 | 019 | 25000209/M-00002 | 73240913 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 60 | 0 | 0 | 60 | Not Past Due | 07/22/2026
12914188 | 053 | 25000209/M-00002 | 73240913 | 100047695 | Insulator Pin Crossarm HV 1in x 7in | 40 | 0 | 0 | 40 | Not Past Due | 08/19/2026
12914188 | 020 | 25000209/M-00002 | 73240913 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 30 | 0 | 0 | 30 | Not Past Due | TBD
12914188 | 026a | 25000209/M-00002 | 73240913 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 25 | 25 | 0 | 25 | Allocated
12914188 | 017 | 25000209/M-00002 | 73240913 | 100074602 | Rod Armor Al .491-.521 Sgl 56in 11/set | 24 | 0 | 0 | 24 | Not Past Due | 07/22/2026
12914188 | 027 | 25000209/M-00002 | 73240913 | 100054802 | Switch disc 13.2kV 600a hookstick poly | 6 | 0 | 0 | 6 | Not Past Due | 08/14/2026
12914202 | 060 | 25000209/M-00002 | 73242557 | 100301153 | Base Gain Galv With 9in Offset | 43 | 33 | 0 | 43 | Not Past Due | 08/11/2026
12914202 | 015 | 25000209/M-00002 | 73242557 | 100310428 | Bracket Standoff 3Ph 48in 24in 7H | 6 | 0 | 0 | 6 | Not Past Due | 09/04/2026 | Req'd Expedite
12914202 | 014 | 25000209/M-00002 | 73242557 | 100310427 | Bracket Standoff FG 1.5inX48in w/HD | 2 | 0 | 0 | 2 | Not Past Due | 09/04/2026 | Req'd Expedite
12914202 | 012 | 25000209/M-00002 | 73242557 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 40 | 40 | 0 | 40 | Allocated
12914202 | 017 | 25000209/M-00002 | 73242557 | 100015054 | Connector Wedge Al/Cu #6-#2 | 50 | 0 | 0 | 50 | Not Past Due | 11/03/2026 | Req'd Expedite
12914202 | 064 | 25000209/M-00002 | 73242557 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 3 | 0 | 0 | 3 | Not Past Due | 07/29/2026
12914202 | 029 | 25000209/M-00002 | 73242557 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 3 | 0 | 0 | 3 | Not Past Due | 07/29/2026
12914202 | 030 | 25000209/M-00002 | 73242557 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 7 | 0 | 0 | 7 | Not Past Due | 07/29/2026
12914202 | 065 | 25000209/M-00002 | 73242557 | 100303366 | Crossarm FG 3-5/8inX4-5/8inX120in Tangnt | 4 | 0 | 0 | 4 | Not Past Due | 07/29/2026
12914202 | 063 | 25000209/M-00002 | 73242557 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 10 | 0 | 0 | 10 | Not Past Due | 07/23/2026
12914202 | 020 | 25000209/M-00002 | 73242557 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 5 | 0 | 0 | 5 | Not Past Due | 07/22/2026
12914202 | 021 | 25000209/M-00002 | 73242557 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 20 | 0 | 0 | 20 | Not Past Due | TBD
12914202 | 028a | 25000209/M-00002 | 73242557 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 5 | 5 | 0 | 5 | Allocated
12914202 | 018 | 25000209/M-00002 | 73242557 | 100074602 | Rod Armor Al .491-.521 Sgl 56in 11/set | 18 | 0 | 0 | 18 | Not Past Due | 07/22/2026
12914202 | 068 | 25000209/M-00002 | 73242557 | 100103235 | Stirrup Wejtap Alum 477 To 636 1/0 Bail | 25 | 0 | 0 | 25 | Not Past Due | 09/10/2026 | Req'd Expedite
12914220 | 044 | 25000209/M-00002 | 73242619 | 100301153 | Base Gain Galv With 9in Offset | 29 | 29 | 0 | 29 | Allocated
12914220 | 013 | 25000209/M-00002 | 73242619 | 100310428 | Bracket Standoff 3Ph 48in 24in 7H | 6 | 0 | 0 | 6 | Not Past Due | 09/04/2026 | Req'd Expedite
12914220 | 012 | 25000209/M-00002 | 73242619 | 100310427 | Bracket Standoff FG 1.5inX48in w/HD | 4 | 0 | 0 | 4 | Not Past Due | 09/04/2026 | Req'd Expedite
12914220 | 010 | 25000209/M-00002 | 73242619 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 23 | 23 | 0 | 23 | Allocated
12914220 | 016 | 25000209/M-00002 | 73242619 | 100015054 | Connector Wedge Al/Cu #6-#2 | 30 | 0 | 0 | 30 | Not Past Due | 11/03/2026 | Req'd Expedite
12914220 | 047 | 25000209/M-00002 | 73242619 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 12 | 0 | 0 | 12 | Not Past Due | 07/29/2026
12914220 | 024 | 25000209/M-00002 | 73242619 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 5 | 0 | 0 | 5 | Not Past Due | 07/29/2026
12914220 | 048 | 25000209/M-00002 | 73242619 | 100303366 | Crossarm FG 3-5/8inX4-5/8inX120in Tangnt | 2 | 0 | 0 | 2 | Not Past Due | 07/29/2026
12914220 | 018 | 25000209/M-00002 | 73242619 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 15 | 0 | 0 | 15 | Not Past Due | 07/22/2026
12914220 | 043 | 25000209/M-00002 | 73242619 | 100322238 | Insulator Riser Support 28kV sil rubber | 10 | 10 | 0 | 10 | Allocated
12914220 | 019 | 25000209/M-00002 | 73242619 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 15 | 0 | 0 | 15 | Not Past Due | TBD
12914220 | 023a | 25000209/M-00002 | 73242619 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 2 | 2 | 0 | 2 | Allocated
12914239 | 054 | 25000209/M-00002 | 73244139 | 100301153 | Base Gain Galv With 9in Offset | 80 | 0 | 0 | 80 | Not Past Due | 08/11/2026
12914239 | 015 | 25000209/M-00002 | 73244139 | 100310428 | Bracket Standoff 3Ph 48in 24in 7H | 2 | 0 | 0 | 2 | Not Past Due | 09/04/2026 | Req'd Expedite
12914239 | 014 | 25000209/M-00002 | 73244139 | 100310427 | Bracket Standoff FG 1.5inX48in w/HD | 2 | 0 | 0 | 2 | Not Past Due | 09/04/2026 | Req'd Expedite
12914239 | 012 | 25000209/M-00002 | 73244139 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 14 | 14 | 0 | 14 | Allocated
12914239 | 059a | 25000209/M-00002 | 73244139 | 100053167 | Clamp DE Bltd Fe Straight NoFit .16-.40 | 30 | 5 | 25 | 5 | Allocated
12914239 | 019 | 25000209/M-00002 | 73244139 | 100015054 | Connector Wedge Al/Cu #6-#2 | 75 | 0 | 0 | 75 | Not Past Due | 11/03/2026 | Req'd Expedite
12914239 | 061 | 25000209/M-00002 | 73244139 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 2 | 0 | 0 | 2 | Not Past Due | 07/29/2026
12914239 | 062 | 25000209/M-00002 | 73244139 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 7 | 0 | 0 | 7 | Not Past Due | 07/29/2026
12914239 | 030 | 25000209/M-00002 | 73244139 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 7 | 0 | 0 | 7 | Not Past Due | 07/29/2026
12914239 | 031 | 25000209/M-00002 | 73244139 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 10 | 0 | 0 | 10 | Not Past Due | 07/29/2026
12914239 | 057 | 25000209/M-00002 | 73244139 | 100339982 | Cutout Polymer L Open 15.5kV 110kV BIL | 3 | 3 | 0 | 3 | Allocated
12914239 | 058 | 25000209/M-00002 | 73244139 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 10 | 0 | 0 | 10 | Not Past Due | 07/23/2026
12914239 | 022 | 25000209/M-00002 | 73244139 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 30 | 0 | 0 | 30 | Not Past Due | 07/22/2026
12914239 | 053 | 25000209/M-00002 | 73244139 | 100322238 | Insulator Riser Support 28kV sil rubber | 28 | 28 | 0 | 28 | Allocated
12914239 | 023 | 25000209/M-00002 | 73244139 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 103 | 0 | 0 | 103 | Not Past Due | TBD
12914239 | 029a | 25000209/M-00002 | 73244139 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 15 | 1 | 0 | 15 | Not Past Due | 08/24/2026
12914239 | 020 | 25000209/M-00002 | 73244139 | 100074602 | Rod Armor Al .491-.521 Sgl 56in 11/set | 10 | 0 | 0 | 10 | Not Past Due | 07/22/2026
12914260 | 028 | 25000209/M-00002 | 73279347 | 100301153 | Base Gain Galv With 9in Offset | 144 | 0 | 0 | 144 | Not Past Due | 08/11/2026
12914260 | 009 | 25000209/M-00002 | 73279347 | 100310428 | Bracket Standoff 3Ph 48in 24in 7H | 13 | 0 | 0 | 13 | Not Past Due | 09/04/2026 | Req'd Expedite
12914260 | 008 | 25000209/M-00002 | 73279347 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 13 | 13 | 0 | 13 | Allocated
12914260 | 015 | 25000209/M-00002 | 73279347 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 2 | 0 | 0 | 2 | Not Past Due | 07/29/2026
12914260 | 027 | 25000209/M-00002 | 73279347 | 100322238 | Insulator Riser Support 28kV sil rubber | 21 | 21 | 0 | 21 | Allocated
12914260 | 014a | 25000209/M-00002 | 73279347 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 6 | 6 | 0 | 6 | Allocated
12914260 | 030 | 25000209/M-00002 | 73279347 | 100103235 | Stirrup Wejtap Alum 477 To 636 1/0 Bail | 20 | 0 | 0 | 20 | Not Past Due | 09/10/2026 | Req'd Expedite
12914333 | 044 | 25000209/M-00002 | 73301547 | 100301153 | Base Gain Galv With 9in Offset | 90 | 0 | 0 | 90 | Not Past Due | 08/11/2026
12914333 | 013 | 25000209/M-00002 | 73301547 | 100310428 | Bracket Standoff 3Ph 48in 24in 7H | 4 | 0 | 0 | 4 | Not Past Due | 09/04/2026 | Req'd Expedite
12914333 | 012 | 25000209/M-00002 | 73301547 | 100310427 | Bracket Standoff FG 1.5inX48in w/HD | 5 | 0 | 0 | 5 | Not Past Due | 09/04/2026 | Req'd Expedite
12914333 | 010 | 25000209/M-00002 | 73301547 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 5 | 5 | 0 | 5 | Allocated
12914333 | 045 | 25000209/M-00002 | 73301547 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 15 | 0 | 0 | 15 | Not Past Due | 07/23/2026
12914333 | 049 | 25000209/M-00002 | 73301547 | 100012488 | Cutout SPL 15kV 200a VAR 084 | 1 | 0 | 0 | 1 | Not Past Due | 08/17/2026
12914333 | 043 | 25000209/M-00002 | 73301547 | 100322238 | Insulator Riser Support 28kV sil rubber | 6 | 6 | 0 | 6 | Allocated
12914333 | 017 | 25000209/M-00002 | 73301547 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 60 | 0 | 0 | 60 | Not Past Due | TBD
12914333 | 028 | 25000209/M-00002 | 73301547 | 100302982 | Pin Ridge Horizontal 18in FG 1ph | 6 | 0 | 0 | 6 | Not Past Due | 08/11/2026
12914340 | 046 | 25000209/M-00002 | 73301585 | 100301153 | Base Gain Galv With 9in Offset | 135 | 0 | 0 | 135 | Not Past Due | 08/11/2026
12914340 | 015 | 25000209/M-00002 | 73301585 | 100310428 | Bracket Standoff 3Ph 48in 24in 7H | 4 | 0 | 0 | 4 | Not Past Due | 09/04/2026 | Req'd Expedite
12914340 | 014 | 25000209/M-00002 | 73301585 | 100310427 | Bracket Standoff FG 1.5inX48in w/HD | 2 | 0 | 0 | 2 | Not Past Due | 09/04/2026 | Req'd Expedite
12914340 | 013 | 25000209/M-00002 | 73301585 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 15 | 15 | 0 | 15 | Allocated
12914340 | 016 | 25000209/M-00002 | 73301585 | 100062712 | Connector Wedge Al/Cu #6-1/0 | 70 | 0 | 50 | 20 | Not Past Due | 10/28/2026 | Req'd Expedite
12914340 | 025 | 25000209/M-00002 | 73301585 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 3 | 0 | 0 | 3 | Not Past Due | 07/29/2026
12914340 | 050 | 25000209/M-00002 | 73301585 | 100303366 | Crossarm FG 3-5/8inX4-5/8inX120in Tangnt | 1 | 0 | 0 | 1 | Not Past Due | 07/29/2026
12914340 | 049 | 25000209/M-00002 | 73301585 | 100339983 | Cutout Polymer L Open 15.5kV 110kV BIL | 2 | 0 | 0 | 2 | Not Past Due | 07/23/2026
12914340 | 052 | 25000209/M-00002 | 73301585 | 100012488 | Cutout SPL 15kV 200a VAR 084 | 2 | 0 | 0 | 2 | Not Past Due | 08/17/2026
12914340 | 045 | 25000209/M-00002 | 73301585 | 100322238 | Insulator Riser Support 28kV sil rubber | 58 | 58 | 0 | 58 | Allocated
12914340 | 019 | 25000209/M-00002 | 73301585 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 32 | 0 | 0 | 32 | Not Past Due | TBD
12914340 | 023 | 25000209/M-00002 | 73301585 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 2 | 0 | 0 | 2 | Not Past Due | 08/24/2026
12914340 | 017 | 25000209/M-00002 | 73301585 | 100074602 | Rod Armor Al .491-.521 Sgl 56in 11/set | 50 | 0 | 0 | 50 | Not Past Due | 07/22/2026
12914340 | 024 | 25000209/M-00002 | 73301585 | 100054802 | Switch disc 13.2kV 600a hookstick poly | 3 | 0 | 0 | 3 | Not Past Due | 08/14/2026
12914350 | 039 | 25000209/M-00002 | 73305080 | 100301153 | Base Gain Galv With 9in Offset | 36 | 0 | 0 | 36 | Not Past Due | 08/11/2026
12914350 | 021 | 25000209/M-00002 | 73305080 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 7 | 0 | 0 | 7 | Not Past Due | 07/29/2026
12914350 | 015 | 25000209/M-00002 | 73305080 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 15 | 0 | 0 | 15 | Not Past Due | TBD
12914350 | 020 | 25000209/M-00002 | 73305080 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 4 | 0 | 0 | 4 | Not Past Due | 08/24/2026
12914350 | 014 | 25000209/M-00002 | 73305080 | 100074602 | Rod Armor Al .491-.521 Sgl 56in 11/set | 32 | 0 | 14 | 18 | Not Past Due | 07/22/2026
12914355 | 002 | 25000209/M-00002 | 73346088 | 100000122 | Elbow LB 15kV Insert | 10 | 0 | 0 | 10 | Not Past Due | 07/28/2026
12914359 | 005 | 25000209/M-00002 | 73358165 | 100015054 | Connector Wedge Al/Cu #6-#2 | 11 | 0 | 5 | 6 | Not Past Due | 11/03/2026 | Req'd Expedite
12914359 | 008 | 25000209/M-00002 | 73358165 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 5 | 0 | 0 | 5 | Not Past Due | 07/29/2026
12914359 | 006 | 25000209/M-00002 | 73358165 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 3 | 0 | 0 | 3 | Not Past Due | TBD
12914359 | 002 | 25000209/M-00002 | 73358165 | 100101263 | Washer Square 3inx3inx3/16in 3/4in Bolt | 11 | 8 | 3 | 8 | Allocated
12914361 | 046 | 25000209/M-00002 | 73802595 | 100301153 | Base Gain Galv With 9in Offset | 105 | 0 | 0 | 105 | Not Past Due | 08/11/2026
12914361 | 008 | 25000209/M-00002 | 73802595 | 100310426 | Bracket Standoff FG 24in W.Hdwr | 8 | 8 | 0 | 8 | Allocated
12914361 | 012 | 25000209/M-00002 | 73802595 | 100015054 | Connector Wedge Al/Cu #6-#2 | 10 | 0 | 0 | 10 | Not Past Due | 11/03/2026 | Req'd Expedite
12914361 | 050 | 25000209/M-00002 | 73802595 | 100303365 | Crossarm 3-5/8 x 4-5/8 x 96in FG | 5 | 0 | 0 | 5 | Not Past Due | 07/29/2026
12914361 | 021 | 25000209/M-00002 | 73802595 | 100095397 | Crossarm DE FG 3 5/8inx4 5/8inx120in | 4 | 0 | 0 | 4 | Not Past Due | 07/29/2026
12914361 | 022 | 25000209/M-00002 | 73802595 | 100095608 | Crossarm FG 3-5/8 x 4-5/8 x 96in | 9 | 0 | 0 | 9 | Not Past Due | 07/29/2026
12914361 | 049 | 25000209/M-00002 | 73802595 | 100339982 | Cutout Polymer L Open 15.5kV 110kV BIL | 2 | 2 | 0 | 2 | Allocated
12914361 | 013 | 25000209/M-00002 | 73802595 | 100084645 | Grip Guy DE 7/16in-7#7 36in | 9 | 0 | 0 | 9 | Not Past Due | 07/22/2026
12914361 | 053 | 25000209/M-00002 | 73802595 | GS36018CC1 | Insulator Guy Strain 18in 36K | 4 | 0 | 0 | 4 | Not Past Due | 09/22/2026 | Req'd Expedite
12914361 | 048 | 25000209/M-00002 | 73802595 | 100035985 | Insulator Susp SL 25k Y/B 52-5 | 3 | 0 | 0 | 3 | Not Past Due | 08/25/2026
12914361 | 014 | 25000209/M-00002 | 73802595 | 100075415 | Molding Wood 1in x 8ft With 1/2in | 50 | 0 | 0 | 50 | Not Past Due | TBD
12914361 | 019 | 25000209/M-00002 | 73802595 | 12655 | Rod Anchor Extension 1-1/2in x 3-1/2ft | 6 | 0 | 0 | 6 | Not Past Due | 08/24/2026
12914361 | 051 | 25000209/M-00002 | 73802595 | 100103235 | Stirrup Wejtap Alum 477 To 636 1/0 Bail | 20 | 0 | 0 | 20 | Not Past Due | 09/10/2026 | Req'd Expedite
12914361 | 020 | 25000209/M-00002 | 73802595 | 100054802 | Switch disc 13.2kV 600a hookstick poly | 12 | 0 | 0 | 12 | Not Past Due | 08/14/2026
12914382 | 003 | 25000209/M-00002 |  | EA1R12076C7JP01 | Transformer Pole Mnt 100kVA 4800/8320Y | 1 | 0 | 0 | 1 | On Hold |  | Cancel?
12914382 | 001 | 25000209/M-00002 |  | 300014321 | Transformer Pole Mnt 25kVA 4800/8320Y | 48 | 0 | 0 | 48 | On Hold |  | Cancel?
12914382 | 002 | 25000209/M-00002 |  | 300014322 | Transformer Pole Mnt 50kVA 4800/8320Y | 35 | 0 | 0 | 35 | On Hold |  | Cancel?
12914385 | 001 | 25000209/M-00002 |  | 300014317 | Regulator 7620V 219A 167KVA | 3 | 0 | 0 | 3 | On Hold |  | Cancel?
12914455 | 006a | 25000209/M-00002 |  | #2 CU SOLID BARE | Wire #2 Cu Sol Bare SD | 7500 | 0 | 0 | 7500 | Not Past Due | 06/08/2026
12914455 | 008 | 25000209/M-00002 |  | NERITINA RP 1200 | Wire Neritina 1/0-7 ACSR OH Poly 1200Ft | 15600 | 0 | 2400 | 13200 | Allocated
12914455 | 004 | 25000209/M-00002 |  | 10160060 | Wire Raven 1/0-6/1 ACSR OH 6095Ft Rl | 60950 | 0 | 60929 | 21 | Not Past Due | 06/11/2026
12914593 | 001 | 25000209/M-00002 |  | BREADFRUIT | Wire 636kcmil AAC 61str Breadfruit | 5000 | 0 | 0 | 5000 | Not Past Due | 2026-10-12