## Slide 1
INTEGRATED CAPITAL DELIVERY PROCESS
Engineering · Estimating · Procurement · Project Management | CVR & HWC
FOR CEO / COO APPROVAL
Presented by the SVP of Engineering · Document CVR-PROC-001 Rev 0 · July 2026
100% UTILITY · 100% OF THE TIME

## Slide 2
1
WHY CHANGE, WHY NOW
Today, engineering, estimating, procurement, and project management sit in different organizations, connected by email and network drives. The cost of those seams:
Estimates built blind
Estimates assembled without design quantities or field production input
Unverified purchasing
POs placed without engineering verification of part numbers and quantities
GP surprises
Margin erosion discovered after the money is spent, not while it can be managed
Schedules that don’t drive buying
Material ordering disconnected from construction need dates
The stakes are rising: our IOU clients (DTE and others) are moving to open-book arrangements — they are effectively auditing our project controls. Predictable delivery is becoming a condition of winning the work.
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 3
2
DECISIONS REQUESTED
1
Adopt the integrated process
Mandatory for all projects ≥ $500k; exceptions approved by SVP Engineering or COO
2
Move estimating into CVR
Transition the estimating team from HWC to CVR, reporting to the SVP of Engineering
3
Stand up the dedicated CVR PM team
PMP/PE-credentialed PMs, separate from engineering leads, operating in the Capital Delivery model with P6
4
Endorse the CVR → PLS transmittal system
Engineer-verified transmittals as the single channel for material procurement
5
Pilot on New Baltimore
Prove the process on the 39-work-order program before the spring 2027 construction start
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 4
3
WHAT "CAPITAL DELIVERY" MEANS
Every project managed as a financial investment, not just a construction job — the discipline investor-owned utilities apply to their own capital programs, where cost and schedule performance flows directly into their rate cases.
1
Baselined
Every project carries a baselined budget and P6 schedule from day one
2
Committed-cost visibility
Track dollars the moment a PO obligates them — not when invoices arrive
3
Forecast monthly
Forecast-at-completion and GP projection as a standing report, not a fire drill
4
Gated decisions
Leadership decides at defined gates — and stays out of the day-to-day critical path
Managing GP the way an IOU’s capital program office manages rate-base spend.
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 5
4
THE OPERATING MODEL
ACCURATE ESTIMATES
CVR Estimating
Estimating moves into CVR under the SVP of Engineering. Estimates built from real design quantities, validated by HWC Construction/Operations PMs who know field conditions and production rates.
VERIFIED PROCUREMENT
Lead Engineer (EOR)
The Engineer of Record leads procurement through Power Line Supply — part numbers, quantities, and technical requirements verified by engineering before anything is ordered.
CAPITAL DELIVERY PM
Dedicated CVR PM (PMP/PE)
A credentialed PM, separate from the engineering lead — financial performance, on-time purchasing, and P6 resource-loaded schedules.
The critical relationship: the CVR PM (capital delivery: cost, schedule, procurement, reporting) and the HWC Construction PM (field execution: crews, production, constructability) meet weekly, share one schedule and one cost picture, and jointly own the outcome.
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 6
5
GOVERNANCE & ORGANIZATION
$500k
and above — the process is mandatory
Exceptions approved only by the SVP Engineering or the COO
Gate decision documented at project award / kickoff
Below threshold: lightweight path; teams may opt in
Exceptions reviewed quarterly by SVP / COO
Estimating → CVR
Team transitions from HWC to CVR, reporting to the SVP of Engineering — estimates and engineering under one roof
EOR named per project
The Lead Engineer / Engineer of Record owns design integrity and all technical procurement content
CVR PM ≠ EOR
The dedicated PM is a PMP/PE and a different person than the engineering lead — checks and balances by design
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 7
6
ONE PROCESS, ONE BACKBONE
DESIGN
CVR Engineering (EOR)
Quantity takeoffs and technical specifications
ESTIMATE
CVR Estimating + HWC PM
Shared cost codes; constructability validated by the field
PROCURE
EOR → Transmittal → PLS
PO timing driven by P6 schedule need dates
EXECUTE
CVR PM ↔ HWC PM
Resource-loaded P6 schedule; cost tracked vs. estimate
CLOSE OUT
All functions
Actuals and lessons feed the estimating library
External dependency handled by design: schedule-prerequisite projects (e.g., TRK-4911, design/built by Burns & McDonnell) enter the P6 schedule as tracked external predecessor milestones.
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 8
7
THE CVR-PLS TRANSMITTAL SYSTEM
The only channel by which material requirements reach Power Line Supply — no verbal orders, no email-thread BOMs.
Numbered & revision-controlled
NB-PLS-004 Rev B — an auditable record of what was ordered, when, and on whose authority
Dual signature
EOR signs for technical accuracy; CVR PM signs for budget and schedule alignment
Schedule-driven need dates
Required-on-site dates pulled from P6; PO deadline = need date − lead time
PLS acknowledgment SLA
Pricing, lead times, and promise dates confirmed within 5 business days
Change control
Any change to part number, quantity, spec, or date = new revision, same dual signature
Start simple
SharePoint form + status register now; graduate to a platform when volume justifies
Outcome: zero procurement rework from wrong part numbers or quantities.
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 9
8
SYSTEMS ROADMAP: PROCESS FIRST, PLATFORM SECOND
CRAWL
Now – 60 days
~$10–15k internal effort
SharePoint/Teams transmittal register, WO cost workbook, standard templates — on tools we already own. No new spend.
WALK
Q4 2026 – Q2 2027
$75–150k first year
Platform pilot on New Baltimore: Oracle Primavera Unifier vs. InEight, head-to-head. Estimating tool selection folds in.
RUN
2027 – 2028
$150–400k/yr run-rate
Full rollout: platform + P6 + estimating tool + ERP feed. Estimate → PO → schedule → actuals on one backbone.
No software commitment is requested today. Budgetary quotes from Oracle and InEight are a Walk-phase deliverable; the platform decision comes to the quarterly Portfolio/Governance Review. ROM figures are planning-level.
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 10
9
PLATFORM OPTIONS & ROM COSTS
Platform | Role | P6 link | ROM cost (planning-level) | Assessment
Oracle Primavera Unifier | Capital program cost mgmt tied to P6 WBS; workflows incl. transmittals | Native | $75–250k/yr + $100–300k impl. | Strongest Capital Delivery match; heaviest lift
InEight | Contractor suite; estimate → cost codes → controls | Connector | $50–150k/yr + $50–150k impl. | Lighter-lift challenger — evaluate head-to-head
Oracle Aconex | Controlled transmittals & document control | Oracle ecosystem | $30–100k/yr | Add-on if volume outgrows SharePoint
Procore | Field/construction PM; best field UX | 3rd-party | $40–120k/yr | Complement at HWC field end — not the backbone
HCSS HeavyBid / InEight Estimate | Estimating (evaluation already underway) | Export to P6 | $15–50k/yr | Choose together with the platform — one data model
Recommendation: two-vendor evaluation — Unifier vs. InEight — piloted against New Baltimore’s 39-work-order reconciliation, decision at the quarterly governance review.
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 11
10
OPERATING RHYTHM & ACCOUNTABILITY
WEEKLY
CVR PM ↔ HWC Construction PM sync — never cancelled; the anchor of the process
BIWEEKLY
Procurement & expediting review — transmittal register, promise vs. need dates
MONTHLY
Cost/GP review + P6 re-forecast — same week, so cost and schedule tell one story
QUARTERLY
Portfolio & governance review with SVP Engineering / COO — GP, exceptions, lessons
Accountability, made structural (full RACI in the process document):
CVR PM accountable for capital delivery · EOR accountable for everything technical · HWC PM accountable for the field · SVP/COO accountable only at the gates — leadership out of the daily critical path
CVR-PROC-001 Rev 0 · July 23, 2026 · Utility Supply & Construction Company

## Slide 12
THE ASK
✓
Approve the integrated process — mandatory ≥ $500k
✓
Approve the estimating move into CVR
✓
Approve the dedicated CVR PM team
✓
Endorse the CVR → PLS transmittal system
✓
Green-light the New Baltimore pilot
In return: GP forecasting as a standing report, on-time material, zero procurement rework, and project controls our IOU clients will recognize as their own.
uscco.com
100% UTILITY · 100% OF THE TIME