## Transmittal
NEW BALTIMORE 4.8 kV CONVERSION PROGRAM
Overhead Material Quantities Transmittal
Contract No. | 4400008681
From | HWC Construction / CVR Engineering
To | DTE Electric Company — Attn: John Chang, Supply Chain
Transmittal No. | (enter)
Transmittal Date | (enter)
Prepared Under Direction Of | Jim Codling, SVP Engineering, CVR Engineering
Yellow cells: complete before issuing.
PURPOSE
In response to DTE’s request for confirmed overhead material quantities, this package transmits the source-validated material quantity reconciliation for the New Baltimore overhead conversion scope: quantities by DTE IM number across the program, quantities by CWO and IM, and a short list of materials pending DTE IM confirmation. Quantities are reconciled across three independent sources: DTE CUE estimate material summaries, construction bills of material, and confirmed supplier order records.
COVERAGE
This package covers the 15 reconciled overhead CWOs listed on the Summary by CWO tab — approximately 97% of program install quantities when compared against DTE’s Maximo work-order quantities. Reconciliation of the remaining small CWOs (four recloser CWOs and CWO 73303193) will follow under separate cover. Underground CWOs removed from the program by credit are excluded.
CONTENTS
Summary by CWO | Program headline quantities (poles, conductor, transformers) and material line counts per CWO.
Quantities by DTE IM | One row per confirmed DTE IM across the program: BOM, CUE-required, variance, and confirmed ordered quantities.
Quantities by CWO and IM | Full detail — each DTE IM within each contributing CWO.
Pending IM Confirmation | Materials without a confirmed DTE IM number; DTE confirmation requested.
Basis and Exclusions | Sources, methodology, exclusions, and reservation of rights.
RESERVATION OF RIGHTS
This transmittal is provided for quantity reconciliation and coordination purposes only. It documents material quantities derived from DTE CUE estimates, construction bills of material, and confirmed supplier order records. Nothing herein constitutes agreement to any credit, back-charge, price adjustment, or change to contract scope or value under Contract 4400008681, and all rights under the contract are expressly reserved. Any adjustment arising from these quantities shall be processed exclusively through the contract change process.

## Summary by CWO
Program Headline Quantities by CWO
Source: reconciled DTE CUE estimates and construction BOMs (Jul 2026 reconciliation).
CWO | Pole Replacements | Bare Conductor (ft) | Transformers | Material Line Items
73232522 | 30 | 9776 | 12 | 109
73234686 | 23 | 8311 | 9 | 154
73239897 | 25 | 5946 | 7 | 93
73239916 | 33 | 6580 | 13 | 108
73239926 | 25 | 6114 | 5 | 132
73240913 | 36 | 22026 | 9 | 156
73242557 | 20 | 4757 | 4 | 134
73242619 | 18 | 8446 | 6 | 96
73244139 | 38 | 8978 | 6 | 124
73279347 | 0 | 145 | 0 | 68
73301547 | 32 | 13450 | 6 | 106
73301585 | 33 | 16885 | 3 | 104
73305080 | 15 | 10960 | 0 | 70
73358165 | 3 | 668 | 0 | 39
73802595 | 1 | 17247 | 4 | 95
TOTAL | 332 | 140289 | 84 | 1588
Pole, conductor, and transformer counts are program headline quantities from the CWO-level reconciliation; conductor is bare primary/neutral wire and excludes triplex/secondary cable. Material line items counts the CWO-and-IM detail rows in this package.

## Quantities by DTE IM
Overhead Material Quantities by DTE IM — Program-Wide
One row per confirmed DTE IM across all 15 reconciled CWOs. Ordered Qty reflects confirmed supplier order records as of 7/28/2026 and excludes DTE-furnished job stock.
DTE IM | Material Description | UOM | CWO Count | BOM Qty | CUE Required Qty | Variance (CUE − BOM) | Ordered Qty (as of 7/28/26) | CWO Numbers
100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA | EA | 15 | 186 | 196 | 10 | 200 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 15 | 3086 | 2280 | -806 | 3086 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100019342 | STRAP_GROUND,GALV STL | EA | 15 | 494 | 764 | 270 | 500 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 15 | 350 | 382 | 32 | 350 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 15 | 1543 | 1112 | -431 | 1729 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 15 | 2231 | 2391 | 160 | 2259 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 15 | 3534 | 3696 | 162 | 3534 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 15 | 339 | 327 | -12 | 339 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 15 | 560 | 342 | -218 | 560 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 15 | 517 | 516 | -1 | 517 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 15 | 1454 | 1078 | -376 | 1448 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 15 | 305 | 227 | -78 | 305 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L | FT | 15 | 3910 | 12141 | 8231 | 2307.1667 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN | EA | 15 | 197 | 126 | -71 | 200 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 15 | 1287 | 1205 | -82 | 1287 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 15 | 872 | 818 | -54 | 835 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 15 | 188 | 543 | 355 | 527 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 15 | 3586 | 2547 | -1039 | 3776 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 15 | 380 | 334 | -46 | 380 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL | LB | 15 | 13 | 247 | 234 | 51 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 14 | 992 | 869 | -123 | 993 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 14 | 1138 | 756 | -382 | 1108 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100068975 | Fuse & Arrester Mounting Bracket | EA | 14 | 175 | 0 | -175 | 178 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585; 73305080; 73358165; 73802595
100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 14 | 441 | 412 | -29 | 411 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73358165; 73802595
100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 14 | 402 | 505 | 103 | 402 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 14 | 3325 | 5692 | 2367 |  | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 14 | 251 | 249 | -2 | 251 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 | EA | 14 | 147 | 374 | 227 | 169 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV | EA | 13 | 136 | 154 | 18 | 136 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301585; 73358165; 73802595
100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 13 | 672 | 572 | -100 | 866 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 13 | 64366 | 57894 | -6472 | 60950 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585; 73358165; 73802595
100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 13 | 89 | 83 | -6 | 173 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301585; 73305080; 73802595
100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL | EA | 13 | 26 | 124 | 98 | 26 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 13 | 50 | 51 | 1 | 50 | 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73244139; 73279347; 73301547; 73301585; 73305080; 73358165; 73802595
100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 13 | 103 | 85 | -18 | 103 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 13 | 514 | 747 | 233 | 514 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 13 | 259 | 307 | 48 | 259 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 | EA | 13 | 167 | 570 | 403 | 50 | 73232522; 73234686; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100115241 | LINK_FUSE,UNV,15 AMP | EA | 13 | 85 | 160 | 75 | 98 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 13 | 830 | 562 | -268 | 830 | 73232522; 73234686; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 13 | 185 | 93 | -92 | 222 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 13 | 1594 | 12328 | 10734 | 7000 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585; 73305080; 73802595
100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG | FT | 12 | 101 | 196 | 95 | 500 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585; 73305080
100021353 | LINK_FUSE,UNV,30 AMP | EA | 12 | 234 | 22 | -212 | 290 | 73232522; 73234686; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 | EA | 12 | 433 | 344 | -89 | 450 | 73234686; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73305080; 73802595
100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 12 | 147 | 202 | 55 | 157 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301585; 73305080; 73802595
100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 12 | 127 | 152 | 25 | 127 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73358165; 73802595
100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 12 | 61 | 38 | -23 | 84 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73305080; 73802595
100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 12 | 213 | 155 | -58 | 213 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301585; 73305080; 73802595
100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 12 | 127 | 30 | -97 | 127 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73279347; 73301547; 73305080; 73802595
100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 11 | 93 | 22 | -71 | 94 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73305080; 73802595
100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, | EA | 11 | 55 | 94 | 39 | 85 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73244139; 73301547; 73301585; 73305080
100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 11 | 69 | 83 | 14 | 69 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301585; 73305080
100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 11 | 61 | 83 | 22 | 61 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301585; 73305080
100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A | EA | 11 | 42 | 190 | 148 | 50 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585
100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 11 | 276 | 280 | 4 | 276 | 73232522; 73234686; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585; 73802595
100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 11 | 74 | 99 | 25 | 74 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73802595
100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 11 | 230 | 176 | -54 | 248 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301585; 73802595
100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 11 | 181 | 165 | -16 | 181 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73802595
100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 | EA | 11 | 160 | 167 | 7 | 160 | 73232522; 73234686; 73239897; 73239916; 73239926; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585
100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 11 | 0 | 68 | 68 | 83 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73358165
100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 11 | 89 | 81 | -8 | 89 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73802595
100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 11 | 39 | 34 | -5 | 40 | 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585
100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC | EA | 11 | 136 | 181 | 45 | 150 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301585; 73305080
300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 11 | 54 | 49 | -5 | 51 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73802595
100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 10 | 261 | 130 | -131 | 161 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547
100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L | EA | 10 | 51 | 51 | 0 | 51 | 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73358165
100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 | EA | 10 | 50 | 86 | 36 | 100 | 73232522; 73234686; 73239926; 73240913; 73242557; 73244139; 73279347; 73301585; 73305080; 73802595
100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 10 | 118 | 101 | -17 | 118 | 73232522; 73234686; 73239926; 73240913; 73242557; 73244139; 73301547; 73301585; 73305080; 73802595
100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 10 | 26728 | 8206 | -18522 | 37200.0001 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547
100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, | EA | 10 | 6 | 61 | 55 | 127 | 73232522; 73234686; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585; 73305080
100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B | EA | 10 | 125 | 75 | -50 | 125 | 73232522; 73234686; 73239916; 73239926; 73240913; 73242557; 73279347; 73301547; 73301585; 73802595
100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 10 | 111 | 74 | -37 | 111 | 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73244139; 73305080; 73358165; 73802595
100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC | EA | 10 | 150 | 188 | 38 | 195 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547
100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 10 | 0 | 147 | 147 |  | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242619; 73244139; 73301547; 73802595
100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 10 | 86462 | 61866 | -24596 | 86799.9999 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301547; 73301585; 73305080; 73358165; 73802595
100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 10 | 354 | 324 | -30 | 354 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547
100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, | EA | 10 | 177 | 12 | -165 | 180 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73358165
100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP | EA | 10 | 69 | 100 | 31 | 44 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242619; 73244139; 73301547; 73802595
100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 10 | 69 | 78 | 9 | 94 | 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585
100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 | EA | 9 | 88 | 40 | -48 | 100 | 73232522; 73234686; 73239897; 73239916; 73239926; 73242557; 73242619; 73244139; 73305080
100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 9 | 50 | 62 | 12 |  | 73232522; 73234686; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301585
100015054 | Connector Wedge Al/Cu #6-#2 | EA | 9 | 0 | 0 | 0 | 360 | 73232522; 73239897; 73239926; 73242557; 73242619; 73244139; 73305080; 73358165; 73802595
100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F | EA | 9 | 246 | 91 | -155 | 260 | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139
300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 9 | 29 | 28 | -1 | 26 | 73234686; 73239916; 73239926; 73240913; 73242557; 73244139; 73301547; 73301585; 73802595
100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 8 | 350 | 28 | -322 |  | 73234686; 73239916; 73239926; 73240913; 73242557; 73244139; 73301547; 73301585
100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S | EA | 8 | 95 | 89 | -6 | 192 | 73232522; 73239897; 73239916; 73239926; 73242557; 73242619; 73244139; 73301547
100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 | EA | 8 | 172 | 70 | -102 | 246 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301547; 73301585; 73305080
100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 8 | 500 | 3464 | 2964 |  | 73232522; 73234686; 73239897; 73239926; 73240913; 73242557; 73242619; 73244139
100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T | EA | 8 | 27 | 14 | -13 | 20 | 73232522; 73239916; 73239926; 73240913; 73242557; 73242619; 73279347; 73802595
100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR | EA | 8 | 57 | 70 | 13 | 57 | 73232522; 73234686; 73239916; 73239926; 73240913; 73242557; 73244139; 73301547
100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 8 | 0 | 56 | 56 |  | 73234686; 73239916; 73239926; 73240913; 73242557; 73244139; 73301547; 73301585
100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 8 | 183 | 126 | -57 | 220 | 73234686; 73239926; 73240913; 73242557; 73244139; 73305080; 73358165; 73802595
100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 8 | 132 | 150 | 18 | 132 | 73234686; 73239926; 73240913; 73242619; 73244139; 73279347; 73301547; 73301585
100102696 | Guy Insulator Attachment | EA | 8 | 89 | 0 | -89 | 100 | 73232522; 73239897; 73239926; 73242557; 73242619; 73301585; 73305080; 73802595
100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 | EA | 8 | 62 | 43 | -19 | 62 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301547; 73301585; 73305080
100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 8 | 25 | 32 | 7 | 34 | 73232522; 73239926; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585
100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 8 | 25 | 17 | -8 | 35 | 73232522; 73234686; 73242557; 73242619; 73244139; 73279347; 73301547; 73301585
100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 7 | 300 | 704 | 404 |  | 73234686; 73239916; 73239926; 73240913; 73279347; 73301585; 73802595
100042242 | POLE_WOOD, PINE, 55FT, CL 1 | EA | 7 | 0 | 27 | 27 | 26 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301585; 73305080
100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 7 | 650 | 28 | -622 |  | 73232522; 73234686; 73240913; 73242557; 73279347; 73301547; 73802595
100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 | EA | 7 | 119 | 107 | -12 | 150 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301585; 73305080
100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | EA | 7 | 30 | 36 | 6 | 30 | 73234686; 73239916; 73239926; 73240913; 73279347; 73301585; 73802595
100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 7 | 0 | 126 | 126 |  | 73234686; 73239926; 73242619; 73244139; 73279347; 73301547; 73301585
100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, | EA | 7 | 75 | 126 | 51 | 75 | 73234686; 73239926; 73242619; 73244139; 73279347; 73301547; 73301585
100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H | EA | 7 | 76 | 80 | 4 | 71 | 73234686; 73239916; 73239926; 73240913; 73279347; 73301585; 73802595
100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, | EA | 7 | 30 | 120 | 90 | 30 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301585; 73305080
100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | EA | 7 | 52 | 52 | 0 | 139 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301585; 73305080
100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT | EA | 7 | 114 | 52 | -62 | 120 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301585; 73305080
100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM | EA | 7 | 32 | 43 | 11 | 32 | 73234686; 73239926; 73240913; 73244139; 73301547; 73301585; 73305080
100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 7 | 12 | 160 | 148 |  | 73234686; 73239916; 73239926; 73240913; 73279347; 73301585; 73802595
100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO | FT | 7 | 465 | 680 | 215 | 950 | 73234686; 73239897; 73239926; 73242619; 73279347; 73301547; 73802595
100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 7 | 139 | 0 | -139 | 139 | 73234686; 73239926; 73242619; 73244139; 73279347; 73301547; 73301585
100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S | EA | 7 | 102 | 160 | 58 | 102 | 73234686; 73239916; 73239926; 73240913; 73279347; 73301585; 73802595
100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 | EA | 7 | 62 | 55 | -7 | 60 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301585; 73305080
100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS | EA | 7 | 20 | 29 | 9 | 22 | 73232522; 73234686; 73239916; 73240913; 73242619; 73244139; 73301547
100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 | EA | 7 | 52 | 52 | 0 | 25 | 73234686; 73239926; 73240913; 73242557; 73244139; 73301585; 73305080
100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 7 | 0 | 81 | 81 |  | 73232522; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619
100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 7 | 132 | 126 | -6 | 132 | 73234686; 73239926; 73242619; 73244139; 73279347; 73301547; 73301585
100057790 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G | EA | 6 | 31 | 18 | -13 | 31 | 73239897; 73239916; 73240913; 73242619; 73244139; 73301547
100069647 | WIRE_TIE,NO. 8,CU,45 IN LG |  | 6 | 0 | 36 | 36 |  | 73232522; 73234686; 73240913; 73279347; 73301547; 73301585
100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN | EA | 6 | 6 | 14 | 8 | 8 | 73232522; 73239916; 73239926; 73240913; 73242557; 73242619
100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- | EA | 6 | 65 | 48 | -17 | 65 | 73234686; 73240913; 73242557; 73244139; 73279347; 73802595
100110238 | PIN_INSULATOR,LAG SCRW,5/8 IN,GALV STL,8 |  | 6 | 0 | 22 | 22 |  | 73232522; 73234686; 73240913; 73279347; 73301547; 73301585
100327860 | 3/4" x 7 3/4" Steel Pin with Lock Washer and Nut | EA | 6 | 78 | 0 | -78 | 80 | 73232522; 73239916; 73239926; 73242557; 73242619; 73244139
100006750 | BOLT_MACHINE,5/8 IN DIA,11 TPI,8 IN LG,G | EA | 5 | 15 | 19 | 4 | 19 | 73239897; 73239916; 73240913; 73242557; 73301585
100012488 | CUTOUT_FUSED,OPN,POLYMER,15KV MAX,110KV | EA | 5 | 1 | 4 | 3 | 5 | 73239897; 73239916; 73240913; 73301547; 73301585
100025788 | POLE_WOOD, PINE, 50FT, CL3 | EA | 5 | 0 | 35 | 35 | 43 | 73234686; 73240913; 73242557; 73301547; 73301585
100036858 | BRACKET_SUPPORT,TERMINATN/ARSTR | EA | 5 | 24 | 16 | -8 | 24 | 73232522; 73234686; 73279347; 73301585; 73305080
100042243 | POLE_WOOD, PINE, 60FT, CL 1 | EA | 5 | 0 | 11 | 11 | 7 | 73234686; 73240913; 73244139; 73305080; 73802595
100052588 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,477K | EA | 5 | 45 | 84 | 39 | 120 | 73232522; 73234686; 73242557; 73305080; 73802595
100069509 | POLE_WOOD, PINE, 50FT, CL 1 | EA | 5 | 0 | 15 | 15 | 11 | 73239926; 73240913; 73242557; 73244139; 73301585
100106838 | PIN_INSULATOR,ANGLE XARM BRAKET,HOT DIPP | EA | 5 | 23 | 11 | -12 | 23 | 73232522; 73239897; 73239916; 73239926; 73240913
100317909 | CONNECTOR_TAP,SECNDRY H-TAP,ALUM | EA | 5 | 150 | 303 | 153 | 150 | 73232522; 73239897; 73239916; 73239926; 73242557
100007836 | WIRE_TIE,NO. 8,CU,54 IN LG | FT | 4 | 100 | 11 | -89 | 500 | 73240913; 73242557; 73244139; 73301547
100019758 | NUT_SQUARE,5/8 IN,GALV STL,11 TPI | EA | 4 | 35 | 41 | 6 | 15 | 73234686; 73239916; 73240913; 73301547
100035087 | LINK_CHAIN,1 IN X 3-1/4 IN,GALV STL,5/8 |  | 4 | 0 | 14 | 14 |  | 73239897; 73239926; 73240913; 73244139
100039661 | BOLT_MACHINE,5/8 IN DIA,11 TPI,2 IN LG,G |  | 4 | 0 | 18 | 18 |  | 73232522; 73234686; 73240913; 73301547
100039664 | WASHER_FLAT,3/4 IN ID,2 IN OD,WROUGHT ST |  | 4 | 0 | 22 | 22 |  | 73234686; 73240913; 73242557; 73802595
100046669 | BOLT_MACHINE,5/8 IN DIA,11 TPI,4 IN LG,G |  | 4 | 0 | 31 | 31 |  | 73232522; 73234686; 73240913; 73301547
100057912 | BOLT_MACHINE,3/4 IN DIA,10 TPI,14 IN LG, |  | 4 | 0 | 18 | 18 |  | 73232522; 73234686; 73240913; 73301547
100062712 | Connector Wedge Al/Cu #6-1/0 | EA | 4 | 0 | 0 | 0 | 260 | 73239916; 73240913; 73301547; 73301585
100065179 | MOUNT_TRNSCST,VEE,GALV STL,3 TRANSFRMRS, | EA | 4 | 3 | 6 | 3 | 3 | 73232522; 73234686; 73240913; 73301547
100094846 | SCREW_LAG,3/8 IN DIA,4 IN LG,HOT DIP GAL |  | 4 | 0 | 12 | 12 |  | 73239897; 73239916; 73242557; 73301585
100311653 | CONNECTOR_TAP,WDGE,ALUM ALLOY |  | 4 | 0 | 26 | 26 |  | 73234686; 73301547; 73358165; 73802595
100313938 | POLE_WOOD,CEDAR,40 FT LG,CLASS 3 |  | 4 | 0 | 4 | 4 |  | 73232522; 73239897; 73240913; 73242557
100018203 | POLE_WOOD, PINE, 40FT, CL 3 | EA | 3 | 0 | 5 | 5 | 4 | 73239926; 73242557; 73244139
100027618 | CABLE_BARE,3/0 AWG,6 X 1 STRANDD,7670 FT |  | 3 | 2600 | 5701 | 3101 |  | 73240913; 73301585; 73305080
100032501 | CABLE_INSUL,TRIPLEX,60 MIL HMPE,1/0 AWG, |  | 3 | 0 | 122 | 122 |  | 73239916; 73240913; 73301547
100047695 | PIN_INSULATOR,HD,3/4 IN X 7 IN,GALV STL, | EA | 3 | 60 | 41 | -19 | 60 | 73239916; 73240913; 73301547
100053167 | CLAMP_DEADEND,STRGHT LINE,MALLEABLE/DUCT | EA | 3 | 30 | 16 | -14 | 30 | 73242557; 73244139; 73802595
100056177 | CABLE_BARE,6 AWG,CU,SOLID,10000 FT LG,AS |  | 3 | 0 | 231 | 231 |  | 73279347; 73301547; 73301585
100061029 | POLE_WOOD, PINE, 45FT, CL 1 | EA | 3 | 0 | 6 | 6 | 5 | 73232522; 73234686; 73242619
100076569 | BOLT_MACHINE,3/4 IN DIA,10 TPI,12 IN LG, |  | 3 | 0 | 10 | 10 |  | 73234686; 73242557; 73802595
100086522 | FITTING_SIDWLK,DUCTILE IRON |  | 3 | 0 | 5 | 5 |  | 73234686; 73239926; 73240913
100093755 | CABLE_INSUL,POWR,60 MIL XLPE,1/0 AWG,6 X |  | 3 | 0 | 1506 | 1506 |  | 73242557; 73244139; 73358165
100107159 | POLE_WOOD, PINE, 55FT, CL 3 | EA | 3 | 0 | 15 | 15 | 14 | 73234686; 73240913; 73305080
100289876 | POLE_WOOD,CEDAR,45 FT LG,CLASS 1 |  | 3 | 0 | 5 | 5 |  | 73232522; 73239916; 73239926
100302982 | BRACKET_MNTNG,POLETOP VRTCL,1-PHAS LP IN | EA | 3 | 6 | 7 | 1 | 6 | 73232522; 73242619; 73301547
100001517 | LINK_FUSE,UNV,10 AMP |  | 2 | 0 | 10 | 10 |  | 73232522; 73301585
100007567 | CONNECTOR_OVERHEAD,FIRED ON,1/0 AWG,ALUM | EA | 2 | 20 | 10 | -10 | 20 | 73242557; 73244139
100013784 | INSULATOR_STRAIN,GUY,30 IN LG,FBRGLAS 24 |  | 2 | 0 | 5 | 5 |  | 73239926; 73305080
100017509 | LEAD_ELECT,SECNDRY,12 FT LG,CU,4/0 AWG |  | 2 | 12 | 2 | -10 |  | 73234686; 73242557
100022671 | LINK_FUSE,UNV,20 AMP | EA | 2 | 28 | 33 | 5 | 28 | 73232522; 73239897
100024362 | POLE_WOOD, PINE, 50FT, CL 2 | EA | 2 | 0 | 2 | 2 | 2 | 73234686; 73240913
100024531 | CONNECTOR_CABLE,PARRELL,ALUM,ACSR/ALUM,N | EA | 2 | 20 | 28 | 8 | 25 | 73240913; 73244139
100027126 | CLEVIS_STRN_INSUL,SECNDRY SRVC,PORCLN,1- | EA | 2 | 50 | 29 | -21 | 60 | 73239926; 73301547
100038866 | RACK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS |  | 2 | 0 | 2 | 2 |  | 73234686; 73240913
100038906 | GUY_ASSY,5/16 IN DIA,165 FT LG,EHS STL S |  | 2 | 0 | 7 | 7 |  | 73232522; 73244139
100042507 | Bracket_mntng shield wire | EA | 2 | 11 | 0 | -11 | 11 | 73234686; 73242557
100043112 | CABLE_INSUL,XLPE,1/0 AWG,CU,7 STRANDD,1 |  | 2 | 900 | 1118 | 218 |  | 73239926; 73244139
100055729 | CONNECTOR_CABLE,BARTAP,TINNED BRNZ,NO.6- |  | 2 | 0 | 5 | 5 |  | 73234686; 73239897
100058551 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 2 | 0 | 31 | 31 |  | 73358165; 73802595
100064127 | LEAD_ELECT,SECNDRY,12 FT LG,ALUM, HARD D |  | 2 | 0 | 4 | 4 |  | 73234686; 73242557
100065871 | CABLE_INSUL,60 MIL PE,1/0 AWG,HARD DRAWN |  | 2 | 0 | 307 | 307 |  | 73234686; 73240913
100077194 | clamp susp 1/0 | EA | 2 | 10 | 0 | -10 | 10 | 73234686; 73242557
100079513 | NAIL_FASTENER,BARB,3/8 IN,2 IN LG,GALV S | EA | 2 | 0 | 32 | 32 | 3500 | 73232522; 73240913
100084565 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,1 |  | 2 | 0 | 4 | 4 |  | 73234686; 73301585
100089217 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,4 F | EA | 2 | 2 | 2 | 0 | 2 | 73239926; 73301547
100104417 | PIN_INSULATOR,XARM,5/8 IN X 6-1/2 IN,GAL | EA | 2 | 21 | 6 | -15 | 21 | 73239926; 73802595
100104745 | LINK_FUSE,UNV,25 AMP | EA | 2 | 3 | 3 | 0 | 4 | 73239897; 73802595
100106252 | BRACE_SUPPORT,SIDWLK GUY,ZINC COATED STL |  | 2 | 0 | 3 | 3 |  | 73234686; 73239926
100113829 | BOLT_EYE,5/8 IN DIA,11 TPI,10 IN LG,GALV |  | 2 | 0 | 4 | 4 |  | 73234686; 73301585
100308950 | CONNECTOR_CABLE,GRND,NO. 6 SOLID TO 1/0 |  | 2 | 0 | 5 | 5 |  | 73234686; 73239897
100341161 | POLE_WOOD,CEDAR,45 FT LG,CLASS 2 |  | 2 | 0 | 3 | 3 |  | 73239897; 73239916
300014323 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 2 | 1 | 2 | 1 | 2 | 73234686; 73242557
100004957 | BASE_MNTNG,SIGN,10 IN WD,WOOD,8 IN LG |  | 1 | 10 | 4 | -6 |  | 73240913
100005379 | SIGN_WARNING,PLSTC,BLK/WHITE,SCRWED |  | 1 | 0 | 4 | 4 |  | 73240913
100010817 | CONNECTOR_OVERHEAD,FIRED ON,NO. 2-556.5 |  | 1 | 0 | 3 | 3 |  | 73242557
100017083 | 5/8" ground rod connector | EA | 1 | 10 | 0 | -10 | 10 | 73232522
100024354 | 5/8" x 16 LG Machine Bolt | EA | 1 | 10 | 0 | -10 | 10 | 73239897
100024784 | MOUNT_TRNSCST,GALV STL,3 TRANSFRMRS,5/8 |  | 1 | 0 | 1 | 1 |  | 73301585
100030339 | CABLE_INSUL,XLPE,1/0 AWG,ALUM,7 STRANDD |  | 1 | 0 | 1 | 1 |  | 73232522
100030941 | LINK_FUSE,UNV,40 AMP | EA | 1 | 3 | 1 | -2 | 3 | 73242557
100031258 | PLATE_ADAPTER,MOUNTNG |  | 1 | 0 | 3 | 3 |  | 73802595
100033974 | LINK_FUSE,UNV,65 AMP | EA | 1 | 6 | 6 | 0 | 6 | 73242557
100035985 | 40kV Suspension Deadend Insulator | EA | 1 | 3 | 0 | -3 | 3 | 73802595
100037863 | BOLT_MACHINE,5/8 IN DIA,11 TPI,30 IN LG, |  | 1 | 0 | 8 | 8 |  | 73240913
100040596 | CONNECTOR_CABLE,TAP,BRNZ,CU,4/0 AWG,2-HO |  | 1 | 0 | 2 | 2 |  | 73234686
100042239 | POLE_WOOD, PINE, 35FT, CL2 | EA | 1 | 0 | 1 | 1 | 1 | 73239916
100042925 | FUSE_CURRNT_LIMIT,FAULT TAMER,15KV,10T A |  | 1 | 0 | 1 | 1 |  | 73242557
100044155 | TUBE_ELECT,FUSE,4-1/2 IN OD,23 IN LG,PVC |  | 1 | 0 | 1 | 1 |  | 73234686
100047463 | CONNECTOR_OVERHEAD,BOLTED, 1/0-4/0 AWG,BR | EA | 1 | 12 | 12 | 0 | 12 | 73802595
100049677 | PADLOCK_ASSY,1-1/2 IN CASE |  | 1 | 0 | 6 | 6 |  | 73802595
100050811 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 1 | 0 | 3 | 3 |  | 73234686
100056487 | CABLE_BARE,1/0 AWG,CU,7 STRAND,ASTM B8/A |  | 1 | 0 | 2456 | 2456 |  | 73305080
100057791 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G |  | 1 | 0 | 1 | 1 |  | 73358165
100058033 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 1 | 0 | 3 | 3 |  | 73234686
100070266 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,5 F | EA | 1 | 4 | 4 | 0 | 4 | 73305080
100071576 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,2 AC |  | 1 | 0 | 1 | 1 |  | 73244139
100072154 | SCREW_LAG, 1/4 IN DIA,2 IN LG,GALV STL,HE |  | 1 | 0 | 150 | 150 |  | 73802595
100073619 | BOLT_EYE,5/8 IN DIA,11 TPI,14 INLG,GALV |  | 1 | 0 | 2 | 2 |  | 73802595
100073793 | GUARD_PROTCT,U CABLE,2-1/4 IN WD,PLSTC,6 |  | 1 | 0 | 18 | 18 |  | 73802595
100074003 | POLE_WOOD, PINE, 65FT, CL 2 |  | 1 | 0 | 1 | 1 |  | 73242557
100078799 | BRACE_SUPPORT,SIDWLK GUY,ZINC COATED STL |  | 1 | 0 | 2 | 2 |  | 73240913
100084202 | BOLT_MACHINE,3/8 IN DIA,16 TPI,10 IN LG, |  | 1 | 0 | 1 | 1 |  | 73802595
100088375 | RACK_INSULATOR,SUSPN,8 IN WIRE SPACING |  | 1 | 0 | 1 | 1 |  | 73234686
100089247 | BOLT_MACHINE,5/8 IN DIA,11 TPI,34 IN LG, |  | 1 | 0 | 8 | 8 |  | 73240913
100095014 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 1 | 0 | 3 | 3 |  | 73234686
100097570 | Insulator_Strain, Deadend, 3" Spool, Porc |  | 1 | 18 | 0 | -18 |  | 73239916
100097571 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC. |  | 1 | 0 | 4 | 4 |  | 73358165
100097596 | Insulator_Spool |  | 1 | 15 | 0 | -15 |  | 73244139
100098069 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,N |  | 1 | 0 | 3 | 3 |  | 73242557
100101973 | SIGN_WARNING,WHITE/YELW,480 VOLT,SCRWED |  | 1 | 0 | 1 | 1 |  | 73234686
100108945 | INSULATOR_STRAIN,GUY,LARGE,PORCLN,SKY,5/ |  | 1 | 0 | 3 | 3 |  | 73234686
100110298 | INDICATOR_FAULT,4.8-41.6KV,200 AMP,CURRN | EA | 1 | 1 | 1 | 0 | 1 | 73239897
100111213 | SCREW_LAG,1/4 IN DIA,2-1/2 IN LG,GALV ST | EA | 1 | 30 | 8 | -22 | 30 | 73240913
100111680 | CABLE_INSUL,XLPE,3/0 AWG,ALUM,19 STRANDD |  | 1 | 0 | 896 | 896 |  | 73301547
100116153 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,NO.1 |  | 1 | 0 | 3 | 3 |  | 73242557
100289874 | POLE_WOOD,CEDAR,50 FT LG,CL 3,BUTT PRESE |  | 1 | 0 | 1 | 1 |  | 73239926
100301538 | CABLE_INSUL,TRIPLEX,XLPE,4/0 AWG,ALUM,19 |  | 1 | 0 | 4 | 4 |  | 73242557
100302469 | ENCLOSURE_ELECT,JUNCTION BOX,8 IN WD,8 I |  | 1 | 0 | 3 | 3 |  | 73240913
100302470 | ENCLOSURE_ELECT,JUNCTION BOX,8 IN WD,8 I |  | 1 | 0 | 1 | 1 |  | 73240913
100302471 | CONTROL_CAPACITOR,OH CAPCTR CNTRL,13.8V, |  | 1 | 0 | 4 | 4 |  | 73240913
100303361 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 |  | 1 | 0 | 1 | 1 |  | 73358165
100310066 | STRAP_GROUND,C-CLAMP,1.08 X 0.50 IN,STL, |  | 1 | 0 | 8 | 8 |  | 73240913
100316436 | BRACKET_SUPPORT,CONDUIT STNDOFF,9 IN X 2 |  | 1 | 0 | 16 | 16 |  | 73240913
100316438 | STRAP_CONDUIT,KIT,4 IN |  | 1 | 0 | 16 | 16 |  | 73240913
100317530 | EXTENSION_POLE_TOP,60 IN LG,FBRGLAS |  | 1 | 2 | 2 | 0 |  | 73239916
100318537 | CONDUIT_RIGID,PVC,4 IN DIA,10 FT LG |  | 1 | 0 | 12 | 12 |  | 73240913
100326132 | COVER_PROTCT,ANIMAL CONDUCTOR COVER,SILC |  | 1 | 0 | 1 | 1 |  | 73234686
100332478 | SENSOR_CURRNT,LINE POST |  | 1 | 0 | 12 | 12 |  | 73240913
100332479 | SENSOR_ACCESSORY,NEUTRAL |  | 1 | 0 | 1 | 1 |  | 73240913
100335234 | STIRRUP_HYDRANT,DISC,4-5/8 X 4-5/8 X 2-5 |  | 1 | 0 | 3 | 3 |  | 73234686
100336218 | 40kV Extension Link |  | 1 | 3 | 0 | -3 |  | 73802595
100336386 | CABLE_CNTRL,POWR AND CNTRL |  | 1 | 0 | 1 | 1 |  | 73240913
100336388 | CABLE_CNTRL,POWR AND CNTRL | EA | 1 | 4 | 3 | -1 | 4 | 73240913
100342373 | POLE_WOOD,PINE,45 FT LG,CLASS 2 |  | 1 | 0 | 1 | 1 |  | 73244139
100352548 | CAP_END,BUMP,1.24 IN X 1.165 IN,PLSTC/RU |  | 1 | 0 | 8 | 8 |  | 73240913
300014317 | REGULATOR_VLTG,BI-DIRECTIONAL STEP,4800/ | EA | 1 | 3 | 3 | 0 | 3 | 73802595
300014341 | TRANSFORMER_DISTR,ISOLATION/OIL FILLED/P |  | 1 | 0 | 3 | 3 |  | 73301547
Line items: | 251

## Quantities by CWO and IM
Overhead Material Quantities by CWO and DTE IM
Each row is one DTE IM within one contributing CWO. Same sources and exclusions as the program-wide tab.
CWO | DTE IM | Material Description | UOM | BOM Qty | CUE Required Qty | Variance (CUE − BOM) | Ordered Qty (as of 7/28/26)
73232522 | 100001517 | LINK_FUSE,UNV,10 AMP |  | 0 | 1 | 1
73232522 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 0 | 5 | 5
73232522 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 8 | 1 | -7 | 8
73232522 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 15 | 18 | 3 | 15
73232522 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 | EA | 16 | 1 | -15 | 100
73232522 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 0 | 2 | 2
73232522 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 0 | 12 | 12
73232522 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 60
73232522 | 100017083 | 5/8" ground rod connector | EA | 10 | 0 | -10 | 10
73232522 | 100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S | EA | 21 | 12 | -9 | 192
73232522 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 |  | 0 | 2 | 2
73232522 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 146 | 106 | -40 | 146
73232522 | 100019342 | STRAP_GROUND,GALV STL |  | 0 | 60 | 60
73232522 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 10 | 30 | 20 | 10
73232522 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 0 | 27 | 27
73232522 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 10 | 0 | -10 | 10
73232522 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 93 | 80 | -13 | 125
73232522 | 100022671 | LINK_FUSE,UNV,20 AMP |  | 0 | 5 | 5
73232522 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 0 | 210 | 210 | 12
73232522 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 300 | 319 | 19 | 300
73232522 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV |  | 0 | 2 | 2
73232522 | 100030339 | CABLE_INSUL,XLPE,1/0 AWG,ALUM,7 STRANDD |  | 0 | 1 | 1
73232522 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, |  | 0 | 3 | 3
73232522 | 100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 0 | 250 | 250
73232522 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL |  | 0 | 4 | 4
73232522 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 60 | 12 | -48 | 60
73232522 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 4 | 7 | 3 | 4
73232522 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 22 | 15 | -7 | 22
73232522 | 100036858 | BRACKET_SUPPORT,TERMINATN/ARSTR | EA | 6 | 0 | -6 | 24
73232522 | 100038906 | GUY_ASSY,5/16 IN DIA,165 FT LG,EHS STL S |  | 0 | 1 | 1
73232522 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 61 | 43 | -18 | 61
73232522 | 100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T |  | 0 | 3 | 3
73232522 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL |  | 0 | 7 | 7
73232522 | 100039661 | BOLT_MACHINE,5/8 IN DIA,11 TPI,2 IN LG,G |  | 0 | 4 | 4
73232522 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL |  | 0 | 68 | 68
73232522 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 8300 | 8801 | 501 | 8667.4605
73232522 | 100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR |  | 0 | 7 | 7
73232522 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 31 | 31
73232522 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 62 | 50 | -12 | 62
73232522 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 33 | 22 | -11 | 33
73232522 | 100046669 | BOLT_MACHINE,5/8 IN DIA,11 TPI,4 IN LG,G |  | 0 | 6 | 6
73232522 | 100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 0 | 3 | 3
73232522 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 975 | 975
73232522 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 5100 | 293 | -4807 | 7165.1937
73232522 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN | EA | 1 | 1 | 0 | 200
73232522 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 93 | 83 | -10 | 93
73232522 | 100052588 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,477K | EA | 0 | 0 | 0 | 120
73232522 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT |  | 0 | 3 | 3
73232522 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 |  | 0 | 7 | 7
73232522 | 100057912 | BOLT_MACHINE,3/4 IN DIA,10 TPI,14 IN LG, |  | 0 | 3 | 3
73232522 | 100061029 | POLE_WOOD, PINE, 45FT, CL 1 |  | 0 | 1 | 1
73232522 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, | EA | 0 | 2 | 2 | 121
73232522 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 62 | 48 | -14 | 62
73232522 | 100065179 | MOUNT_TRNSCST,VEE,GALV STL,3 TRANSFRMRS, |  | 0 | 1 | 1
73232522 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 15 | 0 | -15 | 15
73232522 | 100069647 | WIRE_TIE,NO. 8,CU,45 IN LG |  | 0 | 1 | 1
73232522 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 23 | 18 | -5 | 23
73232522 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G |  | 0 | 12 | 12
73232522 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 40 | 29 | -11 | 40
73232522 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, |  | 0 | 22 | 22
73232522 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 45 | 45 | 30
73232522 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 |  | 0 | 46 | 46
73232522 | 100079513 | NAIL_FASTENER,BARB,3/8 IN,2 IN LG,GALV S | EA | 0 | 0 | 0 | 3500
73232522 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B |  | 0 | 1 | 1
73232522 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 12 | 12
73232522 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, |  | 0 | 6 | 6
73232522 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN |  | 0 | 27 | 27
73232522 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR |  | 0 | 16 | 16
73232522 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 | EA | 22 | 24 | 2 | 160
73232522 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 301 | 210 | -91 | 333
73232522 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 2 | 2 | 3
73232522 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 2 | 2 | 0 | 25
73232522 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 4 | 5 | 1 | 4
73232522 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 24 | 13 | -11 | 24
73232522 | 100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN | EA | 2 | 3 | 1 | 8
73232522 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC |  | 0 | 21 | 21
73232522 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 |  | 0 | 58 | 58
73232522 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 0 | 488 | 488
73232522 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 |  | 0 | 2 | 2
73232522 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL | LB | 0 | 15 | 15 | 50
73232522 | 100102696 | Guy Insulator Attachment | EA | 16 | 0 | -16 | 16
73232522 | 100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS |  | 0 | 3 | 3
73232522 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN |  | 0 | 29 | 29
73232522 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 8 | 2 | -6 | 8
73232522 | 100106838 | PIN_INSULATOR,ANGLE XARM BRAKET,HOT DIPP | EA | 3 | 3 | 0 | 3
73232522 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 36 | 36
73232522 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 22 | 22
73232522 | 100110238 | PIN_INSULATOR,LAG SCRW,5/8 IN,GALV STL,8 |  | 0 | 1 | 1
73232522 | 100115241 | LINK_FUSE,UNV,15 AMP |  | 0 | 7 | 7
73232522 | 100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 0 | 24 | 24
73232522 | 100289876 | POLE_WOOD,CEDAR,45 FT LG,CLASS 1 |  | 0 | 1 | 1
73232522 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 40 | 22 | -18 | 40
73232522 | 100302982 | BRACKET_MNTNG,POLETOP VRTCL,1-PHAS LP IN |  | 0 | 2 | 2
73232522 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 4 | 3 | -1 | 4
73232522 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 6 | 2 | -4 | 17
73232522 | 100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 0 | 0 | 0 | 6
73232522 | 100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN |  | 0 | 1 | 1
73232522 | 100313938 | POLE_WOOD,CEDAR,40 FT LG,CLASS 3 |  | 0 | 1 | 1
73232522 | 100317909 | CONNECTOR_TAP,SECNDRY H-TAP,ALUM |  | 0 | 63 | 63
73232522 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. |  | 0 | 19 | 19
73232522 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 0 | 30 | 30
73232522 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 31 | 32 | 1 | 31
73232522 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, | EA | 15 | 0 | -15 | 180
73232522 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 0 | 14 | 14
73232522 | 100327860 | 3/4" x 7 3/4" Steel Pin with Lock Washer and Nut |  | 12 | 0 | -12
73232522 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F | EA | 12 | 14 | 2 | 260
73232522 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 1125 | 1125 | 691.4894
73232522 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP |  | 0 | 23 | 23
73232522 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 13 | 12 | -1 | 12
73234686 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA | EA | 18 | 16 | -2 | 200
73234686 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 3 | 3 | 0 | 3
73234686 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 2 | 2 | 0 | 2
73234686 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 |  | 2 | 1 | -1
73234686 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 8 | 6 | -2
73234686 | 100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 200 | 7 | -193
73234686 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV | EA | 24 | 24 | 0 | 136
73234686 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L | EA | 1 | 1 | 0 | 1
73234686 | 100017509 | LEAD_ELECT,SECNDRY,12 FT LG,CU,4/0 AWG |  | 12 | 1 | -11
73234686 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 | EA | 8 | 8 | 0 | 8
73234686 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 180 | 172 | -8 | 180
73234686 | 100019342 | STRAP_GROUND,GALV STL | EA | 72 | 72 | 0 | 500
73234686 | 100019758 | NUT_SQUARE,5/8 IN,GALV STL,11 TPI | EA | 15 | 0 | -15 | 15
73234686 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 40 | 36 | -4 | 40
73234686 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG | FT | 2 | 7 | 5 | 500
73234686 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 15 | 0 | -15 | 30
73234686 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 110 | 96 | -14 | 110
73234686 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 185 | 182 | -3 | 185
73234686 | 100024362 | POLE_WOOD, PINE, 50FT, CL 2 | EA | 0 | 1 | 1 | 1
73234686 | 100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 | EA | 8 | 0 | -8 | 50
73234686 | 100025788 | POLE_WOOD, PINE, 50FT, CL3 | EA | 0 | 1 | 1 | 1
73234686 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 160 | 254 | 94 | 160
73234686 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 33 | 36 | 3 | 33
73234686 | 100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 0 | 48 | 48
73234686 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, | EA | 20 | 8 | -12 | 20
73234686 | 100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 0 | 120 | 120
73234686 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 4 | 9 | 5 | 4
73234686 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 10 | 6 | -4 | 10
73234686 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 6 | 5 | -1 | 6
73234686 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 150 | 104 | -46 | 150
73234686 | 100036858 | BRACKET_SUPPORT,TERMINATN/ARSTR |  | 0 | 1 | 1
73234686 | 100038866 | RACK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS |  | 0 | 1 | 1
73234686 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 24 | 23 | -1 | 50
73234686 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 6 | 5 | -1 | 6
73234686 | 100039661 | BOLT_MACHINE,5/8 IN DIA,11 TPI,2 IN LG,G |  | 0 | 2 | 2
73234686 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 200 | 115 | -85 | 200
73234686 | 100039664 | WASHER_FLAT,3/4 IN ID,2 IN OD,WROUGHT ST |  | 0 | 2 | 2
73234686 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 5200 | 4458 | -742 | 5430.2162
73234686 | 100040596 | CONNECTOR_CABLE,TAP,BRNZ,CU,4/0 AWG,2-HO |  | 0 | 2 | 2
73234686 | 100042242 | POLE_WOOD, PINE, 55FT, CL 1 | EA | 0 | 6 | 6 | 3
73234686 | 100042243 | POLE_WOOD, PINE, 60FT, CL 1 | EA | 0 | 2 | 2 | 2
73234686 | 100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR |  | 0 | 1 | 1
73234686 | 100042507 | Bracket_mntng shield wire | EA | 6 | 0 | -6 | 6
73234686 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 | EA | 20 | 3 | -17 | 450
73234686 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 15 | 15
73234686 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 100 | 92 | -8 | 100
73234686 | 100044155 | TUBE_ELECT,FUSE,4-1/2 IN OD,23 IN LG,PVC |  | 0 | 1 | 1
73234686 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 18 | 18 | 0 | 18
73234686 | 100046669 | BOLT_MACHINE,5/8 IN DIA,11 TPI,4 IN LG,G |  | 0 | 5 | 5
73234686 | 100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 0 | 5 | 5
73234686 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 970 | 970
73234686 | 100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 0 | 14 | 14
73234686 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 1600 | 160 | -1440 | 2247.9039
73234686 | 100050811 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 0 | 3 | 3
73234686 | 100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 | EA | 14 | 13 | -1 | 45
73234686 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 10 | 4 | -6
73234686 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 110 | 120 | 10 | 110
73234686 | 100052588 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,477K |  | 0 | 36 | 36
73234686 | 100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | EA | 3 | 3 | 0 | 3
73234686 | 100055729 | CONNECTOR_CABLE,BARTAP,TINNED BRNZ,NO.6- |  | 0 | 4 | 4
73234686 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 12 | 11 | -1 | 12
73234686 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 6 | 5 | -1 | 20
73234686 | 100057912 | BOLT_MACHINE,3/4 IN DIA,10 TPI,14 IN LG, |  | 0 | 3 | 3
73234686 | 100058033 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 0 | 3 | 3
73234686 | 100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 36 | 36 | 0 | 220
73234686 | 100061029 | POLE_WOOD, PINE, 45FT, CL 1 | EA | 0 | 3 | 3 | 3
73234686 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, |  | 0 | 5 | 5
73234686 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 60 | 56 | -4 | 60
73234686 | 100064127 | LEAD_ELECT,SECNDRY,12 FT LG,ALUM, HARD D |  | 0 | 2 | 2
73234686 | 100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 0 | 3 | 3
73234686 | 100065179 | MOUNT_TRNSCST,VEE,GALV STL,3 TRANSFRMRS, |  | 0 | 1 | 1
73234686 | 100065871 | CABLE_INSUL,60 MIL PE,1/0 AWG,HARD DRAWN |  | 0 | 22 | 22
73234686 | 100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 6 | 3 | -3 | 6
73234686 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 18 | 0 | -18 | 18
73234686 | 100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, |  | 0 | 3 | 3
73234686 | 100069647 | WIRE_TIE,NO. 8,CU,45 IN LG |  | 0 | 2 | 2
73234686 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 21 | 24 | 3 | 21
73234686 | 100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H |  | 0 | 6 | 6
73234686 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 6 | 8 | 2 | 6
73234686 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 85 | 89 | 4 | 85
73234686 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 10 | 12 | 2 | 10
73234686 | 100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, |  | 0 | 22 | 22
73234686 | 100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | EA | 5 | 5 | 0 | 5
73234686 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 50 | 46 | -4 | 50
73234686 | 100076569 | BOLT_MACHINE,3/4 IN DIA,10 TPI,12 IN LG, |  | 0 | 2 | 2
73234686 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 50 | 58 | 8 | 50
73234686 | 100077194 | clamp susp 1/0 | EA | 5 | 0 | -5 | 5
73234686 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B |  | 0 | 7 | 7
73234686 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 8 | 8
73234686 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 20 | 16 | -4 | 20
73234686 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 0 | 2 | 2
73234686 | 100084565 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,1 |  | 0 | 3 | 3
73234686 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 4 | 2 | -2 | 4
73234686 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 24 | 24 | 0 | 24
73234686 | 100086522 | FITTING_SIDWLK,DUCTILE IRON |  | 0 | 2 | 2
73234686 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 8 | 7 | -1
73234686 | 100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT | EA | 4 | 5 | 1 | 120
73234686 | 100088375 | RACK_INSULATOR,SUSPN,8 IN WIRE SPACING |  | 0 | 1 | 1
73234686 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 150 | 163 | 13 | 150
73234686 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 6 | 6 | 6
73234686 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA |  | 0 | 1 | 1
73234686 | 100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM | EA | 10 | 6 | -4 | 10
73234686 | 100095014 | TAG_IDNT,PP,2-1/2 IN WD,3-1/2 IN LG,BLK/ |  | 0 | 3 | 3
73234686 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 4 | 4 | 0 | 4
73234686 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 12 | 12 | 0 | 12
73234686 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 11 | 10 | -1 | 11
73234686 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC | EA | 42 | 47 | 5 | 180
73234686 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 50 | 77 | 27 | 50
73234686 | 100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 0 | 12 | 12
73234686 | 100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO |  | 0 | 36 | 36
73234686 | 100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 6 | 0 | -6 | 6
73234686 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 175 | 503 | 328
73234686 | 100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S |  | 0 | 12 | 12
73234686 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 33 | 36 | 3 | 33
73234686 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 18 | 18
73234686 | 100101973 | SIGN_WARNING,WHITE/YELW,480 VOLT,SCRWED |  | 0 | 1 | 1
73234686 | 100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 | EA | 6 | 6 | 0 | 6
73234686 | 100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- |  | 0 | 3 | 3
73234686 | 100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 | EA | 8 | 8 | 0 | 60
73234686 | 100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS | EA | 6 | 5 | -1 | 6
73234686 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 30 | 31 | 1 | 30
73234686 | 100106252 | BRACE_SUPPORT,SIDWLK GUY,ZINC COATED STL |  | 0 | 2 | 2
73234686 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 10 | 1 | -9 | 10
73234686 | 100107159 | POLE_WOOD, PINE, 55FT, CL 3 | EA | 0 | 1 | 1 | 1
73234686 | 100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 |  | 0 | 5 | 5
73234686 | 100108945 | INSULATOR_STRAIN,GUY,LARGE,PORCLN,SKY,5/ |  | 0 | 3 | 3
73234686 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 3 | 3
73234686 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 47 | 47
73234686 | 100110238 | PIN_INSULATOR,LAG SCRW,5/8 IN,GALV STL,8 |  | 0 | 2 | 2
73234686 | 100113829 | BOLT_EYE,5/8 IN DIA,11 TPI,10 IN LG,GALV |  | 0 | 3 | 3
73234686 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 3 | 9 | 6 | 6
73234686 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 3500 | 2883 | -617 | 3513.6823
73234686 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 55 | 47 | -8 | 55
73234686 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 4 | 5 | 1 | 4
73234686 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 5 | 6 | 1 | 5
73234686 | 100308950 | CONNECTOR_CABLE,GRND,NO. 6 SOLID TO 1/0 |  | 0 | 4 | 4
73234686 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 7 | 6 | -1 | 7
73234686 | 100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN |  | 0 | 1 | 1
73234686 | 100311653 | CONNECTOR_TAP,WDGE,ALUM ALLOY |  | 0 | 3 | 3
73234686 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 15 | 15 | 0 | 15
73234686 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 | EA | 30 | 36 | 6 | 30
73234686 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 30 | 23 | -7 | 30
73234686 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 23 | 4 | -19
73234686 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC | EA | 13 | 11 | -2 | 150
73234686 | 100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 6 | 3 | -3 | 6
73234686 | 100326132 | COVER_PROTCT,ANIMAL CONDUCTOR COVER,SILC |  | 0 | 1 | 1
73234686 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F |  | 37 | 2 | -35
73234686 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB |  | 0 | 375 | 375
73234686 | 100335234 | STIRRUP_HYDRANT,DISC,4-5/8 X 4-5/8 X 2-5 |  | 0 | 3 | 3
73234686 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP | EA | 5 | 6 | 1 | 5
73234686 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 15 | 19 | 4 | 15
73234686 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 1 | 1 | 0 | 1
73234686 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 8 | 7 | -1 | 5
73234686 | 300014323 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 0 | 1 | 1 | 1
73239897 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 0 | 5 | 5
73239897 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 22 | 0 | -22 | 22
73239897 | 100006750 | BOLT_MACHINE,5/8 IN DIA,11 TPI,8 IN LG,G |  | 0 | 4 | 4
73239897 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 17 | 17 | 0 | 17
73239897 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 |  | 10 | 11 | 1
73239897 | 100012488 | CUTOUT_FUSED,OPN,POLYMER,15KV MAX,110KV |  | 0 | 3 | 3
73239897 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 0 | 7 | 7
73239897 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 44
73239897 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L |  | 0 | 8 | 8
73239897 | 100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S |  | 7 | 7 | 0
73239897 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 114 | 80 | -34 | 114
73239897 | 100019342 | STRAP_GROUND,GALV STL |  | 0 | 148 | 148
73239897 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG |  | 0 | 68 | 68
73239897 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 0 | 3 | 3
73239897 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 39 | 78 | 39 | 119
73239897 | 100022671 | LINK_FUSE,UNV,20 AMP | EA | 28 | 28 | 0 | 28
73239897 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 42 | 145 | 103 | 42
73239897 | 100024354 | 5/8" x 16 LG Machine Bolt | EA | 10 | 0 | -10 | 10
73239897 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 195 | 252 | 57 | 195
73239897 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 32 | 17 | -15 | 32
73239897 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, |  | 0 | 3 | 3
73239897 | 100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 500 | 252 | -248
73239897 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 40 | 9 | -31 | 40
73239897 | 100035087 | LINK_CHAIN,1 IN X 3-1/4 IN,GALV STL,5/8 |  | 0 | 3 | 3
73239897 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 11 | 11 | 0 | 11
73239897 | 100036719 | NUT_EYE,5/8 IN,GALV STL |  | 0 | 28 | 28
73239897 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 32 | 26 | -6 | 32
73239897 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 11 | 11 | 0 | 11
73239897 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL |  | 0 | 37 | 37
73239897 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 2450 | 3501 | 1051 | 2558.4673
73239897 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 76 | 76
73239897 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 46 | 31 | -15 | 40
73239897 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 30 | 10 | -20 | 30
73239897 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L | FT | 1800 | 2445 | 645 | 819.921
73239897 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 2150 | 50 | -2100 | 3020.6209
73239897 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 0 | 3 | 3
73239897 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 49 | 81 | 32 | 49
73239897 | 100055729 | CONNECTOR_CABLE,BARTAP,TINNED BRNZ,NO.6- |  | 0 | 1 | 1
73239897 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 |  | 0 | 11 | 11
73239897 | 100057790 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G | EA | 1 | 1 | 0 | 1
73239897 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 14 | 14 | 0 | 14
73239897 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 30 | 0 | -30 | 30
73239897 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 60 | 62 | 2 | 60
73239897 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 7 | 7 | 0 | 7
73239897 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 32 | 28 | -4 | 32
73239897 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 4 | 4 | 0 | 6
73239897 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 103 | 103 | 22
73239897 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 70 | 79 | 9 | 70
73239897 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 7 | 7
73239897 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 18 | 18 | 0 | 36
73239897 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 11 | 11 | 0 | 11
73239897 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 3 | 3 | 0 | 3
73239897 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 15 | 15 | 0 | 15
73239897 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 14 | 14 | 0
73239897 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 187 | 194 | 7 | 207
73239897 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 4 | 4 | 3
73239897 | 100094846 | SCREW_LAG,3/8 IN DIA,4 IN LG,HOT DIP GAL |  | 0 | 4 | 4
73239897 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 10 | 0 | -10 | 10
73239897 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 2 | 2 | 0 | 2
73239897 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 3 | 3 | 0 | 3
73239897 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 10 | 3 | -7 | 10
73239897 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC |  | 5 | 4 | -1
73239897 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 |  | 0 | 130 | 130
73239897 | 100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO |  | 0 | 60 | 60
73239897 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 0 | 790 | 790
73239897 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 32 | 17 | -15 | 32
73239897 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL | LB | 0 | 37 | 37 | 1
73239897 | 100102696 | Guy Insulator Attachment | EA | 10 | 0 | -10 | 10
73239897 | 100104745 | LINK_FUSE,UNV,25 AMP | EA | 2 | 2 | 0 | 2
73239897 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN |  | 0 | 60 | 60
73239897 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 10 | 0 | -10 | 10
73239897 | 100106838 | PIN_INSULATOR,ANGLE XARM BRAKET,HOT DIPP |  | 0 | 3 | 3
73239897 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 21 | 21
73239897 | 100110298 | INDICATOR_FAULT,4.8-41.6KV,200 AMP,CURRN | EA | 1 | 1 | 0 | 1
73239897 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 1 | 1 | 0 | 2
73239897 | 100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 0 | 17 | 17
73239897 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 7 | 7 | 0 | 7
73239897 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 0 | 0 | 0 | 1
73239897 | 100308950 | CONNECTOR_CABLE,GRND,NO. 6 SOLID TO 1/0 |  | 0 | 1 | 1
73239897 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 54 | 24 | -30 | 54
73239897 | 100313938 | POLE_WOOD,CEDAR,40 FT LG,CLASS 3 |  | 0 | 1 | 1
73239897 | 100317909 | CONNECTOR_TAP,SECNDRY H-TAP,ALUM |  | 0 | 87 | 87
73239897 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. |  | 0 | 10 | 10
73239897 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 0 | 68 | 68
73239897 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 27 | 27 | 0 | 27
73239897 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 10 | 0 | -10
73239897 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 0 | 11 | 11
73239897 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F |  | 11 | 14 | 3
73239897 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 89 | 30 | -59 | 79.7872
73239897 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP | EA | 27 | 27 | 0 | 27
73239897 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 1 | 1 | 0 | 1
73239897 | 100341161 | POLE_WOOD,CEDAR,45 FT LG,CLASS 2 |  | 0 | 1 | 1
73239897 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 7 | 7 | 0 | 7
73239916 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 17 | 18 | 1
73239916 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 10 | 1 | -9 | 10
73239916 | 100006750 | BOLT_MACHINE,5/8 IN DIA,11 TPI,8 IN LG,G | EA | 15 | 8 | -7 | 15
73239916 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 24 | 24 | 0 | 24
73239916 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 |  | 8 | 5 | -3
73239916 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 4 | 4 | 0
73239916 | 100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 100 | 4 | -96
73239916 | 100012488 | CUTOUT_FUSED,OPN,POLYMER,15KV MAX,110KV | EA | 0 | 0 | 0 | 1
73239916 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 60 | 53 | -7
73239916 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L |  | 0 | 3 | 3
73239916 | 100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S |  | 30 | 37 | 7
73239916 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 110 | 188 | 78 | 110
73239916 | 100019342 | STRAP_GROUND,GALV STL |  | 52 | 52 | 0
73239916 | 100019758 | NUT_SQUARE,5/8 IN,GALV STL,11 TPI |  | 20 | 2 | -18
73239916 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 26 | 26 | 0 | 26
73239916 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 25 | 25 | 0
73239916 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 10 | 0 | -10 | 20
73239916 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 225 | 160 | -65 | 225
73239916 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 142 | 313 | 171 | 142
73239916 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 330 | 553 | 223 | 330
73239916 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 34 | 5 | -29 | 34
73239916 | 100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 100 | 48 | -52
73239916 | 100032501 | CABLE_INSUL,TRIPLEX,60 MIL HMPE,1/0 AWG, |  | 0 | 118 | 118
73239916 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, |  | 0 | 3 | 3
73239916 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 50 | 23 | -27 | 50
73239916 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 6 | 6 | 0 | 6
73239916 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 73 | 55 | -18 | 73
73239916 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 72 | 99 | 27 | 72
73239916 | 100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T |  | 4 | 4 | 0
73239916 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 6 | 6 | 0 | 6
73239916 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 90 | 85 | -5 | 90
73239916 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 5500 | 5735 | 235 | 5743.4979
73239916 | 100042239 | POLE_WOOD, PINE, 35FT, CL2 | EA | 0 | 1 | 1 | 1
73239916 | 100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR | EA | 35 | 32 | -3 | 35
73239916 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 0 | 36 | 36
73239916 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A | EA | 30 | 26 | -4 | 50
73239916 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 40 | 76 | 36 | 40
73239916 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 23 | 22 | -1 | 23
73239916 | 100047695 | PIN_INSULATOR,HD,3/4 IN X 7 IN,GALV STL, | EA | 20 | 2 | -18 | 20
73239916 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 845 | 845
73239916 | 100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 0 | 8 | 8
73239916 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 4200 | 4844 | 644 | 5900.7478
73239916 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 2 | 0 | -2
73239916 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 280 | 191 | -89 | 280
73239916 | 100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | EA | 3 | 3 | 0 | 3
73239916 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 6 | 6 | 0 | 6
73239916 | 100057790 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G |  | 0 | 1 | 1
73239916 | 100062712 | Connector Wedge Al/Cu #6-1/0 | EA | 0 | 0 | 0 | 70
73239916 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 36 | 71 | 35 | 36
73239916 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 0 | 0 | 0 | 1
73239916 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 9 | 15 | 6 | 9
73239916 | 100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H | EA | 6 | 6 | 0 | 71
73239916 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 14 | 13 | -1 | 14
73239916 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 52 | 56 | 4 | 15
73239916 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 34 | 32 | -2 | 34
73239916 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 40 | 39 | -1 | 72
73239916 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 42 | 37 | -5 | 42
73239916 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B | EA | 10 | 6 | -4 | 10
73239916 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL | EA | 20 | 13 | -7 | 20
73239916 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 10 | 8 | -2 | 10
73239916 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 5 | 5 | 0 | 5
73239916 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 25 | 25 | 0 | 25
73239916 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 15 | 21 | 6 | 15
73239916 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 23 | 43 | 20
73239916 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 302 | 383 | 81 | 302
73239916 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 2 | 2 | 2
73239916 | 100094846 | SCREW_LAG,3/8 IN DIA,4 IN LG,HOT DIP GAL |  | 0 | 2 | 2
73239916 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 8 | 7 | -1 | 8
73239916 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 1 | 1 | 0 | 1
73239916 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 31 | 18 | -13 | 31
73239916 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 17 | 15 | -2 | 17
73239916 | 100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN |  | 4 | 4 | 0
73239916 | 100097570 | Insulator_Strain, Deadend, 3" Spool, Porc |  | 18 | 0 | -18
73239916 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC |  | 0 | 25 | 25
73239916 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 48 | 26 | -22 | 48
73239916 | 100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 12 | 12 | 0
73239916 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 0 | 291 | 291
73239916 | 100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S | EA | 12 | 12 | 0 | 12
73239916 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 33 | 5 | -28 | 33
73239916 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 13 | 13 | 0
73239916 | 100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS | EA | 3 | 3 | 0 | 4
73239916 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 24 | 13 | -11 | 24
73239916 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 8 | 7 | -1 | 8
73239916 | 100106838 | PIN_INSULATOR,ANGLE XARM BRAKET,HOT DIPP | EA | 20 | 3 | -17 | 20
73239916 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 27 | 27
73239916 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 28 | 28
73239916 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 9 | 15 | 6 | 18
73239916 | 100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 0 | 25 | 25
73239916 | 100289876 | POLE_WOOD,CEDAR,45 FT LG,CLASS 1 |  | 0 | 3 | 3
73239916 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 13 | 28 | 15 | 13
73239916 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 5 | 2 | -3 | 5
73239916 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 5 | 1 | -4 | 5
73239916 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 14 | 1 | -13 | 14
73239916 | 100317530 | EXTENSION_POLE_TOP,60 IN LG,FBRGLAS |  | 2 | 2 | 0
73239916 | 100317909 | CONNECTOR_TAP,SECNDRY H-TAP,ALUM | EA | 150 | 144 | -6 | 150
73239916 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 15 | 24 | 9 | 15
73239916 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 | EA | 26 | 26 | 0 | 26
73239916 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 57 | 58 | 1 | 57
73239916 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 53 | 4 | -49
73239916 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 21 | 20 | -1
73239916 | 100327860 | 3/4" x 7 3/4" Steel Pin with Lock Washer and Nut |  | 19 | 0 | -19
73239916 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F |  | 19 | 19 | 0
73239916 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 1505 | 1504 | -1 | 1601.0638
73239916 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP |  | 25 | 10 | -15
73239916 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 0 | 3 | 3 | 25
73239916 | 100341161 | POLE_WOOD,CEDAR,45 FT LG,CLASS 2 |  | 0 | 2 | 2
73239916 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 14 | 9 | -5 | 8
73239916 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 0 | 4 | 4 | 4
73239926 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 16 | 13 | -3
73239926 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 15 | 2 | -13 | 15
73239926 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 13 | 13 | 0 | 13
73239926 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 |  | 13 | 11 | -2
73239926 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 0 | 6 | 6
73239926 | 100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 50 | 4 | -46
73239926 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 12 | 23 | 11
73239926 | 100013784 | INSULATOR_STRAIN,GUY,30 IN LG,FBRGLAS 24 |  | 0 | 1 | 1
73239926 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 50
73239926 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L |  | 0 | 11 | 11
73239926 | 100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S |  | 20 | 15 | -5
73239926 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 |  | 0 | 2 | 2
73239926 | 100018203 | POLE_WOOD, PINE, 40FT, CL 3 | EA | 0 | 1 | 1 | 1
73239926 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 150 | 151 | 1 | 150
73239926 | 100019342 | STRAP_GROUND,GALV STL |  | 50 | 60 | 10
73239926 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 30 | 30 | 0 | 30
73239926 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 0 | 7 | 7
73239926 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 30 | 16 | -14 | 30
73239926 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 390 | 94 | -296 | 390
73239926 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 150 | 211 | 61 | 150
73239926 | 100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 |  | 0 | 6 | 6
73239926 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 450 | 372 | -78 | 450
73239926 | 100027126 | CLEVIS_STRN_INSUL,SECNDRY SRVC,PORCLN,1- | EA | 30 | 18 | -12 | 30
73239926 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 22 | 19 | -3 | 22
73239926 | 100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 0 | 48 | 48
73239926 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, | EA | 0 | 21 | 21 | 30
73239926 | 100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 0 | 220 | 220
73239926 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL |  | 0 | 2 | 2
73239926 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 50 | 26 | -24 | 50
73239926 | 100035087 | LINK_CHAIN,1 IN X 3-1/4 IN,GALV STL,5/8 |  | 0 | 2 | 2
73239926 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 12 | 16 | 4 | 12
73239926 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 50 | 40 | -10 | 50
73239926 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 60 | 49 | -11 | 60
73239926 | 100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T |  | 0 | 1 | 1
73239926 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 20 | 16 | -4 | 20
73239926 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 75 | 86 | 11 | 75
73239926 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 5200 | 5139 | -61 | 5430.2162
73239926 | 100042242 | POLE_WOOD, PINE, 55FT, CL 1 | EA | 0 | 2 | 2 | 4
73239926 | 100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR | EA | 20 | 22 | 2 | 20
73239926 | 100043112 | CABLE_INSUL,XLPE,1/0 AWG,CU,7 STRANDD,1 |  | 0 | 264 | 264
73239926 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 50 | 71 | 21
73239926 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 4 | 4
73239926 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 65 | 58 | -7 | 65
73239926 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 15 | 7 | -8 | 15
73239926 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L | FT | 650 | 975 | 325 | 296.0826
73239926 | 100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 0 | 8 | 8
73239926 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 2800 | 254 | -2546 | 3933.8319
73239926 | 100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 |  | 0 | 4 | 4
73239926 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 5 | 5 | 0
73239926 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 100 | 105 | 5 | 100
73239926 | 100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | EA | 3 | 3 | 0 | 3
73239926 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 6 | 10 | 4 | 6
73239926 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 12 | 16 | 4 | 40
73239926 | 100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 12 | 6 | -6
73239926 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, |  | 0 | 2 | 2
73239926 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 50 | 39 | -11 | 50
73239926 | 100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 0 | 5 | 5
73239926 | 100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 3 | 5 | 2 | 3
73239926 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 15 | 0 | -15 | 15
73239926 | 100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, |  | 0 | 5 | 5
73239926 | 100069509 | POLE_WOOD, PINE, 50FT, CL 1 | EA | 0 | 2 | 2 | 2
73239926 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 55 | 58 | 3 | 55
73239926 | 100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H |  | 0 | 6 | 6
73239926 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 6 | 5 | -1 | 6
73239926 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 50 | 49 | -1 | 50
73239926 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 36 | 42 | 6 | 36
73239926 | 100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, |  | 0 | 4 | 4
73239926 | 100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 |  | 0 | 2 | 2
73239926 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 45 | 45 | 25
73239926 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 52 | 52 | 0 | 52
73239926 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B | EA | 20 | 6 | -14 | 20
73239926 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 5 | 5
73239926 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 14 | 14 | 0 | 14
73239926 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 10 | 10 | 0 | 10
73239926 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 30 | 5 | -25 | 30
73239926 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR |  | 0 | 6 | 6
73239926 | 100086522 | FITTING_SIDWLK,DUCTILE IRON |  | 0 | 1 | 1
73239926 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 19 | 14 | -5
73239926 | 100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT |  | 5 | 2 | -3
73239926 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 525 | 255 | -270 | 525
73239926 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 5 | 5 | 5
73239926 | 100089217 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,4 F | EA | 2 | 0 | -2 | 2
73239926 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 5 | 5 | 0 | 5
73239926 | 100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM |  | 0 | 3 | 3
73239926 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 4 | 3 | -1 | 4
73239926 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 2 | 3 | 1 | 2
73239926 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 26 | 18 | -8 | 26
73239926 | 100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN |  | 0 | 1 | 1
73239926 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC |  | 50 | 15 | -35
73239926 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 100 | 122 | 22 | 100
73239926 | 100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 0 | 12 | 12
73239926 | 100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO |  | 0 | 192 | 192
73239926 | 100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 10 | 0 | -10 | 10
73239926 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 0 | 600 | 600
73239926 | 100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S |  | 0 | 12 | 12
73239926 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 22 | 19 | -3 | 22
73239926 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 15 | 15
73239926 | 100102696 | Guy Insulator Attachment | EA | 26 | 0 | -26 | 26
73239926 | 100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 |  | 0 | 3 | 3
73239926 | 100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 |  | 0 | 2 | 2
73239926 | 100104417 | PIN_INSULATOR,XARM,5/8 IN X 6-1/2 IN,GAL | EA | 15 | 0 | -15 | 15
73239926 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 100 | 45 | -55 | 100
73239926 | 100106252 | BRACE_SUPPORT,SIDWLK GUY,ZINC COATED STL |  | 0 | 1 | 1
73239926 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 26 | 5 | -21 | 26
73239926 | 100106838 | PIN_INSULATOR,ANGLE XARM BRAKET,HOT DIPP |  | 0 | 1 | 1
73239926 | 100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 |  | 0 | 2 | 2
73239926 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 3 | 3
73239926 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 7 | 7
73239926 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 10 | 11 | 1 | 10
73239926 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 1310 | 0 | -1310 | 1315.1211
73239926 | 100289874 | POLE_WOOD,CEDAR,50 FT LG,CL 3,BUTT PRESE |  | 0 | 1 | 1
73239926 | 100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 0 | 11 | 11
73239926 | 100289876 | POLE_WOOD,CEDAR,45 FT LG,CLASS 1 |  | 0 | 1 | 1
73239926 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 25 | 7 | -18 | 25
73239926 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F |  | 7 | 3 | -4
73239926 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 0 | 4 | 4 | 7
73239926 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 1 | 2 | 1 | 1
73239926 | 100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 13 | 10 | -3 | 13
73239926 | 100317909 | CONNECTOR_TAP,SECNDRY H-TAP,ALUM |  | 0 | 6 | 6
73239926 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 12 | 10 | -2 | 12
73239926 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 0 | 30 | 30
73239926 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 50 | 34 | -16 | 50
73239926 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 13 | 0 | -13
73239926 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 24 | 27 | 3
73239926 | 100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 3 | 5 | 2 | 3
73239926 | 100327860 | 3/4" x 7 3/4" Steel Pin with Lock Washer and Nut |  | 13 | 0 | -13
73239926 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F |  | 32 | 30 | -2
73239926 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 1754 | 1754 | 1063.8298
73239926 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP |  | 0 | 2 | 2
73239926 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 10 | 11 | 1 | 10
73239926 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 0 | 1 | 1 | 1
73239926 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 5 | 4 | -1 | 4
73240913 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 48 | 39 | -9
73240913 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE |  | 0 | 3 | 3
73240913 | 100004957 | BASE_MNTNG,SIGN,10 IN WD,WOOD,8 IN LG |  | 10 | 4 | -6
73240913 | 100005379 | SIGN_WARNING,PLSTC,BLK/WHITE,SCRWED |  | 0 | 4 | 4
73240913 | 100006750 | BOLT_MACHINE,5/8 IN DIA,11 TPI,8 IN LG,G |  | 0 | 1 | 1
73240913 | 100007836 | WIRE_TIE,NO. 8,CU,54 IN LG |  | 0 | 1 | 1
73240913 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 150 | 36 | -114 | 50
73240913 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 0 | 10 | 10
73240913 | 100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 0 | 3 | 3
73240913 | 100012488 | CUTOUT_FUSED,OPN,POLYMER,15KV MAX,110KV | EA | 0 | 0 | 0 | 1
73240913 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 0 | 4 | 4
73240913 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L |  | 0 | 1 | 1
73240913 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 | EA | 0 | 18 | 18 | 50
73240913 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 400 | 134 | -266 | 400
73240913 | 100019342 | STRAP_GROUND,GALV STL |  | 60 | 100 | 40
73240913 | 100019758 | NUT_SQUARE,5/8 IN,GALV STL,11 TPI |  | 0 | 33 | 33
73240913 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 80 | 56 | -24 | 80
73240913 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 40 | 40 | 0
73240913 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 18 | 0 | -18 | 18
73240913 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 230 | 278 | 48 | 230
73240913 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 270 | 162 | -108 | 270
73240913 | 100024362 | POLE_WOOD, PINE, 50FT, CL 2 | EA | 0 | 1 | 1 | 1
73240913 | 100024531 | CONNECTOR_CABLE,PARRELL,ALUM,ACSR/ALUM,N | EA | 20 | 25 | 5 | 25
73240913 | 100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 | EA | 18 | 24 | 6 | 50
73240913 | 100025788 | POLE_WOOD, PINE, 50FT, CL3 | EA | 0 | 3 | 3 | 10
73240913 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 350 | 445 | 95 | 350
73240913 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 160 | 161 | 1 | 160
73240913 | 100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 200 | 176 | -24
73240913 | 100027618 | CABLE_BARE,3/0 AWG,6 X 1 STRANDD,7670 FT |  | 0 | 1685 | 1685
73240913 | 100032501 | CABLE_INSUL,TRIPLEX,60 MIL HMPE,1/0 AWG, |  | 0 | 2 | 2
73240913 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, |  | 0 | 14 | 14
73240913 | 100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 0 | 2622 | 2622
73240913 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 40 | 40 | 0 | 40
73240913 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV |  | 0 | 16 | 16
73240913 | 100035087 | LINK_CHAIN,1 IN X 3-1/4 IN,GALV STL,5/8 |  | 0 | 2 | 2
73240913 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 4 | 5 | 1 | 4
73240913 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 100 | 118 | 18 | 100
73240913 | 100037863 | BOLT_MACHINE,5/8 IN DIA,11 TPI,30 IN LG, |  | 0 | 8 | 8
73240913 | 100038866 | RACK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS |  | 0 | 1 | 1
73240913 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 140 | 96 | -44 | 140
73240913 | 100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T | EA | 10 | 2 | -8 | 20
73240913 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL |  | 0 | 5 | 5
73240913 | 100039661 | BOLT_MACHINE,5/8 IN DIA,11 TPI,2 IN LG,G |  | 0 | 8 | 8
73240913 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 259 | 135 | -124 | 260
73240913 | 100039664 | WASHER_FLAT,3/4 IN ID,2 IN OD,WROUGHT ST |  | 0 | 12 | 12
73240913 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 11000 | 10245 | -755 | 11486.9959
73240913 | 100042242 | POLE_WOOD, PINE, 55FT, CL 1 | EA | 0 | 6 | 6 | 8
73240913 | 100042243 | POLE_WOOD, PINE, 60FT, CL 1 | EA | 0 | 2 | 2 | 1
73240913 | 100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR |  | 0 | 2 | 2
73240913 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 20 | 12 | -8
73240913 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 12 | 12
73240913 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 330 | 182 | -148 | 330
73240913 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 28 | 31 | 3 | 28
73240913 | 100046669 | BOLT_MACHINE,5/8 IN DIA,11 TPI,4 IN LG,G |  | 0 | 12 | 12
73240913 | 100047695 | PIN_INSULATOR,HD,3/4 IN X 7 IN,GALV STL, | EA | 40 | 33 | -7 | 40
73240913 | 100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 0 | 6 | 6
73240913 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 1525 | 1525
73240913 | 100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 0 | 6 | 6
73240913 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 3533 | 2350 | -1183 | 4963.6528
73240913 | 100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 | EA | 30 | 24 | -6 | 30
73240913 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 42 | 37 | -5
73240913 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 275 | 283 | 8 | 275
73240913 | 100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | EA | 6 | 6 | 0 | 6
73240913 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT |  | 0 | 6 | 6
73240913 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 25 | 5 | -20 | 50
73240913 | 100057790 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G |  | 0 | 1 | 1
73240913 | 100057912 | BOLT_MACHINE,3/4 IN DIA,10 TPI,14 IN LG, |  | 0 | 6 | 6
73240913 | 100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 25 | 24 | -1
73240913 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, |  | 0 | 10 | 10
73240913 | 100062712 | Connector Wedge Al/Cu #6-1/0 | EA | 0 | 0 | 0 | 60
73240913 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 200 | 33 | -167 | 200
73240913 | 100065179 | MOUNT_TRNSCST,VEE,GALV STL,3 TRANSFRMRS, | EA | 2 | 2 | 0 | 2
73240913 | 100065871 | CABLE_INSUL,60 MIL PE,1/0 AWG,HARD DRAWN |  | 0 | 285 | 285
73240913 | 100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A |  | 0 | 24 | 24
73240913 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 0 | 0 | 0 | 1
73240913 | 100069509 | POLE_WOOD, PINE, 50FT, CL 1 |  | 0 | 6 | 6
73240913 | 100069647 | WIRE_TIE,NO. 8,CU,45 IN LG |  | 0 | 2 | 2
73240913 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 24 | 29 | 5 | 24
73240913 | 100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H |  | 20 | 20 | 0
73240913 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 8 | 9 | 1 | 8
73240913 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 138 | 145 | 7 | 138
73240913 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 20 | 16 | -4 | 20
73240913 | 100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, |  | 0 | 20 | 20
73240913 | 100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | EA | 15 | 10 | -5 | 24
73240913 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 63 | 63 | 30
73240913 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 47 | 65 | 18 | 47
73240913 | 100078799 | BRACE_SUPPORT,SIDWLK GUY,ZINC COATED STL |  | 0 | 2 | 2
73240913 | 100079513 | NAIL_FASTENER,BARB,3/8 IN,2 IN LG,GALV S |  | 0 | 32 | 32
73240913 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B | EA | 50 | 14 | -36 | 50
73240913 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 9 | 9
73240913 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 60 | 30 | -30 | 60
73240913 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 30 | 26 | -4 | 30
73240913 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 60 | 42 | -18 | 60
73240913 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 30 | 17 | -13 | 30
73240913 | 100086522 | FITTING_SIDWLK,DUCTILE IRON |  | 0 | 2 | 2
73240913 | 100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT |  | 21 | 10 | -11
73240913 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 620 | 344 | -276 | 670
73240913 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 4 | 4 | 4
73240913 | 100089247 | BOLT_MACHINE,5/8 IN DIA,11 TPI,34 IN LG, |  | 0 | 8 | 8
73240913 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 8 | 7 | -1 | 8
73240913 | 100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM | EA | 10 | 12 | 2 | 10
73240913 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 10 | 14 | 4 | 10
73240913 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 18 | 17 | -1 | 18
73240913 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 26 | 25 | -1 | 26
73240913 | 100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN |  | 0 | 2 | 2
73240913 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC |  | 20 | 22 | 2
73240913 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 20 | 32 | 12 | 20
73240913 | 100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 0 | 40 | 40
73240913 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 550 | 661 | 111
73240913 | 100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S | EA | 40 | 40 | 0 | 40
73240913 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 155 | 161 | 6 | 155
73240913 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 81 | 81
73240913 | 100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 | EA | 10 | 12 | 2 | 10
73240913 | 100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- |  | 0 | 4 | 4
73240913 | 100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 |  | 15 | 14 | -1
73240913 | 100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS | EA | 8 | 9 | 1 | 8
73240913 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 10 | 16 | 6 | 10
73240913 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 8 | 7 | -1 | 8
73240913 | 100106838 | PIN_INSULATOR,ANGLE XARM BRAKET,HOT DIPP |  | 0 | 1 | 1
73240913 | 100107159 | POLE_WOOD, PINE, 55FT, CL 3 | EA | 0 | 2 | 2 | 1
73240913 | 100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 | EA | 40 | 10 | -30 | 25
73240913 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 18 | 18
73240913 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 33 | 33
73240913 | 100110238 | PIN_INSULATOR,LAG SCRW,5/8 IN,GALV STL,8 |  | 0 | 2 | 2
73240913 | 100111213 | SCREW_LAG,1/4 IN DIA,2-1/2 IN LG,GALV ST | EA | 30 | 8 | -22 | 30
73240913 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 9 | 12 | 3 | 9
73240913 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 8826 | 8571 | -255 | 8860.5029
73240913 | 100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 0 | 2 | 2
73240913 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 35 | 33 | -2 | 35
73240913 | 100302469 | ENCLOSURE_ELECT,JUNCTION BOX,8 IN WD,8 I |  | 0 | 3 | 3
73240913 | 100302470 | ENCLOSURE_ELECT,JUNCTION BOX,8 IN WD,8 I |  | 0 | 1 | 1
73240913 | 100302471 | CONTROL_CAPACITOR,OH CAPCTR CNTRL,13.8V, |  | 0 | 4 | 4
73240913 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 40 | 49 | 9 | 40
73240913 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 15 | 14 | -1 | 15
73240913 | 100310066 | STRAP_GROUND,C-CLAMP,1.08 X 0.50 IN,STL, |  | 0 | 8 | 8
73240913 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 6 | 7 | 1 | 11
73240913 | 100313938 | POLE_WOOD,CEDAR,40 FT LG,CLASS 3 |  | 0 | 1 | 1
73240913 | 100316436 | BRACKET_SUPPORT,CONDUIT STNDOFF,9 IN X 2 |  | 0 | 16 | 16
73240913 | 100316438 | STRAP_CONDUIT,KIT,4 IN |  | 0 | 16 | 16
73240913 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 26 | 28 | 2 | 26
73240913 | 100318537 | CONDUIT_RIGID,PVC,4 IN DIA,10 FT LG |  | 0 | 12 | 12
73240913 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 | EA | 56 | 56 | 0 | 56
73240913 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 46 | 55 | 9 | 46
73240913 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 4 | 4 | 0
73240913 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 27 | 23 | -4
73240913 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F |  | 100 | 0 | -100
73240913 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 3377 | 3377 | 319.1489
73240913 | 100332478 | SENSOR_CURRNT,LINE POST |  | 0 | 12 | 12
73240913 | 100332479 | SENSOR_ACCESSORY,NEUTRAL |  | 0 | 1 | 1
73240913 | 100336386 | CABLE_CNTRL,POWR AND CNTRL |  | 0 | 1 | 1
73240913 | 100336388 | CABLE_CNTRL,POWR AND CNTRL | EA | 4 | 3 | -1 | 4
73240913 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP | EA | 7 | 9 | 2 | 7
73240913 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 6 | 7 | 1 | 6
73240913 | 100352548 | CAP_END,BUMP,1.24 IN X 1.165 IN,PLSTC/RU |  | 0 | 8 | 8
73240913 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 5 | 6 | 1 | 6
73240913 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 3 | 3 | 0 | 3
73242557 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 7 | 5 | -2
73242557 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE |  | 0 | 2 | 2
73242557 | 100006750 | BOLT_MACHINE,5/8 IN DIA,11 TPI,8 IN LG,G | EA | 0 | 5 | 5 | 4
73242557 | 100007567 | CONNECTOR_OVERHEAD,FIRED ON,1/0 AWG,ALUM |  | 0 | 4 | 4
73242557 | 100007836 | WIRE_TIE,NO. 8,CU,54 IN LG |  | 0 | 2 | 2
73242557 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 10 | 2 | -8 | 10
73242557 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 |  | 0 | 1 | 1
73242557 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 0 | 11 | 11
73242557 | 100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 0 | 3 | 3
73242557 | 100010817 | CONNECTOR_OVERHEAD,FIRED ON,NO. 2-556.5 |  | 0 | 3 | 3
73242557 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 10 | 8 | -2
73242557 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 50
73242557 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L |  | 0 | 3 | 3
73242557 | 100017509 | LEAD_ELECT,SECNDRY,12 FT LG,CU,4/0 AWG |  | 0 | 1 | 1
73242557 | 100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S |  | 9 | 6 | -3
73242557 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 |  | 0 | 1 | 1
73242557 | 100018203 | POLE_WOOD, PINE, 40FT, CL 3 |  | 0 | 1 | 1
73242557 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 190 | 104 | -86 | 190
73242557 | 100019342 | STRAP_GROUND,GALV STL |  | 20 | 20 | 0
73242557 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 10 | 10 | 0 | 10
73242557 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 0 | 9 | 9
73242557 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 45 | 0 | -45 | 45
73242557 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 70 | 70 | 0 | 140
73242557 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 86 | 102 | 16 | 86
73242557 | 100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 | EA | 8 | 0 | -8 | 8
73242557 | 100025788 | POLE_WOOD, PINE, 50FT, CL3 | EA | 0 | 3 | 3 | 3
73242557 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 215 | 152 | -63 | 215
73242557 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 22 | 16 | -6 | 22
73242557 | 100030941 | LINK_FUSE,UNV,40 AMP | EA | 3 | 1 | -2 | 3
73242557 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, |  | 0 | 1 | 1
73242557 | 100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 0 | 0 | 0
73242557 | 100033974 | LINK_FUSE,UNV,65 AMP | EA | 6 | 6 | 0 | 6
73242557 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 14 | 5 | -9 | 14
73242557 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 50 | 5 | -45 | 50
73242557 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 5 | 1 | -4 | 5
73242557 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 16 | 39 | 23 | 16
73242557 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 26 | 21 | -5 | 26
73242557 | 100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T |  | 0 | 3 | 3
73242557 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 1 | 1 | 0 | 1
73242557 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 10 | 45 | 35 | 10
73242557 | 100039664 | WASHER_FLAT,3/4 IN ID,2 IN OD,WROUGHT ST |  | 0 | 2 | 2
73242557 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 2850 | 2524 | -326 | 2976.1762
73242557 | 100042242 | POLE_WOOD, PINE, 55FT, CL 1 |  | 0 | 3 | 3
73242557 | 100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR | EA | 2 | 3 | 1 | 2
73242557 | 100042507 | Bracket_mntng shield wire | EA | 5 | 0 | -5 | 5
73242557 | 100042925 | FUSE_CURRNT_LIMIT,FAULT TAMER,15KV,10T A |  | 0 | 1 | 1
73242557 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 25 | 8 | -17
73242557 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 4 | 4
73242557 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 70 | 54 | -16 | 70
73242557 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 30 | 3 | -27 | 30
73242557 | 100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 0 | 2 | 2
73242557 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L | FT | 0 | 325 | 325 | 170.8169
73242557 | 100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 0 | 6 | 6
73242557 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 950 | 50 | -900 | 1194.199
73242557 | 100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 | EA | 10 | 6 | -4 | 10
73242557 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 10 | 4 | -6
73242557 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 70 | 74 | 4 | 70
73242557 | 100052588 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,477K |  | 0 | 6 | 6
73242557 | 100053167 | CLAMP_DEADEND,STRGHT LINE,MALLEABLE/DUCT |  | 0 | 6 | 6
73242557 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT |  | 0 | 2 | 2
73242557 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 5 | 1 | -4 | 5
73242557 | 100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 9 | 9 | 0
73242557 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, |  | 0 | 5 | 5
73242557 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 60 | 38 | -22 | 30
73242557 | 100064127 | LEAD_ELECT,SECNDRY,12 FT LG,ALUM, HARD D |  | 0 | 2 | 2
73242557 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 30 | 0 | -30 | 30
73242557 | 100069509 | POLE_WOOD, PINE, 50FT, CL 1 | EA | 0 | 4 | 4 | 7
73242557 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 45 | 20 | -25 | 45
73242557 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 3 | 3 | 0 | 3
73242557 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 50 | 39 | -11 | 50
73242557 | 100074003 | POLE_WOOD, PINE, 65FT, CL 2 |  | 0 | 1 | 1
73242557 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 5 | 8 | 3 | 5
73242557 | 100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, |  | 0 | 10 | 10
73242557 | 100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | EA | 10 | 5 | -5 | 18
73242557 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 15 | 15 | 20
73242557 | 100076569 | BOLT_MACHINE,3/4 IN DIA,10 TPI,12 IN LG, |  | 0 | 2 | 2
73242557 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 21 | 26 | 5 | 21
73242557 | 100077194 | clamp susp 1/0 | EA | 5 | 0 | -5 | 5
73242557 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B | EA | 25 | 0 | -25 | 25
73242557 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 3 | 3
73242557 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 30 | 22 | -8 | 30
73242557 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 6 | 14 | 8 | 6
73242557 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 5 | 4 | -1 | 5
73242557 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 10 | 7 | -3 | 10
73242557 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 8 | 4 | -4
73242557 | 100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT |  | 4 | 5 | 1
73242557 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 365 | 103 | -262 | 415
73242557 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 2 | 2 | 2
73242557 | 100093755 | CABLE_INSUL,POWR,60 MIL XLPE,1/0 AWG,6 X |  | 0 | 6 | 6
73242557 | 100094846 | SCREW_LAG,3/8 IN DIA,4 IN LG,HOT DIP GAL |  | 0 | 5 | 5
73242557 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 4 | 2 | -2 | 4
73242557 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 3 | 2 | -1 | 3
73242557 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 7 | 8 | 1 | 7
73242557 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 16 | 14 | -2 | 16
73242557 | 100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN |  | 0 | 3 | 3
73242557 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC |  | 10 | 8 | -2
73242557 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 50 | 40 | -10 | 50
73242557 | 100098069 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,N |  | 0 | 3 | 3
73242557 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 500 | 369 | -131
73242557 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 10 | 16 | 6 | 10
73242557 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 5 | 5
73242557 | 100102696 | Guy Insulator Attachment | EA | 0 | 0 | 0 | 1
73242557 | 100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 | EA | 8 | 0 | -8 | 8
73242557 | 100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- | EA | 25 | 0 | -25 | 25
73242557 | 100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 |  | 0 | 1 | 1
73242557 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 25 | 19 | -6 | 25
73242557 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 8 | 2 | -6 | 8
73242557 | 100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 |  | 0 | 5 | 5
73242557 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 7 | 34 | 27
73242557 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 2 | 1 | -1 | 2
73242557 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 2200 | 1908 | -292 | 2208.6003
73242557 | 100116153 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,NO.1 |  | 0 | 3 | 3
73242557 | 100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 0 | 1 | 1
73242557 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 43 | 34 | -9 | 43
73242557 | 100301538 | CABLE_INSUL,TRIPLEX,XLPE,4/0 AWG,ALUM,19 |  | 0 | 4 | 4
73242557 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 3 | 0 | -3 | 3
73242557 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 4 | 3 | -1 | 4
73242557 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 20 | 7 | -13 | 40
73242557 | 100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 0 | 0 | 0 | 2
73242557 | 100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 0 | 1 | 1 | 6
73242557 | 100313938 | POLE_WOOD,CEDAR,40 FT LG,CLASS 3 |  | 0 | 1 | 1
73242557 | 100317909 | CONNECTOR_TAP,SECNDRY H-TAP,ALUM |  | 0 | 3 | 3
73242557 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 5 | 3 | -2 | 5
73242557 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 | EA | 25 | 10 | -15 | 25
73242557 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 24 | 24 | 0 | 24
73242557 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 12 | 0 | -12
73242557 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 17 | 15 | -2
73242557 | 100327860 | 3/4" x 7 3/4" Steel Pin with Lock Washer and Nut | EA | 10 | 0 | -10 | 80
73242557 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F |  | 10 | 2 | -8
73242557 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 500 | 500 | 212.766
73242557 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 10 | 11 | 1 | 10
73242557 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 0 | 0 | 0 | 1
73242557 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 3 | 3 | 0 | 2
73242557 | 300014323 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 1 | 1 | 0 | 1
73242619 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 0 | 13 | 13
73242619 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 13 | 1 | -12 | 13
73242619 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 20 | 5 | -15 | 20
73242619 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 |  | 13 | 1 | -12
73242619 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 0 | 3 | 3
73242619 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 0 | 2 | 2
73242619 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 30
73242619 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L |  | 0 | 6 | 6
73242619 | 100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S |  | 3 | 2 | -1
73242619 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 150 | 88 | -62 | 150
73242619 | 100019342 | STRAP_GROUND,GALV STL |  | 0 | 24 | 24
73242619 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 12 | 12 | 0 | 12
73242619 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 0 | 15 | 15
73242619 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 31 | 0 | -31 | 62
73242619 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 75 | 54 | -21 | 105
73242619 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 125 | 141 | 16 | 125
73242619 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 280 | 206 | -74 | 280
73242619 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV |  | 0 | 20 | 20
73242619 | 100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 0 | 0 | 0
73242619 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 35 | 16 | -19 | 35
73242619 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I |  | 0 | 4 | 4
73242619 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 25 | 13 | -12 | 25
73242619 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 40 | 59 | 19 | 40
73242619 | 100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T |  | 1 | 1 | 0
73242619 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL |  | 0 | 4 | 4
73242619 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL |  | 0 | 51 | 51
73242619 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 7300 | 8056 | 756 | 7623.1882
73242619 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 20 | 20 | 0
73242619 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 12 | 12 | 0
73242619 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 60 | 58 | -2 | 60
73242619 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 13 | 13 | 0 | 13
73242619 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 390 | 390
73242619 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 2650 | 81 | -2569 | 3512.3499
73242619 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 8 | 5 | -3
73242619 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 61 | 54 | -7 | 61
73242619 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 20 | 6 | -14 | 20
73242619 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 2 | 4 | 2 | 4
73242619 | 100057790 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G |  | 0 | 1 | 1
73242619 | 100061029 | POLE_WOOD, PINE, 45FT, CL 1 | EA | 0 | 2 | 2 | 2
73242619 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, |  | 0 | 3 | 3
73242619 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 25 | 38 | 13 | 25
73242619 | 100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 0 | 3 | 3
73242619 | 100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 10 | 3 | -7 | 10
73242619 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 13 | 0 | -13 | 13
73242619 | 100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, |  | 0 | 3 | 3
73242619 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 31 | 28 | -3 | 31
73242619 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 6 | 6 | 0 | 6
73242619 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 35 | 37 | 2 | 35
73242619 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 10 | 14 | 4 | 10
73242619 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 18 | 18 | 15
73242619 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 48 | 44 | -4 | 48
73242619 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL | EA | 6 | 6 | 0 | 6
73242619 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 12 | 8 | -4 | 12
73242619 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 15 | 15 | 0 | 15
73242619 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 4 | 8 | 4 | 4
73242619 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 17 | 12 | -5
73242619 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 230 | 135 | -95 | 260
73242619 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 13 | 13 | 10
73242619 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 3 | 4 | 1 | 3
73242619 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 5 | 5 | 0 | 5
73242619 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 36 | 10 | -26 | 36
73242619 | 100097490 | ANCHOR_SCREW,TD,10 IN,STL/IRON,1-3/8 IN |  | 0 | 1 | 1
73242619 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC |  | 0 | 20 | 20
73242619 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 70 | 68 | -2 | 70
73242619 | 100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO | FT | 85 | 72 | -13 | 950
73242619 | 100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 10 | 0 | -10 | 10
73242619 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 450 | 411 | -39
73242619 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 |  | 0 | 20 | 20
73242619 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 6 | 6
73242619 | 100102696 | Guy Insulator Attachment | EA | 30 | 0 | -30 | 30
73242619 | 100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS |  | 0 | 4 | 4
73242619 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN |  | 0 | 28 | 28
73242619 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 17 | 4 | -13 | 17
73242619 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 18 | 18
73242619 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 23 | 23
73242619 | 100115241 | LINK_FUSE,UNV,15 AMP |  | 0 | 19 | 19
73242619 | 100289875 | POLE_WOOD,CEDAR,45 FT LG,CLASS 3 |  | 0 | 1 | 1
73242619 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 29 | 23 | -6 | 29
73242619 | 100302982 | BRACKET_MNTNG,POLETOP VRTCL,1-PHAS LP IN |  | 0 | 3 | 3
73242619 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 12 | 5 | -7 | 12
73242619 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 2 | 0 | -2 | 2
73242619 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 23 | 11 | -12 | 23
73242619 | 100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 4 | 1 | -3 | 4
73242619 | 100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 1 | 0 | -1 | 6
73242619 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 9 | 9 | 0 | 9
73242619 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 0 | 12 | 12
73242619 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 20 | 17 | -3 | 20
73242619 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 11 | 0 | -11
73242619 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 0 | 11 | 11
73242619 | 100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 10 | 3 | -7 | 10
73242619 | 100327860 | 3/4" x 7 3/4" Steel Pin with Lock Washer and Nut |  | 20 | 0 | -20
73242619 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F |  | 20 | 5 | -15
73242619 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 876 | 876 | 531.9149
73242619 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP |  | 0 | 12 | 12
73242619 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP |  | 0 | 7 | 7
73242619 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 6 | 6 | 0 | 5
73244139 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 42 | 16 | -26
73244139 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 18 | 9 | -9 | 18
73244139 | 100007567 | CONNECTOR_OVERHEAD,FIRED ON,1/0 AWG,ALUM | EA | 20 | 6 | -14 | 20
73244139 | 100007836 | WIRE_TIE,NO. 8,CU,54 IN LG | FT | 100 | 0 | -100 | 500
73244139 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR | EA | 10 | 5 | -5 | 10
73244139 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 |  | 22 | 9 | -13
73244139 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 38 | 16 | -22
73244139 | 100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 0 | 3 | 3
73244139 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 30 | 10 | -20
73244139 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 75
73244139 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L |  | 0 | 2 | 2
73244139 | 100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S |  | 0 | 10 | 10
73244139 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 | EA | 26 | 13 | -13 | 26
73244139 | 100018203 | POLE_WOOD, PINE, 40FT, CL 3 | EA | 0 | 3 | 3 | 3
73244139 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 200 | 321 | 121 | 200
73244139 | 100019342 | STRAP_GROUND,GALV STL |  | 96 | 88 | -8
73244139 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 48 | 44 | -4 | 48
73244139 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 34 | 40 | 6
73244139 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 12 | 0 | -12 | 12
73244139 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 120 | 78 | -42 | 120
73244139 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 180 | 248 | 68 | 180
73244139 | 100024531 | CONNECTOR_CABLE,PARRELL,ALUM,ACSR/ALUM,N |  | 0 | 3 | 3
73244139 | 100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 | EA | 20 | 8 | -12 | 20
73244139 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 326 | 302 | -24 | 326
73244139 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV |  | 0 | 7 | 7
73244139 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, | EA | 15 | 13 | -2 | 15
73244139 | 100032688 | ROPE_WIRE,5/16 IN DIA,STL,5000 FT LG REE |  | 0 | 0 | 0
73244139 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 10 | 17 | 7 | 10
73244139 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 22 | 40 | 18 | 22
73244139 | 100035087 | LINK_CHAIN,1 IN X 3-1/4 IN,GALV STL,5/8 |  | 0 | 7 | 7
73244139 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 15 | 9 | -6 | 15
73244139 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 60 | 16 | -44 | 60
73244139 | 100038906 | GUY_ASSY,5/16 IN DIA,165 FT LG,EHS STL S |  | 0 | 6 | 6
73244139 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 41 | 32 | -9 | 41
73244139 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 15 | 9 | -6 | 15
73244139 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 200 | 107 | -93 | 200
73244139 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 4416 | 2372 | -2044 | 4611.5067
73244139 | 100042242 | POLE_WOOD, PINE, 55FT, CL 1 | EA | 0 | 6 | 6 | 9
73244139 | 100042243 | POLE_WOOD, PINE, 60FT, CL 1 | EA | 0 | 5 | 5 | 2
73244139 | 100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR |  | 0 | 1 | 1
73244139 | 100043112 | CABLE_INSUL,XLPE,1/0 AWG,CU,7 STRANDD,1 |  | 900 | 854 | -46
73244139 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 6 | 4 | -2
73244139 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 7 | 7
73244139 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 105 | 111 | 6 | 105
73244139 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 15 | 21 | 6 | 15
73244139 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L | FT | 1460 | 1380 | -80 | 665.0471
73244139 | 100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 0 | 6 | 6
73244139 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 2770 | 58 | -2712 | 3891.6837
73244139 | 100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 | EA | 20 | 30 | 10 | 20
73244139 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 20 | 13 | -7
73244139 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 120 | 80 | -40 | 120
73244139 | 100053167 | CLAMP_DEADEND,STRGHT LINE,MALLEABLE/DUCT | EA | 30 | 0 | -30 | 30
73244139 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 56 | 36 | -20 | 56
73244139 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 15 | 9 | -6 | 30
73244139 | 100057790 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G |  | 0 | 2 | 2
73244139 | 100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 24 | 12 | -12
73244139 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, |  | 0 | 17 | 17
73244139 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 85 | 104 | 19 | 85
73244139 | 100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 0 | 18 | 18
73244139 | 100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 28 | 18 | -10 | 28
73244139 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 15 | 0 | -15 | 15
73244139 | 100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, |  | 0 | 18 | 18
73244139 | 100069509 | POLE_WOOD, PINE, 50FT, CL 1 |  | 0 | 1 | 1
73244139 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 12 | 20 | 8 | 12
73244139 | 100071576 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,2 AC |  | 0 | 1 | 1
73244139 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G |  | 0 | 9 | 9
73244139 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 84 | 40 | -44 | 84
73244139 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, |  | 0 | 6 | 6
73244139 | 100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, | EA | 30 | 34 | 4 | 30
73244139 | 100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | EA | 10 | 17 | 7 | 10
73244139 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 68 | 64 | -4 | 103
73244139 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 8 | 26 | 18 | 8
73244139 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 9 | 9
73244139 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 50 | 46 | -4 | 50
73244139 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 30 | 6 | -24 | 30
73244139 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 30 | 23 | -7 | 30
73244139 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 11 | 31 | 20 | 11
73244139 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 6 | 7 | 1
73244139 | 100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT |  | 10 | 17 | 7
73244139 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 176 | 167 | -9 | 176
73244139 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 19 | 19 | 19
73244139 | 100093755 | CABLE_INSUL,POWR,60 MIL XLPE,1/0 AWG,6 X |  | 0 | 1299 | 1299
73244139 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA |  | 0 | 8 | 8
73244139 | 100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM |  | 0 | 4 | 4
73244139 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 7 | 0 | -7 | 7
73244139 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 10 | 2 | -8 | 10
73244139 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 25 | 24 | -1 | 25
73244139 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC | EA | 11 | 25 | 14 | 15
73244139 | 100097596 | Insulator_Spool |  | 15 | 0 | -15
73244139 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 16 | 22 | 6 | 16
73244139 | 100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 28 | 0 | -28 | 28
73244139 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 0 | 222 | 222
73244139 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 63 | 7 | -56 | 63
73244139 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 22 | 22
73244139 | 100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 |  | 0 | 4 | 4
73244139 | 100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- |  | 0 | 5 | 5
73244139 | 100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 |  | 15 | 13 | -2
73244139 | 100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS | EA | 3 | 3 | 0 | 4
73244139 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN |  | 0 | 11 | 11
73244139 | 100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 |  | 0 | 17 | 17
73244139 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 9 | 9
73244139 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 | EA | 50 | 97 | 47 | 50
73244139 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 15 | 14 | -1 | 15
73244139 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 5226 | 5226 | 0 | 5246.4296
73244139 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 80 | 97 | 17 | 80
73244139 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 2 | 1 | -1 | 9
73244139 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 |  | 7 | 1 | -6
73244139 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 14 | 7 | -7 | 14
73244139 | 100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 2 | 3 | 1 | 2
73244139 | 100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 2 | 3 | 1 | 2
73244139 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. |  | 0 | 9 | 9
73244139 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 0 | 44 | 44
73244139 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 35 | 35 | 0 | 35
73244139 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 31 | 0 | -31
73244139 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 30 | 26 | -4
73244139 | 100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 28 | 18 | -10 | 28
73244139 | 100327860 | 3/4" x 7 3/4" Steel Pin with Lock Washer and Nut |  | 4 | 0 | -4
73244139 | 100328220 | BRACKET_MNTNG,STNDOFF,INSULTR,24 IN LG,F |  | 5 | 5 | 0
73244139 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB |  | 0 | 750 | 750
73244139 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP | EA | 3 | 3 | 0 | 3
73244139 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 10 | 8 | -2 | 10
73244139 | 100342373 | POLE_WOOD,PINE,45 FT LG,CLASS 2 |  | 0 | 1 | 1
73244139 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 3 | 3 | 0 | 3
73244139 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 3 | 3 | 0 | 3
73279347 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 0 | 6 | 6
73279347 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 0 | 2 | 2
73279347 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 |  | 0 | 1 | 1
73279347 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 367 | 222 | -145 | 367
73279347 | 100019342 | STRAP_GROUND,GALV STL |  | 0 | 8 | 8
73279347 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 2 | 4 | 2 | 2
73279347 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 14 | 6 | -8 | 14
73279347 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 40 | 14 | -26 | 40
73279347 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 175 | 131 | -44 | 175
73279347 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 250 | 125 | -125 | 250
73279347 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV |  | 0 | 9 | 9
73279347 | 100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 0 | 96 | 96
73279347 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 51 | 35 | -16 | 51
73279347 | 100036719 | NUT_EYE,5/8 IN,GALV STL |  | 0 | 20 | 20
73279347 | 100036858 | BRACKET_SUPPORT,TERMINATN/ARSTR |  | 0 | 1 | 1
73279347 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 60 | 39 | -21 | 60
73279347 | 100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T |  | 6 | 0 | -6
73279347 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL |  | 0 | 1 | 1
73279347 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 42 | 30 | -12
73279347 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 145 | 90 | -55 | 145
73279347 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 9 | 5 | -4 | 9
73279347 | 100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 200 | 0 | -200
73279347 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 130 | 130
73279347 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 0 | 4 | 4
73279347 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 4 | 16 | 12 | 4
73279347 | 100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS |  | 0 | 6 | 6
73279347 | 100056177 | CABLE_BARE,6 AWG,CU,SOLID,10000 FT LG,AS |  | 0 | 15 | 15
73279347 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 42 | 32 | -10 | 42
73279347 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 6 | 0 | -6 | 6
73279347 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 145 | 81 | -64 | 145
73279347 | 100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 0 | 16 | 16
73279347 | 100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 21 | 16 | -5 | 21
73279347 | 100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, |  | 0 | 16 | 16
73279347 | 100069647 | WIRE_TIE,NO. 8,CU,45 IN LG |  | 0 | 1 | 1
73279347 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 55 | 52 | -3 | 55
73279347 | 100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H |  | 0 | 12 | 12
73279347 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 58 | 59 | 1 | 58
73279347 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D |  | 0 | 6 | 6
73279347 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 18 | 29 | 11 | 18
73279347 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B |  | 0 | 12 | 12
73279347 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 1 | 1
73279347 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 1 | 0 | -1
73279347 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 187 | 73 | -114 | 187
73279347 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 |  | 0 | 3 | 3
73279347 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 2 | 1 | -1 | 2
73279347 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 60 | 60 | 0 | 60
73279347 | 100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 0 | 24 | 24
73279347 | 100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO |  | 180 | 144 | -36
73279347 | 100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 21 | 0 | -21 | 21
73279347 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 400 | 237 | -163
73279347 | 100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S |  | 0 | 24 | 24
73279347 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 |  | 0 | 9 | 9
73279347 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 2 | 2
73279347 | 100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- | EA | 20 | 12 | -8 | 20
73279347 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 20 | 18 | -2 | 20
73279347 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 6 | 0 | -6 | 6
73279347 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 81 | 81
73279347 | 100110238 | PIN_INSULATOR,LAG SCRW,5/8 IN,GALV STL,8 |  | 0 | 1 | 1
73279347 | 100115241 | LINK_FUSE,UNV,15 AMP |  | 0 | 22 | 22
73279347 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 144 | 81 | -63 | 144
73279347 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F |  | 0 | 1 | 1
73279347 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 |  | 0 | 2 | 2
73279347 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 13 | 1 | -12 | 13
73279347 | 100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN |  | 0 | 6 | 6
73279347 | 100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 13 | 4 | -9 | 13
73279347 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 10 | 6 | -4 | 10
73279347 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 0 | 4 | 4
73279347 | 100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 21 | 16 | -5 | 21
73301547 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 0 | 10 | 10
73301547 | 100007836 | WIRE_TIE,NO. 8,CU,54 IN LG |  | 0 | 8 | 8
73301547 | 100008297 | INSULATOR_PIN,1 IN DIA,PORCLN,F-NECK,LAR |  | 0 | 8 | 8
73301547 | 100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 0 | 1 | 1
73301547 | 100012488 | CUTOUT_FUSED,OPN,POLYMER,15KV MAX,110KV | EA | 0 | 0 | 0 | 1
73301547 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L | EA | 50 | 15 | -35 | 50
73301547 | 100017594 | INSULATOR_SUSP,DEADEND,4-1/4 IN,PORCLN,S |  | 5 | 0 | -5
73301547 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 270 | 175 | -95 | 270
73301547 | 100019342 | STRAP_GROUND,GALV STL |  | 80 | 28 | -52
73301547 | 100019758 | NUT_SQUARE,5/8 IN,GALV STL,11 TPI |  | 0 | 6 | 6
73301547 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 44 | 14 | -30 | 44
73301547 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 0 | 10 | 10
73301547 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 10 | 0 | -10 | 10
73301547 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 68 | 50 | -18 | 68
73301547 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 400 | 166 | -234 | 400
73301547 | 100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 |  | 0 | 2 | 2
73301547 | 100025788 | POLE_WOOD, PINE, 50FT, CL3 |  | 0 | 3 | 3
73301547 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 300 | 223 | -77 | 300
73301547 | 100027126 | CLEVIS_STRN_INSUL,SECNDRY SRVC,PORCLN,1- | EA | 20 | 11 | -9 | 30
73301547 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV |  | 0 | 10 | 10
73301547 | 100032501 | CABLE_INSUL,TRIPLEX,60 MIL HMPE,1/0 AWG, |  | 0 | 2 | 2
73301547 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, | EA | 20 | 11 | -9 | 20
73301547 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL |  | 0 | 8 | 8
73301547 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 52 | 33 | -19 | 52
73301547 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 5 | 11 | 6 | 5
73301547 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 63 | 27 | -36 | 115
73301547 | 100039661 | BOLT_MACHINE,5/8 IN DIA,11 TPI,2 IN LG,G |  | 0 | 4 | 4
73301547 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 100 | 33 | -67 | 100
73301547 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 5800 | 6599 | 799 | 6056.7796
73301547 | 100042455 | DEADEND_PREFORMED,GRIP,24 IN LG,STL,ACSR |  | 0 | 2 | 2
73301547 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 50 | 28 | -22
73301547 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 2 | 2
73301547 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 120 | 76 | -44 | 120
73301547 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 21 | 22 | 1 | 21
73301547 | 100046669 | BOLT_MACHINE,5/8 IN DIA,11 TPI,4 IN LG,G |  | 0 | 8 | 8
73301547 | 100047695 | PIN_INSULATOR,HD,3/4 IN X 7 IN,GALV STL, |  | 0 | 6 | 6
73301547 | 100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 0 | 6 | 6
73301547 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 455 | 455
73301547 | 100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 0 | 2 | 2
73301547 | 100050777 | CABLE_INSUL,TRIPLEX,PE,1/0 AWG,ALUM,7 ST | FT | 975 | 66 | -909 | 1369.8165
73301547 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 0 | 1 | 1
73301547 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 68 | 50 | -18 | 68
73301547 | 100056177 | CABLE_BARE,6 AWG,CU,SOLID,10000 FT LG,AS |  | 0 | 6 | 6
73301547 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 20 | 24 | 4 | 20
73301547 | 100057790 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G | EA | 30 | 12 | -18 | 30
73301547 | 100057912 | BOLT_MACHINE,3/4 IN DIA,10 TPI,14 IN LG, |  | 0 | 6 | 6
73301547 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, | EA | 6 | 2 | -4 | 6
73301547 | 100062712 | Connector Wedge Al/Cu #6-1/0 | EA | 0 | 0 | 0 | 60
73301547 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 120 | 66 | -54 | 120
73301547 | 100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 0 | 9 | 9
73301547 | 100065179 | MOUNT_TRNSCST,VEE,GALV STL,3 TRANSFRMRS, | EA | 1 | 2 | 1 | 1
73301547 | 100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 6 | 9 | 3 | 6
73301547 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 21 | 0 | -21 | 21
73301547 | 100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, |  | 0 | 9 | 9
73301547 | 100069647 | WIRE_TIE,NO. 8,CU,45 IN LG |  | 0 | 16 | 16
73301547 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 43 | 33 | -10 | 43
73301547 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 15 | 18 | 3 | 15
73301547 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 47 | 40 | -7 | 47
73301547 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 30 | 21 | -9 | 60
73301547 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 29 | 22 | -7 | 29
73301547 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B |  | 0 | 2 | 2
73301547 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 28 | 28
73301547 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN |  | 0 | 10 | 10
73301547 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 12 | 3 | -9 | 12
73301547 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 18 | 20 | 2
73301547 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 245 | 192 | -53 | 245
73301547 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 8 | 8 | 26
73301547 | 100089217 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,4 F |  | 0 | 2 | 2
73301547 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 13 | 2 | -11 | 13
73301547 | 100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM |  | 0 | 1 | 1
73301547 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 |  | 0 | 1 | 1
73301547 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 |  | 0 | 1 | 1
73301547 | 100097576 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC |  | 12 | 1 | -11
73301547 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 50 | 32 | -18 | 50
73301547 | 100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO |  | 0 | 12 | 12
73301547 | 100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 6 | 0 | -6 | 6
73301547 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 500 | 460 | -40
73301547 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 |  | 0 | 10 | 10
73301547 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 7 | 7
73301547 | 100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 |  | 0 | 1 | 1
73301547 | 100105348 | CK_INSULATOR,SECNDRY,PORCLN SPOOLS,ANS |  | 0 | 2 | 2
73301547 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN | EA | 50 | 15 | -35 | 50
73301547 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 13 | 2 | -11 | 13
73301547 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 6 | 6
73301547 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 50 | 52 | 2
73301547 | 100110238 | PIN_INSULATOR,LAG SCRW,5/8 IN,GALV STL,8 |  | 0 | 2 | 2
73301547 | 100111680 | CABLE_INSUL,XLPE,3/0 AWG,ALUM,19 STRANDD |  | 0 | 896 | 896
73301547 | 100115241 | LINK_FUSE,UNV,15 AMP |  | 0 | 23 | 23
73301547 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 17310 | 6390 | -10920 | 17377.6688
73301547 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 90 | 44 | -46 | 90
73301547 | 100302982 | BRACKET_MNTNG,POLETOP VRTCL,1-PHAS LP IN | EA | 6 | 2 | -4 | 6
73301547 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 |  | 0 | 2 | 2
73301547 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 4 | 1 | -3 | 5
73301547 | 100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 4 | 11 | 7 | 5
73301547 | 100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 5 | 3 | -2 | 4
73301547 | 100311653 | CONNECTOR_TAP,WDGE,ALUM ALLOY |  | 0 | 16 | 16
73301547 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 28 | 24 | -4 | 28
73301547 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 0 | 14 | 14
73301547 | 100319274 | RACK_INSULATOR,HD TRIPLX SECNDRY,PORCLN | EA | 34 | 19 | -15 | 34
73301547 | 100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 6 | 9 | 3 | 6
73301547 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 2 | 2 | 1063.8298
73301547 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP |  | 0 | 6 | 6
73301547 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 15 | 8 | -7 | 15
73301547 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 5 | 2 | -3 | 5
73301547 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 2 | 1 | -1 | 2
73301547 | 300014341 | TRANSFORMER_DISTR,ISOLATION/OIL FILLED/P |  | 0 | 3 | 3
73301585 | 100001517 | LINK_FUSE,UNV,10 AMP |  | 0 | 9 | 9
73301585 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 0 | 2 | 2
73301585 | 100006750 | BOLT_MACHINE,5/8 IN DIA,11 TPI,8 IN LG,G |  | 0 | 1 | 1
73301585 | 100009193 | GUY_ASSY,5/16 IN DIA,125 FT LG,EHS STL S |  | 0 | 4 | 4
73301585 | 100010379 | LEAD_ELECT,SECNDRY,10 FT LG,CU,1/0 AWG |  | 0 | 3 | 3
73301585 | 100012488 | CUTOUT_FUSED,OPN,POLYMER,15KV MAX,110KV | EA | 1 | 1 | 0 | 2
73301585 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 0 | 1 | 1
73301585 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 |  | 0 | 19 | 19
73301585 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 475 | 256 | -219 | 475
73301585 | 100019342 | STRAP_GROUND,GALV STL |  | 0 | 12 | 12
73301585 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 10 | 6 | -4 | 10
73301585 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 0 | 1 | 1
73301585 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 31 | 0 | -31 | 31
73301585 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 2 | 12 | 10 | 2
73301585 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 300 | 212 | -88 | 300
73301585 | 100024784 | MOUNT_TRNSCST,GALV STL,3 TRANSFRMRS,5/8 |  | 0 | 1 | 1
73301585 | 100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 | EA | 100 | 18 | -82 | 100
73301585 | 100025788 | POLE_WOOD, PINE, 50FT, CL3 | EA | 0 | 25 | 25 | 29
73301585 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 200 | 293 | 93 | 200
73301585 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV |  | 0 | 3 | 3
73301585 | 100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 0 | 48 | 48
73301585 | 100027618 | CABLE_BARE,3/0 AWG,6 X 1 STRANDD,7670 FT |  | 0 | 4016 | 4016
73301585 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, |  | 0 | 1 | 1
73301585 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 21 | 1 | -20 | 21
73301585 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 110 | 102 | -8 | 110
73301585 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 2 | 15 | 13 | 2
73301585 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 10 | 16 | 6 | 10
73301585 | 100036858 | BRACKET_SUPPORT,TERMINATN/ARSTR |  | 13 | 14 | 1
73301585 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 53 | 52 | -1 | 169
73301585 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL | EA | 2 | 15 | 13 | 2
73301585 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 30 | 63 | 33 | 30
73301585 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT |  | 6000 | 416 | -5584
73301585 | 100042242 | POLE_WOOD, PINE, 55FT, CL 1 |  | 0 | 2 | 2
73301585 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 200 | 114 | -86
73301585 | 100043158 | CONNECTOR_CABLE,WDGE,ALUM,ACSR,1/0 AWG A |  | 0 | 1 | 1
73301585 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 140 | 72 | -68 | 140
73301585 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 40 | 42 | 2 | 40
73301585 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 195 | 195
73301585 | 100049622 | LEAD_ELECT,SECNDRY,10 FT LG,CU,4/0 AWG |  | 0 | 6 | 6
73301585 | 100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 | EA | 21 | 2 | -19 | 21
73301585 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 80 | 30 | -50
73301585 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 2 | 13 | 11 | 2
73301585 | 100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | EA | 3 | 3 | 0 | 3
73301585 | 100056177 | CABLE_BARE,6 AWG,CU,SOLID,10000 FT LG,AS |  | 0 | 210 | 210
73301585 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT | EA | 120 | 144 | 24 | 120
73301585 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 2 | 15 | 13 | 2
73301585 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, |  | 0 | 3 | 3
73301585 | 100062712 | Connector Wedge Al/Cu #6-1/0 | EA | 0 | 0 | 0 | 70
73301585 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 140 | 69 | -71 | 140
73301585 | 100064203 | NUT_SQUARE,3/4 IN,HOT GALV STL,10 TPI |  | 0 | 72 | 72
73301585 | 100065979 | WASHER_LOCKING,REGULAR,3/4 IN,GALV STL A | EA | 58 | 72 | 14 | 58
73301585 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 0 | 0 | 0 | 1
73301585 | 100069293 | BOLT_MACHINE,3/4 IN DIA,10 TPI,16 IN LG, | EA | 75 | 72 | -3 | 75
73301585 | 100069509 | POLE_WOOD, PINE, 50FT, CL 1 | EA | 0 | 2 | 2 | 2
73301585 | 100069647 | WIRE_TIE,NO. 8,CU,45 IN LG |  | 0 | 14 | 14
73301585 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 30 | 28 | -2 | 30
73301585 | 100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H |  | 0 | 6 | 6
73301585 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 120 | 114 | -6 | 120
73301585 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 6 | 30 | 24 | 6
73301585 | 100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, |  | 0 | 6 | 6
73301585 | 100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | EA | 0 | 1 | 1 | 50
73301585 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 9 | 9 | 32
73301585 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 |  | 0 | 3 | 3
73301585 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B |  | 0 | 6 | 6
73301585 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 14 | 14
73301585 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 10 | 8 | -2 | 10
73301585 | 100084565 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,1 |  | 0 | 1 | 1
73301585 | 100088028 | BRACKET_SUPPORT,POLETOP,13.75 X 4.12 X 4 |  | 24 | 22 | -2
73301585 | 100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT |  | 50 | 1 | -49
73301585 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 195 | 221 | 26 | 195
73301585 | 100094846 | SCREW_LAG,3/8 IN DIA,4 IN LG,HOT DIP GAL |  | 0 | 1 | 1
73301585 | 100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM | EA | 12 | 11 | -1 | 12
73301585 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 3 | 3 | 0 | 3
73301585 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 |  | 0 | 2 | 2
73301585 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 6 | 19 | 13 | 6
73301585 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 |  | 0 | 6 | 6
73301585 | 100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 0 | 12 | 12
73301585 | 100099738 | 3/4" X 10" Machine Bolt, Galv. Steel | EA | 58 | 0 | -58 | 58
73301585 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 300 | 350 | 50
73301585 | 100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S |  | 0 | 12 | 12
73301585 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 |  | 0 | 3 | 3
73301585 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 3 | 3
73301585 | 100102696 | Guy Insulator Attachment | EA | 0 | 0 | 0 | 10
73301585 | 100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 | EA | 30 | 11 | -19 | 30
73301585 | 100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 |  | 0 | 1 | 1
73301585 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN |  | 0 | 3 | 3
73301585 | 100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 |  | 0 | 1 | 1
73301585 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 60 | 47 | -13
73301585 | 100110238 | PIN_INSULATOR,LAG SCRW,5/8 IN,GALV STL,8 |  | 0 | 14 | 14
73301585 | 100113829 | BOLT_EYE,5/8 IN DIA,11 TPI,10 IN LG,GALV |  | 0 | 1 | 1
73301585 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 28 | 18 | -10 | 28
73301585 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 21750 | 12048 | -9702 | 21835.0258
73301585 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 135 | 47 | -88 | 135
73301585 | 100303366 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 | EA | 1 | 1 | 0 | 1
73301585 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 15 | 16 | 1 | 15
73301585 | 100310427 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 2 | 1 | -1 | 2
73301585 | 100310428 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 4 | 4 | 0 | 4
73301585 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 120 | 84 | -36 | 120
73301585 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 0 | 6 | 6
73301585 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 0 | 19 | 19
73301585 | 100322238 | INSULATOR_SUPPORT,DISTRBTN RISR,19.7 IN | EA | 58 | 72 | 14 | 58
73301585 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 1875 | 1875 | 638.2979
73301585 | 100339983 | FUSE_ASSY,CURLMTG,7.6KV,30 AMP | EA | 2 | 3 | 1 | 2
73301585 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 3 | 3 | 0 | 3
73305080 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 0 | 12 | 12
73305080 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 4 | 0 | -4 | 4
73305080 | 100008748 | INSULATOR_STRAIN,GUY,27 IN LG,FBRGLAS 18 |  | 4 | 0 | -4
73305080 | 100013784 | INSULATOR_STRAIN,GUY,30 IN LG,FBRGLAS 24 |  | 0 | 4 | 4
73305080 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 30
73305080 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 | EA | 16 | 16 | 0 | 16
73305080 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 104 | 126 | 22 | 104
73305080 | 100019342 | STRAP_GROUND,GALV STL |  | 64 | 64 | 0
73305080 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 32 | 32 | 0 | 32
73305080 | 100020751 | WIRE_TIE,NO. 4,ALUM,132 IN LG |  | 0 | 12 | 12
73305080 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 40 | 14 | -26 | 40
73305080 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 50 | 56 | 6 | 50
73305080 | 100024990 | TIE_CABLE,NYLON,0.30 IN WD,15.1 IN LG,3 | EA | 18 | 12 | -6 | 18
73305080 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 75 | 76 | 1 | 75
73305080 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 9 | 6 | -3 | 9
73305080 | 100027618 | CABLE_BARE,3/0 AWG,6 X 1 STRANDD,7670 FT |  | 2600 | 0 | -2600
73305080 | 100032667 | BOLT_MACHINE,5/8 IN DIA,11 TPI,10 IN LG, |  | 0 | 16 | 16
73305080 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 24 | 12 | -12 | 24
73305080 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 26 | 14 | -12 | 26
73305080 | 100035876 | ANCHOR_SCREW,TD, HELIX SHAFT ASSY,8-10 I | EA | 4 | 4 | 0 | 4
73305080 | 100036719 | NUT_EYE,5/8 IN,GALV STL | EA | 6 | 6 | 0 | 6
73305080 | 100036858 | BRACKET_SUPPORT,TERMINATN/ARSTR |  | 5 | 0 | -5
73305080 | 100039653 | ADAPTER_PIPE,GUY,18 IN LG,GALV STL |  | 0 | 4 | 4
73305080 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL | EA | 28 | 36 | 8 | 28
73305080 | 100042242 | POLE_WOOD, PINE, 55FT, CL 1 | EA | 0 | 2 | 2 | 2
73305080 | 100042243 | POLE_WOOD, PINE, 60FT, CL 1 | EA | 0 | 1 | 1 | 1
73305080 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 0 | 6 | 6
73305080 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 45 | 42 | -3 | 45
73305080 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 15 | 2 | -13 | 15
73305080 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L | FT | 0 | 1040 | 1040 | 355.2991
73305080 | 100050858 | CLAMP_CABLE,MALLEABLE DI OR MI,0.16 IN-0 | EA | 24 | 28 | 4 | 24
73305080 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 12 | 11 | -1
73305080 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 14 | 14 | 0 | 14
73305080 | 100052588 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,477K |  | 25 | 24 | -1
73305080 | 100056487 | CABLE_BARE,1/0 AWG,CU,7 STRAND,ASTM B8/A |  | 0 | 2456 | 2456
73305080 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 4 | 4 | 0 | 4
73305080 | 100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 24 | 21 | -3
73305080 | 100062663 | BOLT_MACHINE,5/8 IN DIA,11 TPI,14 IN LG, |  | 0 | 12 | 12
73305080 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 36 | 36 | 0 | 36
73305080 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 3 | 0 | -3 | 3
73305080 | 100070266 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,5 F | EA | 4 | 4 | 0 | 4
73305080 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 24 | 24 | 0 | 24
73305080 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 16 | 16 | 0 | 24
73305080 | 100074517 | TIE_CABLE,NYLON,3/32 IN WD,5-1/4 IN LG, |  | 0 | 24 | 24
73305080 | 100074602 | ROD_ARMOR,ALUM ALLOY,56 IN LG,ACSR,3/0,6 | EA | 12 | 12 | 0 | 32
73305080 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 48 | 48 | 15
73305080 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 2 | 2 | 0 | 2
73305080 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 6 | 0 | -6 | 6
73305080 | 100088112 | BRACKET_MNTNG,SHEILD WIRE,MALLEABLE/DUCT |  | 20 | 12 | -8
73305080 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 42 | 28 | -14 | 50
73305080 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 4 | 0 | -4 | 4
73305080 | 100094898 | DEADEND_PREFORMED,GRIP,10 IN LG,STL,ALUM |  | 0 | 6 | 6
73305080 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 7 | 7 | 0 | 7
73305080 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 4 | 4 | 0 | 4
73305080 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 0 | 10 | 10
73305080 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 9 | 6 | -3 | 9
73305080 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 16 | 16
73305080 | 100102696 | Guy Insulator Attachment | EA | 4 | 0 | -4 | 4
73305080 | 100102973 | THIMBLE_WIRE_ROPE,5/8 IN DIA,GALV STL,1 | EA | 8 | 6 | -2 | 8
73305080 | 100103644 | SUPPORT_WIRE,DWNLEAD,18 IN,FBRGLAS ROD,5 |  | 24 | 16 | -8
73305080 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 4 | 0 | -4 | 4
73305080 | 100107159 | POLE_WOOD, PINE, 55FT, CL 3 | EA | 0 | 12 | 12 | 12
73305080 | 100108386 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,6 |  | 12 | 12 | 0
73305080 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 36 | 36
73305080 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 7850 | 7464 | -386 | 7880.6875
73305080 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 36 | 36 | 0 | 36
73305080 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 2 | 2 | 0 | 2
73305080 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 | EA | 0 | 32 | 32 | 32
73305080 | 100321662 | ATTACHMENT_MNTNG,GUY, NO CLEATS,4 IN,DUC |  | 4 | 4 | 0
73305080 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 160 | 160 | 425.5319
73358165 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 18 | 20 | 2
73358165 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 0 | 1 | 1
73358165 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 11
73358165 | 100017321 | TIE_INSULATOR,1-3/4 IN DIA,23 IN-25 IN L |  | 0 | 1 | 1
73358165 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH |  | 0 | 8 | 8
73358165 | 100019342 | STRAP_GROUND,GALV STL |  | 0 | 4 | 4
73358165 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG |  | 0 | 2 | 2
73358165 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, | EA | 15 | 0 | -15 | 15
73358165 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, |  | 0 | 5 | 5
73358165 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 15 | 25 | 10 | 15
73358165 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 11 | 0 | -11 | 11
73358165 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV |  | 0 | 5 | 5
73358165 | 100036719 | NUT_EYE,5/8 IN,GALV STL |  | 0 | 7 | 7
73358165 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT | FT | 350 | 0 | -350 | 365.4953
73358165 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 11 | 7 | -4 | 11
73358165 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 3 | 0 | -3 | 3
73358165 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 65 | 65
73358165 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 3 | 4 | 1
73358165 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 15 | 0 | -15 | 15
73358165 | 100057791 | INSULATOR_SPOOL,WET,PORCLN,3 IN HT,SKY G |  | 0 | 1 | 1
73358165 | 100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 18 | 18 | 0
73358165 | 100058551 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 0 | 6 | 6
73358165 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 3 | 0 | -3 | 3
73358165 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K | EA | 3 | 0 | -3 | 3
73358165 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 18 | 28 | 10 | 18
73358165 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 3 | 3 | 3
73358165 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 3 | 0 | -3 | 3
73358165 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR |  | 0 | 4 | 4
73358165 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 15 | 22 | 7 | 15
73358165 | 100088575 | POLE_WOOD, PINE, 45FT, CL 3 | EA | 0 | 3 | 3 | 3
73358165 | 100093755 | CABLE_INSUL,POWR,60 MIL XLPE,1/0 AWG,6 X |  | 0 | 201 | 201
73358165 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 5 | 7 | 2 | 5
73358165 | 100097571 | INSULATOR_STRAIN,DEADEND,3 IN SPOOL,PORC. |  | 0 | 4 | 4
73358165 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 11 | 7 | -4 | 11
73358165 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 1 | 1
73358165 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 850 | 603 | -247 | 853.3228
73358165 | 100303361 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,10 |  | 0 | 1 | 1
73358165 | 100311653 | CONNECTOR_TAP,WDGE,ALUM ALLOY |  | 0 | 6 | 6
73358165 | 100319350 | RACK_INSULATOR,HD SECNDRY,PORCLN SPOOLS, |  | 5 | 0 | -5
73802595 | 100003861 | CLIP_STATIC,INSULTR DISTRBTN,5/8 IN DIA |  | 20 | 16 | -4
73802595 | 100004757 | MARKER_GUY,PLSTC,1 IN TO 2-1/2 IN DIA,PE | EA | 0 | 0 | 0 | 1
73802595 | 100012641 | BOLT_EYE,5/8 IN DIA,11 TPI,8 IN LG,GALV |  | 0 | 7 | 7
73802595 | 100015054 | Connector Wedge Al/Cu #6-#2 | EA | 0 | 0 | 0 | 10
73802595 | 100017876 | CONNECTOR_CABLE,TAP,BRNZ,CU,NO. 2 |  | 0 | 6 | 6
73802595 | 100018327 | WASHER_FLAT,5/8 IN ID,1-3/4 IN OD,WROUGH | EA | 230 | 149 | -81 | 230
73802595 | 100019342 | STRAP_GROUND,GALV STL |  | 0 | 24 | 24
73802595 | 100020717 | ROD_GROUND,5/8 IN DIA,CRBN STL,8 FT LG | EA | 6 | 12 | 6 | 6
73802595 | 100021353 | LINK_FUSE,UNV,30 AMP | EA | 8 | 0 | -8 | 8
73802595 | 100021354 | BOLT_MACHINE,5/8 IN DIA,11 TPI,16 IN LG, |  | 26 | 34 | 8
73802595 | 100023899 | BOLT_MACHINE,5/8 IN DIA,11 TPI,12 IN LG, | EA | 126 | 107 | -19 | 142
73802595 | 100026047 | WASHER_CURVED,3 IN X 3 IN,MALLEABLE/DUCT | EA | 88 | 99 | 11 | 88
73802595 | 100027139 | STUD_INSULATOR,3/4 IN DIA X 7 IN LG,GALV | EA | 16 | 16 | 0 | 16
73802595 | 100027540 | CABLE_INSUL,XLPE,4/0 AWG,CU,19 STRANDD |  | 0 | 240 | 240
73802595 | 100031258 | PLATE_ADAPTER,MOUNTNG |  | 0 | 3 | 3
73802595 | 100033980 | SCREW_LAG,1/2 IN DIA,4 IN LG,HOT DIP GAL | EA | 5 | 3 | -2 | 5
73802595 | 100034502 | BOLT_EYE,5/8 IN DIA,11 TPI,12 IN LG,GALV | EA | 4 | 0 | -4 | 4
73802595 | 100035985 | 40kV Suspension Deadend Insulator | EA | 3 | 0 | -3 | 3
73802595 | 100036719 | NUT_EYE,5/8 IN,GALV STL |  | 0 | 28 | 28
73802595 | 100039650 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 0 | 6 | 6
73802595 | 100039652 | ROD_ANCHOR,5/8 IN DIA,GALV STL,7 FT LG,T |  | 6 | 0 | -6
73802595 | 100039663 | WASHER_LOCKING,DBL COIL,5/8 IN,GALV STL |  | 0 | 7 | 7
73802595 | 100039664 | WASHER_FLAT,3/4 IN ID,2 IN OD,WROUGHT ST |  | 0 | 6 | 6
73802595 | 100039761 | CABLE_BARE,1/0 AWG,6 X 1 STRANDD,6095 FT |  | 0 | 48 | 48
73802595 | 100042243 | POLE_WOOD, PINE, 60FT, CL 1 | EA | 0 | 1 | 1 | 1
73802595 | 100043150 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM/CU,2 |  | 0 | 12 | 12
73802595 | 100043531 | INSULATOR_ELECT,CLAMP TOP,28KV,POLYMER,I | EA | 115 | 79 | -36 | 115
73802595 | 100045998 | ARRESTER_SURGE,DISTRBTN,POLYMER,METL OXI | EA | 12 | 9 | -3 | 12
73802595 | 100047463 | CONNECTOR_OVERHEAD,BOLTED, 1/0-4/0 AWG,BR | EA | 12 | 12 | 0 | 12
73802595 | 100048129 | WASHER_LOCKING,DBL COIL,3/4 IN,GALV STL |  | 450 | 6 | -444
73802595 | 100048429 | CABLE_BARE,GRND,2 AWG,CU,SOLID,5000 FT L |  | 0 | 426 | 426
73802595 | 100049677 | PADLOCK_ASSY,1-1/2 IN CASE |  | 0 | 6 | 6
73802595 | 100051352 | INSULATOR_STRAIN,CONDUCTOR DEADEND,25 IN |  | 4 | 4 | 0
73802595 | 100052587 | WASHER_SQUARE,2-1/4 IN X 2-1/4 IN,3/16 I | EA | 26 | 41 | 15 | 26
73802595 | 100052588 | CONNECTOR_CABLE,WDGE,ALUM,ACSR/ALUM,477K |  | 20 | 18 | -2
73802595 | 100053167 | CLAMP_DEADEND,STRGHT LINE,MALLEABLE/DUCT |  | 0 | 10 | 10
73802595 | 100054802 | SWITCH_MANUAL,DISC,15KV,600 AMP,2 CNTCTS | EA | 12 | 12 | 0 | 12
73802595 | 100057013 | WASHER_CURVED,4 IN X 4 IN,MALLEABLE/DUCT |  | 0 | 6 | 6
73802595 | 100057672 | ROD_ANCHOR,EXT,1-1/2 IN DIA,GALV STL,3-1 | EA | 6 | 0 | -6 | 6
73802595 | 100058550 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 35 | 0 | -35
73802595 | 100058551 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS |  | 0 | 25 | 25
73802595 | 100062852 | STUD_INSULATOR,3/4 IN DIA X 1-3/4 IN LG, | EA | 105 | 63 | -42 | 105
73802595 | 100068975 | Fuse & Arrester Mounting Bracket | EA | 12 | 0 | -12 | 12
73802595 | 100070377 | CUTOUT_FUSED,OPN,POLYMER,7.2-14.4KV,110K |  | 30 | 25 | -5
73802595 | 100071675 | LUG_CMPRSSN,TERMNL,4/0 AWG,TINNED CU,2-H |  | 50 | 24 | -26
73802595 | 100072154 | SCREW_LAG, 1/4 IN DIA,2 IN LG,GALV STL,HE |  | 0 | 150 | 150
73802595 | 100073413 | BRACKET_MNTNG,KIT,ARSTR,1/4 IN THK MIN,G | EA | 9 | 9 | 0 | 9
73802595 | 100073592 | INSULATOR_SUSP,DEADEND,12-3/4(+-1/4) IN, | EA | 39 | 41 | 2 | 39
73802595 | 100073619 | BOLT_EYE,5/8 IN DIA,11 TPI,14 INLG,GALV |  | 0 | 2 | 2
73802595 | 100073793 | GUARD_PROTCT,U CABLE,2-1/4 IN WD,PLSTC,6 |  | 0 | 18 | 18
73802595 | 100074493 | DEADEND_PREFORMED,GUY GRIP,38 IN LG,STL, | EA | 6 | 0 | -6 | 6
73802595 | 100075415 | GUARD_PROTCT,GRND WIRE MOLDING,1 IN WD,D | EA | 0 | 18 | 18 | 50
73802595 | 100076569 | BOLT_MACHINE,3/4 IN DIA,10 TPI,12 IN LG, |  | 0 | 6 | 6
73802595 | 100076666 | BRACKET_MNTNG,NEMA,ARSTR,3/8 IN X 1-3/4 | EA | 15 | 16 | 1 | 15
73802595 | 100079751 | CONNECTOR_CABLE,GRND,NO.10-NO.1,1/2 IN,B | EA | 20 | 21 | 1 | 20
73802595 | 100081480 | CONNECTOR_CABLE,TAP,BRNZ,NO. 6,SPLIT BOL |  | 0 | 9 | 9
73802595 | 100082948 | DEADEND_PREFORMED,GUY GRIP,31 IN LG,STL, | EA | 6 | 0 | -6 | 6
73802595 | 100083862 | CLAMP_DEADEND,STRGHT LINE,ALUM ALLOY,ACS | EA | 10 | 0 | -10 | 10
73802595 | 100084202 | BOLT_MACHINE,3/8 IN DIA,16 TPI,10 IN LG, |  | 0 | 1 | 1
73802595 | 100084645 | DEADEND_PREFORMED,34 IN LG,ALUM,0.030 IN | EA | 9 | 9 | 0 | 9
73802595 | 100085230 | DEADEND_PREFORMED,GRIP,27 IN LG,STL,ACSR | EA | 6 | 0 | -6 | 6
73802595 | 100088479 | WASHER_LOCKING,HELICAL,5/8 IN,GALV STL A | EA | 46 | 57 | 11 | 46
73802595 | 100094865 | ANCHOR_POLE_BASE,8 IN,CAST IRON/STL,PISA | EA | 4 | 0 | -4 | 4
73802595 | 100095397 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,10 | EA | 4 | 4 | 0 | 4
73802595 | 100095608 | CROSSARM_ASSY,DEADEND WITH CENTR BRKT,8 | EA | 9 | 8 | -1 | 9
73802595 | 100095866 | INSULATOR_STRAIN,GUY,63 IN LG,FBRGLAS,CL | EA | 12 | 0 | -12 | 12
73802595 | 100097691 | CLAMP_JUMPER,BRNZ,CU,8-1/0 | EA | 50 | 74 | 24 | 50
73802595 | 100098979 | WASHER_LOCKING,REGULAR,7/8 IN OD,1/8 IN |  | 0 | 48 | 48
73802595 | 100099096 | CABLE_INSUL,WTHRPRF,45 MIL XLPE,2 AWG,SO |  | 200 | 164 | -36
73802595 | 100100489 | CABLE_INSUL,XLPE,6 AWG,CU,SOLID,1 CONDUC |  | 450 | 300 | -150
73802595 | 100101009 | SCREW_CAP,1/2 IN DIA,13 TPI,2 IN LG,CU S | EA | 50 | 48 | -2 | 50
73802595 | 100101263 | WASHER_SQUARE,7/8 IN ID,3 IN X 3 IN,3/16 | EA | 12 | 16 | 4 | 12
73802595 | 100101751 | STAPLE_FASTENER,0.148 IN DIA X 1-1/2 INL |  | 0 | 6 | 6
73802595 | 100102696 | Guy Insulator Attachment | EA | 3 | 0 | -3 | 3
73802595 | 100103235 | CONNECTOR_CABLE,WDGE,ALUM,ALUM,477KCMIL- | EA | 20 | 24 | 4 | 20
73802595 | 100104417 | PIN_INSULATOR,XARM,5/8 IN X 6-1/2 IN,GAL | EA | 6 | 6 | 0 | 6
73802595 | 100104745 | LINK_FUSE,UNV,25 AMP | EA | 1 | 1 | 0 | 2
73802595 | 100105615 | BOLT_MACHINE,1/2 IN DIA,13 TPI,1-1/2 IN |  | 0 | 19 | 19
73802595 | 100106779 | ROD_ANCHOR,1 IN DIA,GALV STL,7 FT LG,TRI | EA | 9 | 0 | -9 | 9
73802595 | 100109390 | LEAD_ELECT,SECNDRY,10 FT LG,CU,2 AWG SOL |  | 0 | 6 | 6
73802595 | 100110224 | WASHER_SQUARE,9/16 IN ID,2 IN X 2 IN,1/8 |  | 0 | 63 | 63
73802595 | 100115241 | LINK_FUSE,UNV,15 AMP | EA | 8 | 8 | 0 | 8
73802595 | 100115939 | CABLE_BARE,636KCMIL,ALUM,37 STRAND,6200 | FT | 17640 | 16773 | -867 | 17708.9588
73802595 | 100301153 | BRACKET_MNTNG,STND OFF,LINE POST INSULTR | EA | 105 | 63 | -42 | 105
73802595 | 100303365 | CROSSARM_ASSY,TANGNT WITH CENTR BRKT,8 F | EA | 5 | 5 | 0 | 5
73802595 | 100310426 | BRACKET_MNTNG,15 DEG STNDOFF,FOR FUSE AN | EA | 8 | 8 | 0 | 8
73802595 | 100311653 | CONNECTOR_TAP,WDGE,ALUM ALLOY |  | 0 | 1 | 1
73802595 | 100317966 | CONNECTOR_OVERHEAD,HOT LINE,NO. 6-4/0,0. | EA | 9 | 6 | -3 | 9
73802595 | 100319272 | CONNECTOR_CABLE,GRNDING,CU,NO. 6-2/0 |  | 10 | 6 | -4
73802595 | 100329907 | ROPE_WIRE,EHS,7/16 IN DIA,20800 LB | FT | 0 | 0 | 0 | 372.3404
73802595 | 100336218 | 40kV Extension Link |  | 3 | 0 | -3
73802595 | 100339982 | FUSE_ASSY,CURLMTG,7.6KV,20 AMP | EA | 2 | 2 | 0 | 2
73802595 | 300014317 | REGULATOR_VLTG,BI-DIRECTIONAL STEP,4800/ | EA | 3 | 3 | 0 | 3
73802595 | 300014321 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 | EA | 0 | 2 | 2 | 2
73802595 | 300014322 | TRANSFORMER_DISTR,OIL FILLED/POLE,4800/8 |  | 2 | 0 | -2
Line items: | 1588

## Pending IM Confirmation
Materials Pending DTE IM Confirmation
These materials appear in construction BOMs or supplier order records without a confirmed DTE IM number. The closest candidate IM from DTE’s item master is proposed where one exists. DTE is requested to confirm or correct the IM assignment in the yellow column; quantities shown are excluded from the confirmed-IM tabs until then.
Material Description | BOM Qty | UOM | Ordered Qty (unresolved) | Proposed DTE IM (candidate) | Match Confidence | CWO Numbers | DTE Confirmed IM / Response
Ground Wire Molding | 309 | EA |  | 100075415 | MEDIUM DESCRIPTION; similarity 53% | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585; 73305080; 73358165
Ground Wire Staples | 3050 |  |  | 100101751 | VERY LOW DESCRIPTION; similarity 0% | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585; 73305080; 73358165
Molding Staples | 2915 |  |  | 100101751 | VERY LOW DESCRIPTION; similarity 0% | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73301585; 73305080; 73358165
45' CLASS 3 PINE | 83 | EA |  | 100088575 | LOW DESCRIPTION; similarity 43% | 73232522; 73234686; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619; 73244139; 73301547; 73358165
7/16" Guy Wire, Rope Wire | 5000 | FT |  | 100329907 | MEDIUM DESCRIPTION; similarity 68% | 73232522; 73239926; 73240913; 73242557; 73242619; 73301547; 73301585; 73305080; 73802595
#6 AWG Stranded Bare Copper Wire | 10305 |  |  | 100039761 | LOW; similarity 42% | 73232522; 73239897; 73239926; 73242557; 73242619; 73244139; 73305080; 73358165
Crimipit, #6 AWG to #6 AWG | 345 |  |  | 100100489 | LOW; similarity 40% | 73232522; 73239897; 73239926; 73242557; 73242619; 73244139; 73305080; 73358165
Wire #2 Cu Sol Bare SD 2500ft reels |  | FT | 5192.8333 | 100048429 | LOW; similarity 32% | 73234686; 73239916; 73240913; 73279347; 73301547; 73301585; 73802595
45' CLASS 3 CEDAR | 84 | EA | 84 | 100289875 | HIGH; similarity 85% | 73232522; 73239897; 73239916; 73239926; 73240913; 73242557; 73242619
5/16" Guy Wire, Rope Wire | 5575 |  |  | 100032688 | MEDIUM DESCRIPTION; similarity 66% | 73232522; 73239926; 73240913; 73242557; 73242619; 73244139
Crimipit, 2 AWG to 2 AWG | 310 |  |  | 100004757 | LOW; similarity 40% | 73234686; 73239916; 73240913; 73301547; 73301585
55' CLASS 1 PINE | 26 | EA |  | 100042242 | LOW DESCRIPTION; similarity 43% | 73234686; 73239926; 73240913; 73244139; 73305080
60' CLASS 1 PINE | 7 | EA |  | 100042243 | LOW DESCRIPTION; similarity 43% | 73234686; 73240913; 73244139; 73305080; 73802595
2 AWG Stranded Bare Copper Wire | 8150 |  |  | 100048429 | LOW DESCRIPTION; similarity 42% | 73234686; 73239916; 73240913; 73301585
5/8" Lock Nut | 90 |  |  | 100036719 | MEDIUM; similarity 64% | 73232522; 73239897; 73242619; 73305080
5/8" x 16" Machine Bolt, Galvanized Steel | 212 |  |  | 100024354 | HIGH; similarity 80% | 73232522; 73239897; 73242557; 73242619
50' CLASS 1 PINE | 14 | EA | 3 | 100069509 | LOW DESCRIPTION; similarity 43% | 73234686; 73239926; 73242557; 73301585
50' CLASS 3 PINE | 43 | EA |  | 100025788 | VERY LOW DESCRIPTION; similarity 21% | 73234686; 73240913; 73242557; 73301585
Washer Square 2x2 1/2 |  | EA | 147 | 100052587 | MEDIUM; similarity 67% | 73240913; 73242557; 73301547; 73301585
7/16" Guy Grip | 36 | EA | 26 | 100074493 | LOW; similarity 41% | 73232522; 73239897; 73305080
Armor Rod Alum. Alloy | 65 | EA |  | 100074602 | HIGH DESCRIPTION; similarity 81% | 73234686; 73242557; 73301585
Straight Line Deadend Clamp | 231 |  |  | 100039650 | HIGH DESCRIPTION; similarity 87% | 73234686; 73301547; 73301585
45' Class 1 CEDAR | 5 | EA | 5 | 100289876 | HIGH; similarity 85% | 73232522; 73239916; 73239926
55' CLASS 3 PINE | 14 | EA |  | 100107159 | LOW DESCRIPTION; similarity 43% | 73234686; 73240913; 73305080
Armor Rod Alum. Alloy | 29 |  |  | 100074602 | HIGH DESCRIPTION; similarity 81% | 73240913; 73305080
Machine Bolt, Galv. Steel | 28 |  |  | 100099738 | HIGH; similarity 85% | 73232522; 73802595
5/16" Guy Grip | 24 | EA | 6 | 100009193 | MEDIUM; similarity 59% | 73232522; 73239897
Single Phase Fiberglass Mounting Bracket | 31 |  |  | 100310426 | VERY LOW DESCRIPTION; similarity 16% | 73232522; 73242557
Bracket Mounting, Shield Wire, Malleable/Duct | 7 |  |  | 100088112 | MEDIUM DESCRIPTION; similarity 62% | 73234686; 73242557
40' CLASS 3 CEDAR | 3 | EA | 3 | 100313938 | HIGH; similarity 85% | 73240913; 73242557
40' CLASS 3 PINE | 4 | EA |  | 100018203 | LOW DESCRIPTION; similarity 43% | 73239926; 73244139
45' CLASS 1 PINE | 5 | EA |  | 100061029 | LOW DESCRIPTION; similarity 43% | 73234686; 73242619
50' CLASS 2 PINE | 2 | EA |  | 100024362 | LOW DESCRIPTION; similarity 43% | 73234686; 73240913
1/0 AWG Bare | 2600 |  |  | 100039761 | HIGH DESCRIPTION; similarity 82% | 73301547
2 Awg BARE | 375 | FT |  | 100048429 | HIGH DESCRIPTION; similarity 79% | 73242557
2 AWG Bare Copper | 780 | FT |  | 100048429 | MEDIUM DESCRIPTION; similarity 61% | 73305080
2AWG Stranded Bare Copper Wire | 2600 |  |  | 100048429 | VERY LOW DESCRIPTION; similarity 16% | 73301547
3/0 to 3/0 crimpit | 5 |  |  | 100111680 | LOW; similarity 40% | 73358165
40 CLASS 3 CEDAR | 1 | EA | 1 | 100313938 | HIGH; similarity 85% | 73232522
5/8" Eye Bolt and Nut x 26" | 6 |  |  | 100024354 | MEDIUM; similarity 51% | 73802595
5/8" Ground Clamp | 32 |  |  | 100017083 | MEDIUM; similarity 68% | 73305080
5/8" Lock Nut SQ. | 50 |  |  | 100036719 | MEDIUM; similarity 52% | 73242557
5/8" X 10" Machine Bolt, Galv. Steel | 30 |  |  | 100099738 | HIGH; similarity 70% | 73239926
5/8" x 14" Machine Bolt & Nut, Galvanized Steel | 121 | EA |  | 100062663 | LOW DESCRIPTION; similarity 50% | 73232522
55 CLASS 1 PINE | 1 | EA | 1 | 100042242 | LOW; similarity 43% | 73242557
55' CLASS H1 PINE | 1 | EA | 1 | 100342373 | LOW; similarity 41% | 73244139
636 to 636 crimpit | 20 |  |  | 100004757 | VERY LOW; similarity 26% | 73358165
Attachment_mntg, cleats | 10 |  |  | 100321662 | MEDIUM; similarity 53% | 73301585
parallel groove connector 636 AA to 636 AA | 50 |  |  | 100308950 | VERY LOW; similarity 28% | 73232522
P to P fiberglass mounting bracket | 6 |  |  | 100068975 | LOW; similarity 44% | 73232522
Phase to Phase Fiberglass Mounting Bracket | 2 | EA |  | 100310427 | VERY LOW DESCRIPTION; similarity 16% | 73242557
Three Phase Fiberglass Mounting Bracket | 6 | EA |  | 100310428 | VERY LOW DESCRIPTION; similarity 16% | 73242557
Insulator Guy Strain 18in 36K |  | EA | 4 | 100102696 | MEDIUM; similarity 57% | 73802595
Extension pole top fiberglass 54 |  | EA | 2 | 100317530 | MEDIUM; similarity 52% | 73239916
Bolt Oval Eye 5/8in x 16in with (1) square nut assembled |  | EA | 15 | 100024354 | LOW; similarity 36% | 73802595
Washer Lock Galv 7/8in |  | EA | 12 | 100327860 | LOW; similarity 49% | 73239916
5/8" Machine Bolt & Nut, Galv. Steel | 4 |  |  | 100024354 | MEDIUM; similarity 52% | 73242557
Single Phase Fiberglass Mounting Bracket | 5 |  |  | 100310426 | VERY LOW DESCRIPTION; similarity 16% | 73240913
45' CLASS 2 CEDAR | 2 | EA | 2 | 100341161 | HIGH; similarity 85% | 73239916
50' CLASS 3 CEDAR | 1 | EA | 1 | 100289875 | MEDIUM; similarity 62% | 73239926
35' CLASS 2 PINE | 1 | EA |  | 100042239 | VERY LOW DESCRIPTION; similarity 21% | 73239916
45' CLASS 2 PINE | 1 | EA | 1 | 100342373 | HIGH; similarity 85% | 73244139
45'' CLASS 4 PINE | 3 | EA | 3 | 100342373 | MEDIUM; similarity 62% | 73301547
Wire Pigeon 3/0 6/1 ACSR OH 2600ft |  | FT | 2600 | 100077194 | LOW; similarity 40% | 73305080

## Basis and Exclusions
Basis of Quantities, Exclusions, and Reservation of Rights
SOURCES
DTE CUE estimate material summaries | Per-CWO material requirement quantities by DTE IM (“CUE Required Qty”).
Construction bills of material | Per-CWO construction BOM quantities (“BOM Qty”).
Supplier order records (PLS) | Confirmed order allocations by CWO and IM; dollars cross-checked to the PLS purchase order report as of 7/28/2026.
DTE Maximo work-order quantities | Used as a cross-check only; program install quantities agree within ~5% overall and within 0.5% on conductor.
METHODOLOGY
• Quantities were reconciled independently for each of the 15 CWOs, then rolled up by DTE IM at the program level.
• Full 18-digit CUE item numbers were extracted from the CUE document text and normalized to 9-digit DTE IM numbers.
• Order-only line items carrying a valid or suffix-normalized DTE IM are included; unresolved items appear on the Pending IM Confirmation tab.
• Variance columns are calculated in-sheet (CUE Required − BOM) and recompute automatically.
EXCLUSIONS AND PENDING ITEMS
• DTE-furnished job stock is not included in ordered quantities; CUE Required quantities include all material regardless of furnishing party.
• Per-IM delivered quantities are pending a line-item export from the supplier (IM, qty ordered, qty delivered, PO number, promise date) and are not represented here.
• Underground CWOs removed from the program by credit are excluded in their entirety.
• Four recloser CWOs and CWO 73303193 are outside this reconciliation set and will follow under separate cover.
• Where a DTE IM spans mixed units of measure across sources, totals should be read with the UOM column; mixed-UOM lines are flagged in our working files.
RESERVATION OF RIGHTS
This package is a quantity reconciliation provided for informational and coordination purposes at DTE’s request. It is not an agreement to any credit, back-charge, price adjustment, or change to the scope or value of Contract 4400008681. All rights and remedies under the contract are expressly reserved. Any commercial adjustment arising from or related to the quantities herein shall be initiated and processed exclusively through the contract change process.